## Slide 1: Collaborative efforts and associated Financial support
New staging strategy –first 1-tour of a simplified PERLE by beginning 2028
Macro Vision on the PLANNING (detailed plans available)
What is needed ? Call for contributions !

## Slide 2: Collaborative efforts and associated Financial support
iSAS: European INFRA-TECH project 11 research partners (CNRS, CERN, ESS, DESY, VUB, CEA, HZB, INFN, UKRI, UL, EPFL). Financial support for the construction of the full LINAC cryomodule (with IN2P3 matching funds + CM vessel from ESS).
DC-gun + photocathode+ preparation chamber acquired by RI within a Collaboration Agreement. All material has been shipped to IJCLab end of January 2024. Laser has been also purchased and delivered.
We have proposed a project (ERL4ALL) to CNRS which should allow to finance the full injection line and a part of a first tour equipment. Money required 3,6M€. Led by Maud Baylac , Walid Kaabi. We received a first green light and the project will be presented within 2months for final decision/approval.
Discussions well advanced with HZB to recuperate part of the equipment of BESSY VSR - Cryogenic plant, valve box and transfer lines. Possibility to recuperate all materiel by Summer 2025.
Discussion on going for receiving in-kind some material from CBETA (quadrupoles essentially to equip the first tour of PERLE)
Increasing collaborations with
  CERN (R&D on 800MHz SRF Cavities (FCC) : production and post-production processes. Discussion well advanced
  LASA-Milano (cavities LINAC Cryomodule, booster, DC-gun/photocathode). Discussion started
  Jlab (Hom/Absorbers/cavities). Discussion on going
iSAS

## Slide 3
ISAS: Innovate for Sustainable Accelerating Systems
EU call HORIZON-INFRA-2023-TECH-01-01: New technologies and solutions for reducing the environmental and climate footprint of RIs. 5M€ total with important matching funds
The objective of iSAS is to innovate those technologies that have been identified as being a common core of SRF accelerating systems and that have the largest leverage for energy savings with a view to minimizing the intrinsic energy consumption in all phases of operation
Project lead by CNRS
  Scientific coordinator : J. D’Hondt (VUB)
  Project coordinator : A. Stocchi
International consortium :
  11 research partners (CNRS, CERN, ESS, DESY, VUB, CEA, HZB, INFN, UKRI, UL, EPFL)
  6 industrial partners
  SEEN FROM PERLE VIEW POINT IT ALLOWS TO FINANCE (with in-kind and matching funds)
  THE LINAC CRYOMODULE in Collaboration
  with IJCLab, CERN, CEA, ESS, INFN-LASA
Money already available since March 1st 2024, bid for cavities in preparation

## Slide 4: New staging strategy –first 1-tour of a simplified PERLE by beginning 2028
21m
Infrastructures and radioprotection
Financed by CPER funds
Cryogenic Plants.
In-kind from HZB + extra money requests
Injector + First tour
ERL4ALL Project on going
+in-kind needed (as CBETA ) …
Delivered@IJCLab
Financed through
iSAS Program
+ ESS + in-Kind IN2P3

## Slide 5: Macro Vision on the PLANNING (detailed plans available)
Site is now choosen : IGLOO !
(infrastructure studies started)
2024
2025
2026
2027
2028
First Loop
DC-Gun/Laser/FC
Injector
LINAC
Cryomodule
Delivered@Orsay
2nd 3rd Loop
Budget asked (decision in Spring)
Budget obtained
Budget partially asked (decision in Spring) in-kind needed
Designs/ Studies
Procuirement / Construction / Installation
Commissioning
Budget to be asked
If obtained within 2years. PERLE@250MeV could be completed in 2030
Today

## Slide 6: What is needed ? Call for contributions !
The budget situation is significantly improved in the last year,
but even in case we obtained ERL4ALL, to fully realise the PERLE 1-tour (as a first stage):
miss ~4M€ (less than 20% of total cost for 1-turn configuration)
We need your contributions
in-kind contributions from internal collaborators strongly strengthen our budget requests
These contributions could come also in-kind.
The missing items where important contributions could be decisive are :
Dipole Magnets
Cavities for boosters
Cryogenic equipment (to complete the Bessy in-kind)
Vacuum pumps
Some diagnostics
…
Let’s discuss,
but of course
we should have bilateral discussions