## Slide 1: e-driven ILC positron source and prototyping at KEK
2024/10/16
Y. Enomoto
On behalf of positron group
M. Fukuda, Y. Morikawa, M. Sato, H. Hayano
This work was supported by 【MEXT Development of key element technologies to improve the performance of future accelerators Program】 Japan Grant Number JPMXP1423812204.
TRISTAN
KEKB
SuperKEKB
ILC

## Slide 2: Comparison of positron sources
Chart: e- beam power (kW)
| 8.9999999999999993E-3 | 1.52E-2 | 4.2999999999999997E-2 | 0.125 | 4 | 0.91200000000000003 | 1 | 3.5 | 4 | 13.32 | 27 | 56.32 | 62.9 | 73.260000000000005
Ne+/Ne-/GeV | 0.073 | 0.063 | 0.05 | 0.014 | 0.0375 | 0.013 | 0.03 | 0.114 | 0.025 | 0.11667 | 0.036 | 0.28 | 0 | 0.43
●past
▲present
◆future
ILC e-driven
High power
High efficiency
SLC
SuperKEKB
FCCee
(many options)
ILC undulator
CLIC
CEPC
KEKB
BEPC
DAFNE
VEPP-5
 | SKEKB | ILC | FCC
e- energy | 3.2 GeV | 3 GeV | 
e- charge/bunch | 10 nC | 3.7 nC | 
Repetition | 50 (25) Hz | 5 Hz | 
Num. bunches | 2 | 1320 = (33+33) x 20 | 
Total charge / s | 1000 (500) nC | 24667 nC | 
Beam power on target | 3.2 | 74 | 
yield | 0.4 | 1.3 | 
Many options

## Slide 3: Prototype to be built by JFY2027
target
Flux concentrator
Acc. structure
solenoid

## Slide 4: 5 years-plan(as of 2024/3/28)
FY |  | 2022 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  | 
year |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 
Quarter |  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
Test bench |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
High power test bench |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
W-Cu connection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Target unit | Rotation mechanism |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Disk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FC base | 1st unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
magnet | Solenoid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Power supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chamber, vacuum, support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Acc. structure | 1st unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FC power supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design
Manufacuring
test
Now!

## Slide 5: What we did in JFY2023
Vacuum system
FC
Design and manufacture parts
Target
rotation mechanism
ACC structure
RF design, 3D model
Solenoid
Design and procurement of material

## Slide 6: What we plan to do in JFY2024
FC
assemble
solenoid
ACC structure
Manufacturing test
Target disk
Collimator with pillow seal

## Slide 7: Target
 | Technical design | Engineering design | 3D model | Drawings | Manufacturing | Evaluation
Rotation mechanism | Done | Done | Done | Done | Done | Done
Target disk | Done | Done | Done | Done | Done | In progress
Design and manufacturing of rotation mechanism done in FY2023
Design and manufacturing of target disk finished
Assembled into the chamber
  Vacuum test OK
  Rotation test OK
  run-out evaluation by laser displacement sensor is in progress
  Thermal contact evaluation between W and Cu is planned
Narrow gap1 for differential pumping 30um
Narrow gap2 for differential pumping 100um
Mechanical face seal
<10-5 Pa
~10-2 Pa
~101 Pa

## Slide 8
【purchase】NC50, φ470×t132
【lathe&mill】finish red line
【EBW】
【press fit】heat W ring, cool Cu disk
【lathe】finish red line part
【purchase】NC50, φ470×t20mm
【purchase】 φ500×t15.7
【lathe】finish all the part.
【lathe?】finish all the part.

## Slide 9
EBW
Cold fit
machining

## Slide 10: Cold fit W ring

## Slide 11: FC
FY2023
FY2024
Machining
done
EBW
done
Secondary working
Milling & EDM
done
Black plating
done
Welding & assembly
Parts(delivered)
feedthrough
flange, support
piping
electrode
bolt, pin, bush
coil

## Slide 12: FC
FY2023
FY2024
Machining
done
EBW
done
Secondary working
Milling & EDM
done
Black plating
done
Welding & assembly
Done
Parts(delivered)
feedthrough
flange, support
piping
electrode
bolt, pin, bush
coil

## Slide 13: Rotation test

## Slide 14: Water flow test and evaluation
tracer
・polyamide
・diameter 50 um
・1.03 g/cm3

## Slide 16: Target thermal and CFD simulation
Topic of US-Japan collaboration
Share 3D model and material information with JLab
First simulation result about velocity distribution and pressure drop from JLab

## Slide 17: Acc. Structure - concept
Challenges
Beam loading compensation
  High beam current : > 0.6A
  Multi bunch operation
Powerful cooling system is required.
  Very high heat load due to electromagnetic shower from the target
Remote beam flange connection
  High activation by shower from the target and the connection point is surrounded by solenoid coils
Design Policy
High group velocity
Large coupling β
Water channel in the
APS cavity with a bi-periodic structure that operates in the π/2 mode, which maximizes the group velocity.
17
Collimator(16.4%, 10.3kW)
CAV Entrance (7.0%, 4.4kW)
Cavity total (31.7%, 20.0kW)
1st disk (3.5% ,2.2kW)
Target(26.1%, 16.4kW)

## Slide 18: Acc. structure
Machining and bonding of test cell is in progress
Drawing preparation is almost finished
Clean hut for RF test and assemble work was built
Precise cost estimation for all the prototype manufacturing process completed
 | Technical design | Mechanical design | 3D model | Drawings | Material | Manufacturing
Acc. Structure | Done（RF） | Done | Done | Ongoing | Delivered 2024/3 + additional 2025/3 | FY2024-FY2025
Test cell | Done（RF） | Done | Done | Done | Delivered 2024/3 | In progress

## Slide 19: Acc. Structure manufacturing flow
Summary of manufacturing and evaluation flow from raw material to final assembly
  Red: purchase
  Black: machining
  Purple: bonding
  Brown: others
  Light green: leak test
  Sky blue: test and evaluation

## Slide 20: Hot pressing cells
C plate
□445×40t
C plate
□445×40t
C sheet 0.5t
coupling-cell rp
accelerating-cell rp
294 kN@900℃

## Slide 21: infrastructure
Cooling water
  Chiller and cooling tower delivered in March 2023
  Tank, pump and heat exchanger delivered in Aug. and Sept. 2024
  Pipe and valve will be delivered Dec. 2024
    Ordered 2024/9
  Assembly work is planned in Jan. 2025
Electric power
  For solenoid, FC power supply and cooling water system
  Contract was made in Dec. 2023
  Construction finished in Aug. 2024
Cooling water and electric power will be ready by the end of FY2024

## Slide 22: Simulation flow of positron source

## Slide 23: PIC simulation example
M. Fukuda
Blue:electron
Red:positron

## Slide 24: 3D model
Updated largely including many peripheral devices,
such as piping and cable connections
These peripheral devices will be manufactured and integrated by the end of FY2024

## Slide 25: Summary
Prototyping of components are in progress
Cooling water and electric power will be ready by the end of FY2024
Everything but Acc. Structure, power supply (For FC and Solenoid) will be delivered by the end of FY2024

## Slide 26: Outlook
FY2024
  Finish prototyping of hardware
    Except Acc. Structure and power supply
  Infrastructure will be ready
  Fully 3D simulation without beam loading effect
FY2025
  DC power supply for solenoid (full module)
  Prototype Acc. Structure
  Pulsed power supply for FC
  Fully 3D simulation with beam loading effect
FY2026
  Assemble and evaluation of hardware
  Improved design based on detailed simulation and the first prototype