iSAS weekly meeting

19th June 2024

Present : Jorgen D’Hondt, Achille Stocchi, Adèle de Valera

Notes:

WP leaders feedback
To set expectations & help with feedback, Adèle sends a template (same as used for kick-off meeting) to be filled in by 28th June (to synchronise with coordination panel meeting)

Next 2 coordination panel meetings  
Adèle confirms for 8th July & 4th Sept 
8th July are available : Jorgen, Achille, Maud, Giovanni, Frederick, Adèle
4th Sept are available : Jorgen, Achille, Maud, Jens, Adèle

Advisory board 
Adèle sends a message signed by Jorgen, Achille, Dave, to governing board, to get the advisory board members to be approved by 28th June

Consortium agreement
v0 to be available next week (Julie Gendron will provide it)
To be approved by governing board  
Adèle checks a date with Dave, about 1:30 long via Zoom early September, probably 5th pm or 9th am (plenty of time to get to a final version) 

Governing board organisation
Meetings twice a year seems good, 1 via Zoom early September & 1 at annual project meeting next Spring

Project website
Specific website meeting to discuss propositions, Adèle proposes a date early September when key persons available 

Joint side event at ICRI in Australia early December (showcase event, not technical event, because only a few hours)
Jorgen proposes to go because at least one of us should be present 
Achille & Adèle check & get back to Jorgen 

Milestones reporting process
Jorgen & Achille prefer to check milestones before filing
Adèle provides WP leaders with a template to guide milestones reporting process

WP6 financing
Financial risk to be solved as CNRS internal decision making process - Achille handles it & reports back if needed (to take into account a possible delay by 6 months)