iSAS weekly meeting

10th July 2024

Present: Achille Stocchi, Jorgen D’Hondt, Adèle de Valera

Notes:

Repository

* SharePoint at CERN is not available anymore (licence discontinued) - they ask internally if an alternative can be proposed

* Jorgen reminds them if no more info by the end of the week

* If no alternative is proposed, let's check deeper into iFAST experience (similar to iSAS in many ways)

Coordination panel

* Every 6 weeks, and every other coordination panel becomes a steering committee

* Adèle sends invitations for the next year after clearing the schedule plan with key persons

WP3 & WP5 feedback missing

* WP3 committed to get back to Adèle in the next few days

* Adèle reminds WP5 of the feedback update, and asks for the milestone #21 report (due M3) to document the EU continuous reporting tool

4 issues to discuss with the Project Officer

* Adèle asks for a meeting to discuss the delays in milestones reporting (milestone #21 from WP2.1 due M3 & #25 from WP7.1 due M4), the delay we would ask for related to M6 deliverables (to postpone until M8), the integration of milestones and deliverables updates from the GANTT chart into the tables & the continuous reporting tool (on the EU Portal), and the depreciation rules applicable in lump sum grants

* Jorgen and/or Achille participate to the online meeting if possible

"Cahiers de laboratoire"

* Recommended by the CNRS for FAIR data management (though not mandatory), and closely linked de facto with the project's data management plan and with the repository issues

* Adèle & Achille check a bit deeper into the digital tool's actual features - and if partners could have access to it (or if all partners have their own tool, or if Adèle would have to fill it in for all partners from the SharePoint data, for example) - how does it work in other European projects with the CNRS involved? Specially how does iFAST handle it?

https://qualite-en-recherche.cnrs.fr/gt/cahier-de-laboratoire/

https://qualite-en-recherche.cnrs.fr/wp-content/uploads/2022/11/Guide_bonnes_pratiques_CLE_V1.pdf

iSAS website news article on ERL4ALL

* Adèle asks Maud who is interviewed these days about ERL4ALL (the interview may not be published yet)

1st weekly meeting post summer teaching abroad & post holidays (Achille, Jorgen and Adèle all 3 back)

* 21st August