## WPX timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Comments
Y1 | MX | M name | 2024 | M/D | # | WPX | X.1 Task 1 name | M/D description | Accounted for
Y1 | MX | M name | 2024 | M/D | # | WPX | X.3 Task 3 name | M/D description | Accounted for | {{ Interconnexion }} w/ WPY Task Y.?: impact WPX -> WPY
Y1 | MX | M name | 2025 | M/D | # | WPX | X.1 Task 1 name | M/D description | Accounted for
Y1 | MX | M name | 2025 | M/D | # | WPX | X.5 Task 5 name | M/D description | Accounted for | Test infra to be prepped
Y2 | MX | M name | 2025 | M/D | # | WPX | X.1 Task 1 name | M/D description | In progress
Y2 | MX | M name | 2026 | M/D | # | WPX | X.4 Task 4 name | M/D description | Roadblock | To warn coordination asap
Y3 | MX | M name | 2026 | M/D | # | WPX | X.1 Task 1 name | M/D description | Not started
Y3 | MX | M name | 2027 | M/D | # | WPX | X.1 Task 1 name | M/D description | Not started
Y4 | MX | M name | 2027 | M/D | # | WPX | X.5 Task 5 name | M/D description | Not started | Test infra to be available
Y4 | MX | M name | 2028 | M/D | # | WPX | X.1 Task 1 name | M/D description | Not started
Y4 | MX | M name | 2028 | M/D | # | WPX | X.2 Task 2 name | M/D description | Not started
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on L1: adele de-valera: * Not started * Info missing * In progress * To review * Roadblock * Done (w/ reporting still to do) * Delayed (to be discussed w/ PO) * To validate (by Coordination before reporting) * Accounted for (document uploaded directly into SyGMa if it's a deliverable, or reported w/ "actual date" & box "achieved" checked if it's a milestone, while the actual document is available as evidence upon request)

## WPX
M/D | # | Related WP | Related task | Description | Timeline in project months (M) |  |  |  | Status | Comments
|  | WPX | WP Name /Institution Resp |  | Y2 | M15 | May | 2025 |  | Last update timestamp
|  | WPX | X.1 Task 1 name /Institution resp
|  |  |  | WP Coordination /Person resp |  |  |  |  | In progress | All throughout the project (timeline-wise)
|  |  |  | * WPX meetings (w/ WPX iSAS indico link) |  |  |  |  | In progress | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee |  |  |  |  | In progress
|  |  |  | ** Oct Steering Co |  | M8 |  |  | Done
|  |  |  | ** Jan Steering Co |  | M11 |  |  | Done
|  |  |  | ** April Steering Co |  | M14 |  |  | In progress | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  | M17 |  |  | Not started
|  |  |  | * Industry Board meetings |  |  |  |  | In progress
|  |  |  | ** 1st IB meeting |  | M8 |  |  | Done
|  |  |  | ** 2nd IB meeting |  | M10 |  |  | Done
|  |  |  | ** Industry Workshop in Padova |  | M13 |  |  | Done
|  |  |  | * Yearly project meetings |  |  |  |  | In progress
|  |  |  | ** Kick-off meeting at IJCLab |  | M2 |  |  | Done
|  |  |  | ** Padova meeting |  | M13 |  |  | Done
|  |  |  | ** Berlin meeting |  | M25 |  |  | Not started
|  |  |  | ** Lund meeting |  | M37 |  |  | Not started | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  | M48 |  |  | Not started | Host tbc
|  |  |  | * Project data repository to update regularly |  |  |  |  | Not started | w/ relevant WPX documentation to share
M/D | # | WPX | X.1 | M/D description /Person resp | YX | MX | M name | Year | In progress | {{ Interconnexion }} w/ WPY Task Y.?: impact WPX -> WPY
|  |  |  | * Subtask A name /Person resp |  | MX |  |  | Done
|  |  |  | * Subtask B name /Person resp |  | MX |  |  | Done
|  |  |  | * Subtask C name /Person resp |  | MX |  |  | In progress
|  |  |  | ** Sub-subtask a name: design to be created |  | MX |  |  | Done
|  |  |  | ** Sub-subtask b name: ex design to be finalised |  | MX |  |  | Done | Test infra prepped
|  |  |  | ** Sub-subtask c name: ex test based on design |  | MX |  |  | Done | Test infra available
|  |  |  | ** Sub-subtask d name: ex ccl based on test |  | MX |  |  | Not started
|  |  |  | * Subtask D name /Person resp |  | MX |  |  | In progress
|  |  |  | ** Sub-subtask a name |  | MX |  |  | In progress
|  |  |  | * Subtask E name /Person resp |  | MX |  |  | In progress
|  |  |  | * Across all project subtask name /Person resp |  |  |  |  | In progress | All throughout the project (timeline-wise)
|  |  |  | * Close out |  | MX |  |  | Not started
M/D | # | WPX | X.1 | M/D description /Person resp | YX | MX | M name | Year | Accounted for
|  |  |  | * Subtask A name /Person resp |  | MX |  |  | Done
|  |  |  | ** Sub-subtask a name |  | MX |  |  | Done
|  |  |  | ** Sub-subtask b name |  | MX |  |  | Done
|  |  |  | * Subtask B name /Person resp |  | MX |  |  | Done
|  |  |  | * Close out |  | MX |  |  | Done
M/D | # | WPX | X.1 | M/D description /Person resp | YX | MX | M name | Year | Not started | {{ Interconnexion }} w/ WPZ Task Z.?: impact WPZ -> WPX
|  |  |  | * Subtask A name /Person resp |  | MX |  |  | Not started
|  |  |  | ** Sub-subtask a name |  | MX |  |  | Not started | Test infra to be prepped
|  |  |  | ** Sub-subtask b name |  | MX |  |  | Not started | Test infra to be available
|  |  |  | * Subtask B name /Person resp |  | MX |  |  | Not started
|  |  |  | * Close out |  | MX |  |  | Not started
|  | WPX | X.2 Task 2 name /Institution resp
M/D | # | WPX | X.3 | M/D description /Person resp | YX | MX | M name | Year | Not started
|  |  |  | * Subtask A name /Person resp |  | MX |  |  | Not started
|  |  |  | * Close out |  | MX |  |  | Not started
|  | WPX | X.3 Task 3 name /Institution resp
M/D | # | WPX | X.3 | M/D description /Person resp | YX | MX | M name | Year | Accounted for | ex: Due date NOT postponed (because it's a milestone)
|  |  |  | * Subtask A name /Person resp |  | MX |  |  | Done
|  |  |  | * Close out |  | MX |  |  | Done
|  | WPX | X.4 Task 4 name /Institution resp
M/D | # | WPX |  | M/D description /Person resp | YX | MX | M name | Year | In progress
|  |  |  | * Subtask within Task 4 name /Person resp |  | MX |  |  | In progress
|  |  |  | ** Sub-subtask a name |  | MX |  |  | Done
|  |  |  | ** Sub-subtask b name |  | MX |  |  | Done
|  |  |  | ** Sub-subtask c name |  | MX |  |  | Done
|  |  |  | ** Sub-subtask d name |  | MX |  |  | Done
|  |  |  | * Subtask name /Person resp |  | MX |  |  | In progress
|  |  |  | ** Sub-subtask a name |  | MX |  |  | Done
|  |  |  | ** Sub-subtask b name |  | MX |  |  | Roadblock | To warn coordination asap
|  |  |  | * Close out |  | MX |  |  | Not started
|  | WPX | X.5 Task 5 name /Institution resp
M/D | # | WPX | X.5 | M/D description /Person resp | YX | MX | M name | Year | In progress
|  |  |  | * Subtask A name /Person resp |  | MX |  |  | Done
|  |  |  | * Subtask B name /Person resp |  | MX |  |  | Done
|  |  |  | * Close out |  | MX |  |  | Not started
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on G1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on L1: adele de-valera: * Not started * Info missing * In progress * To review * Roadblock * Done (w/ reporting still to do) * Delayed (to be discussed w/ PO) * To validate (by Coordination before reporting) * Accounted for (document uploaded directly into SyGMa if it's a deliverable, or reported w/ "actual date" & box "achieved" checked if it's a milestone, while the actual document is available as evidence upon request)
Note on F35: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F41: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F47: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F51: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F55: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F66: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F71: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status
Y1 | Task name | Not started
Y2 | M/D description | Info missing
Y3 | * Subtasks | In progress
Y4 | ** Sub-subtasks | To review
| {{ WPs interconnexions }} | Done
| Test infra (to be) prepped | Delayed
| Test infra (to be) available | Roadblock
To validate
Accounted for
Note on F7: adele de-valera: in-between in progress status and done status
Note on F8: adele de-valera: after review status and before close out
Note on F9: adele de-valera: -> coordination in the loop asap to help if needed
Note on F10: adele de-valera: obstacle to be removed or workaround path to be found to make progress again -> coordination in the loop asap
Note on F11: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F12: adele de-valera: on EU continuous reporting portal by project management