## WP4 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Comments
Y2 | M16 | June | 2025 | M | 15 | WP4 | 4.5 RF coupler design | Design of FPC coupler | In progress
Y2 | M18 | August | 2025 | M | 16 | WP4 | 4.2 HOM coupler design | Design of HOM coupler | In progress | {{ Interconnexion }} w/ WP6 Task 6.4: impact WP4 -> WP6
Y2 | M24 | Feb | 2026 | M | 38 | WP4 | 4.1 Coordination of R&D on couplers | Impact risk analysis WP4 | Not started
Y2 | M24 | Feb | 2026 | M | 17 | WP4 | 4.3 Fabrication of HOM couplers | Fabrication of HOM couplers | Not started | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
Y3 | M27 | May | 2026 | M | 18 | WP4 | 4.4 Test of HOM couplers | Test of HOM couplers | Not started | Test infra to be prepped & available
Y3 | M27 | May | 2026 | M | 19 | WP4 | 4.6 Fabrication of RF couplers | Fabrication of FPCs | Not started | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
Y3 | M33 | Nov | 2026 | D | 14 | WP4 | 4.4 Test of HOM couplers | Report qualification HOM couplers on cavities at 300 K | Not started
Y3 | M33 | Nov | 2026 | M | 20 | WP4 | 4.7 Test of RF couplers | Test of FPC couplers | Not started | Test infra to be prepped & available
Y4 | M39 | May | 2027 | D | 15 | WP4 | 4.7 Test of RF couplers | Report on RF test of 800-MHz FPC at 50 kW CW | Not started
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on L1: adele de-valera: * Not started * Info missing * In progress * To review * Roadblock * Done (w/ reporting still to do) * Delayed (to be discussed w/ PO) * To validate (by Coordination before reporting) * Accounted for (document uploaded directly into SyGMa if it's a deliverable, or reported w/ "actual date" & box "achieved" checked if it's a milestone, while the actual document is available as evidence upon request)
Note on M3: adele de-valera: Task 4.5 reassigned after departure of Eric Montesinos -> ok now
Note on M4: adele de-valera: Dependent on 800 MHz HOM coupler design delivery from WP4 - Might get delayed 4 months (cf M11 update) -> AMD
Note on M6: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on M9: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4

## WP4
M/D | # | Related WP | Related task | Description | Timeline in project months (M) |  |  |  | Status | Comments
|  | WP4 | WP4 - Higher-order mode dampers & fundamental power couplers /CNRS |  | Y2 | M15 | May | 2025 |  | Last update timestamp
|  | WP4 | 4.1 Coordination of R&D on couplers /CNRS
|  |  |  | WP Coordination /Yolanda Gómez Martínez |  |  |  |  | In progress | All throughout the project (timeline-wise)
|  |  |  | * WP4 meetings |  |  |  |  | In progress | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee |  |  |  |  | In progress
|  |  |  | ** Oct Steering Co |  | M8 |  |  | Done
|  |  |  | ** Jan Steering Co |  | M11 |  |  | Done
|  |  |  | ** April Steering Co |  | M14 |  |  | In progress | Advisory Board WP4 recos to integrate
|  |  |  | ** July Steering Co |  | M17 |  |  | Not started
|  |  |  | * Industry Board meetings |  |  |  |  | In progress
|  |  |  | ** 1st IB meeting |  | M8 |  |  | Done
|  |  |  | ** 2nd IB meeting |  | M10 |  |  | Done
|  |  |  | ** Industry Workshop in Padova |  | M13 |  |  | Done
|  |  |  | * Yearly project meetings |  |  |  |  | In progress
|  |  |  | ** Kick-off meeting at IJCLab |  | M2 |  |  | Done
|  |  |  | ** Padova meeting |  | M13 |  |  | Done
|  |  |  | ** Berlin meeting |  | M25 |  |  | Not started
|  |  |  | ** Lund meeting |  | M37 |  |  | Not started | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  | M48 |  |  | Not started | Host tbc
|  |  |  | * Project data repository to update regularly |  |  |  |  | Not started | w/ relevant WP4 documentation to share
M | 38 | WP4 | 4.1 | Impact risk analysis WP4 /Yolanda Gómez Martínez | Y2 | M24 | Feb | 2026 | In progress
|  |  |  | * Impact risk analysis of FPC tasks |  | M23 | Jan | 2026 | In progress
|  |  |  | * Impact risk analysis on HOM couplers tasks |  | M23 | Jan | 2026 | In progress
|  |  |  | * Close out |  | M24 | Feb | 2026 | Not started
|  | WP4 | 4.2 HOM coupler design /INFN
M | 16 | WP4 | 4.2 | Design of HOM coupler /Dario Giove | Y2 | M18 | August | 2025 | In progress
|  |  |  | * Design of 800 MHz HOM/ Patricia Duchesne |  | M16 | June | 2025 | In progress
|  |  |  | ** RF, thermical and mechanical studies /IJCLab |  | M13 | March | 2025 | Done | Technical review carried out on 27/03/2025. Improving studies ongoing (recommendations of the experts).
|  |  |  | * Design of 1,3 GHz HOM/Dario Giove |  | M17 | July | 2025 | In progress
|  |  |  | ** RF, thermical and mechanical studies /INFN |  | M17 | July | 2025 | In progress | Technical review to be carried out on June. Studies are in preliminary phase.
|  |  |  | * Close out |  | M18 | August | 2025 | Not started
|  | WP4 | 4.3 Fabrication of HOM couplers /CERN
M | 17 | WP4 | 4.3 | Fabrication of HOM couplers /Marco Garlasche | Y2 | M24 | Feb | 2026 | Not started | Engineering report of the fabrication
|  |  |  | * Fabrication of the 800 MHz HOM couplers |  | M24 | Feb | 2026 | In progress
|  |  |  | ** Feasibility study/Marco Garlasche |  | M15 | May | 2025 | In progress
|  |  |  | ** Procurement of Nb / Marco Garlasche |  | M19 | Sept | 2025 | Not started | 4 months for procurement of Nb
|  |  |  | ** Fabrication 4 HOM /Marco Garlasche |  | M28 | June | 2026 | Not started | 9 months for the fabrication of the 4 HOMs; The additional 4 HOM, if funded through iSAS, would need the same time, minus the procurement of Nb if the decision of procurement of material if made in time so for M37 fev 2027
|  |  |  | * Fabrication of 1 prototype 1.3 GHz HOM couplers |  | M28 | Feb | 2026 | Not started
|  |  |  | * Close out |  | M24 | Feb | 2026 | Delayed | No compatible with M28 production deadlines.
|  | WP4 | 4.4 Test of HOM couplers /CNRS | [6 empty] | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
M | 18 | WP4 | 4.4 | Test of HOM couplers /Dario Giove | Y3 | M27 | May | 2026 | Not started
|  |  |  | * 800 MHz HOM test / To be defined |  | M26 | April | 2026 | Not started
|  |  |  | ** Couplers preparation and test |  | M26 | April | 2026 | Not started | Test infra to be available
|  |  |  | * 1,3 GHz test/Dario Giove |  | M26 | April | 2026 | Not started
|  |  |  | ** Couplers preparation and test |  | M26 | April | 2026 | Not started | Test infra to be available.
|  |  |  | * Close out |  | M27 | May | 2026 | Not started
D | 15 | WP4 | 4.4 | Report qualification HOM couplers on cavities at 300 K /To be defined | Y4 | M27 | May | 2027 | Not started
|  |  |  | * Close out |  | M27 | May | 2027 | Not started
|  | WP4 | 4.5 RF coupler design /CERN
M | 15 | WP4 | 4.5 | Design of FPC coupler /Calum Sharp | Y2 | M16 | June | 2025 | In progress
|  |  |  | * RF studies / Patricia Duchesne & Julien Angot |  | M15 | May | 2025 | To review | Technical review planned on 13/05/2025
|  |  |  | * Thermical studies / Karin Candera & Calum Sharp |  | M15 | May | 2025 | To review | Technical review planned on 13/05/2025
|  |  |  | * Mechanical studies / Marco Garlasche & Gilles Olivier & Sebastien Blivet |  | M15 | May | 2025 | To review | Technical review planned on 13/05/2025
|  |  |  | * Close out |  | M16 | June | 2025 | Not started
|  | WP4 | 4.6 Fabrication of RF couplers /CERN
M | 19 | WP4 | 4.6 | Fabrication of FPCs /Marco Garlasche | Y3 | M27 | May | 2026 | Not started | Engineering report of the fabrication
|  |  |  | * Feasibility study/Marco Garlasche |  | M15 | May | 2026 | In progress
|  |  |  | * Procurement of raw / Marco Garlasche |  | M18 | August | 2025 | Not started
|  |  |  | * Fabrication /Marco Garlasche |  | M27 | May | 2026 | Not started
|  |  |  | * Close out |  | M27 | May | 2026 | Not started
|  | WP4 | 4.7 Test of RF couplers /CERN | [6 empty] | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
M | 20 | WP4 | 4.7 | Test of FPC couplers /To be defined | Y3 | M33 | Nov | 2026 | In progress
|  |  |  | * RF conditioning possibilities / Sebastien Calvo (tbc) |  | M15 | May | 2025 | To review | Technical review planned on 13/05/2025. Depending on the RF conditioning choice a change of milestone and deliverable may be necessary ( change frequency or maximum power)
|  |  |  | * Setting up the test bench |  | M27 | May | 2026 | Not started | If RF conditioning at 800 MHz, the manufacture of a test box may be necessary ( ~ 1 year)
|  |  |  | * Couplers preparation and RF conditionning |  | M32 | Oct | 2026 | Not started
|  |  |  | * Close out |  | M33 | Nov | 2026 | Not started
D | 15 | WP4 | 4.7 | Report on RF test of 800-MHz FPC at 50 kW CW /To be defined | Y4 | M39 | May | 2027 | Not started
|  |  |  | * Close out |  | M39 | May | 2027 | Not started
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on G1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on L1: adele de-valera: * Not started * Info missing * In progress * To review * Roadblock * Done (w/ reporting still to do) * Delayed (to be discussed w/ PO) * To validate (by Coordination before reporting) * Accounted for (document uploaded directly into SyGMa if it's a deliverable, or reported w/ "actual date" & box "achieved" checked if it's a milestone, while the actual document is available as evidence upon request)
Note on F26: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F33: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F41: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on M42: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on F48: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F50: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F56: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F62: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on M63: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on F68: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F70: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status
Y1 | Task name | Not started
Y2 | M/D description | Info missing
Y3 | * Subtasks | In progress
Y4 | ** Sub-subtasks | To review
| {{ WPs interconnexions }} | Done
| Test infra (to be) prepped | Delayed
| Test infra (to be) available | Roadblock
To validate
Accounted for