



**iSAS Weekly meeting**

11/9

Present: Jorgen D'Hondt, Achille Stocchi, Adèle de Valera

Notes:

**Website task force**

To set up:

\* Adèle asks Nick Shipman (Conference coordinator), Giorgio Keppel (WP7 Leader), Alick McPherson (Achille & Jorgen also willing to participate)

\* Adèle asks if Jens would be willing to take the leadership role

**WP7 Repository @STFC (WP7 milestone 25 due M4)**

Meeting 6/9 to hopefully validate STFC as host: Joe from STFC IT dpt sends spefications for comments

**To close a few loops**

Regarding the website working group to be set up (and the industrial section within, due M10 so mid-December), the involvement of industrial partners, the repository at STFC (due M4 so last June), among the most pressing topics of September

\* Adèle asks proposes a meeting 18th 9-10 am to WP7 Leader

**WP8 & WP9 deliverables due M7**

Reminder sent, no review sent back yet

\* If no responses after deadline given of Sept 13th, probably Coordination panel member to be asked in person

**CA**

Industrial partners contact list asked for so Julie can send the 1st version

**2025 iSAS in-person meeting @INFN**

\* Adèle asks the Coordination panel to confirm one of the two options until 18th

-> Wednesday 12th to Friday 14th (including travel)

**To start process of including 3 new partners**

Adèle got back to the PO to inform her of Governing Board approval

\* Jorgen gets Adèle Nikhef contacts