iSAS weekly meeting

18th Sept 2024

Present: Jorgen D'Hondt, Achille Stocchi, Adèle de Valera

Notes:

Padova meeting 2025

No opposition to Wednesday 12th March to Friday 14th March 2025 (including travel)

* Adèle asks Ketel for the kick-off guest list to send a formal Save the date (+ info that virtual option will be offered)

* Adèle checks the guest list with WP Leaders (to see if new contacts to add to the list, like new Advisory Board members for ex) & with INFN team

Next Governing Board meeting

No response from Chairperson yet

* Adèle checks if 4/11 2 pm CET ok with Dave & Julie

CA

* Adèle asks Julie if she can send targeted reminder to partners who did not comment yet, ideally by the end of the week (to get to version 2)

Amendment

No response yet from PO (we are encouraged to get PO's opinion as a 1st step)

All 3 new partners PICs & admin contacts ok

Amendment process: https://webgate.ec.europa.eu/funding-tenders-opportunities/display/OM/Amendments

Website

Working group set up in progress: Alick, Giorgio & Jens on board (Nick couldn't ; missing the leader)

* Adèle finalises doodle/evento for skeleton 1st meeting (following dates can be decided at 1st WG meeting, as well as a leader for the group)

2nd general website meeting to validate phase 1 & open phase 2:

* Adèle proposes a new date

WP7 Repository @STFC (WP7 milestone #25 due M4)

* Adèle sends a reminder to IT at STFC about their commitment to send STFC's proposal to comment

* Adèle proposes to WP7 Leader to lead the proposal checking process to make sure it aligns with WP7 stakes

Loops to close in WP7

* To propose to include WP7 Deputy more

* To clear a complete up-to-date Industry Board contact list

* To propose to include participation of Scientific Coordinator and Project Coordinator at 1st Industry Board at end Sept/ early October to say a few words to introduce the project

WP8 & WP9 deliverables due M7

No response yet, despite the Sept 13th deadline being passed

* Adèle sends final call for comments to Coordination panel

Advisory Board members welcome meeting 20/9

Intro by Frederick

Presentation of the iSAS project by Jorgen

Role of the Advisory board by Achille

Questions from the Advisory board members

* Adèle sends Indico page (with agenda items) to the Chairperson as a reminder (to Advisory Boards members as well)

Next iSAS Weekly meeting 25/9

Jorgen will be in Madrid to present iSAS at a workshop dedicated to sustainable research infrastructures organised by Chairperson of TIARA, so he will not be present for next Weekly meeting