iSAS weekly meeting

2nd Oct 2024

Present: Achille Stocchi, Adèle de Valera

Absent: Jorgen D'Hondt

Notes:

Question about prefinancing from ESS

Adèle contacted the CNRS services responsible for the payment back in end April, early May to check the tracing

WP7

Milestone #25 due M4 "Decision on iSAS repository and its implementation" - WP7 Repository @STFC

Wait until effective implementation in addition to decision made to report on the milestone (amendment to justify in any case)

Industry board

No news received yet

Industrial partners contact list

Updated, w/ Governing board contacts & Industry board contacts - not yet received (Governing board invite not sent, neither CA sent to industrial partners yet as a consequence)

* Adèle sends reminder to WP7 Leader asap

WP8

* Should we identify Task leaders? Ketel volunteers for task 8.3 Diversity & equity

* Should we identify contact persons to check future WP8 (& WP9) deliverables? To be asked to the Coordination panel

Steering Committee meeting on Oct 18

Agenda and guidelines for presentations proposed by Jorgen

Governing board 4/11 2 pm

The Chairperson did not send last meeting notes yet, nor next meeting invitations

* Should we send the invitations even without the industrial partners contacts? Whithout them having received the CA? No, Adèle sends a reminder to WP7 leader, then sends last meeting notes and next meeting provisional date for invitations

4th Advisory board member was to be decided offline:

* To be put on 4/11 Governing board agenda (who should propose names officially)

Padova 2025

No response yet from INFN team, or WP5, 6, 7

* Adèle modifies the contact groups, already sent calendar invitations and redirects electronic correspondence following the departure of Giovanni Bisoffi and his replacement by Cristian Pira within the Coordination panel & the Padova hosting team

Website meetings

14th Oct 2nd skeleton meeting

28th Oct 3rd skeleton meeting

12th Nov 2nd general website meeting

Amendment preparation

No e-mail asking for complementary information (as announced) from PO yet

No news yet from Latvian or Polish partners (about their specific contribution)

* Adèle sends a reminder to Latvian & Polish partners (in anticipation of the Governing board meeting of 4/11), Cc WP Leaders & Deputies concerned

* Adèle sends notes on numbering modifications to Achille and Jorgen for comments to prepare the amendment process