iSAS weekly meeting

9th Oct 2024

Present: Achille Stocchi, Adèle de Valera

Absent: Jorgen D'Hondt

Notes:

Question about prefinancing from ESS

No response yet from CNRS DR4 despite the reminder for now

Amendment

PO validated the start of the process, with warnings to be discussed next weekly meeting

Polish & Latvian partners reminded about their detailed participation needed to document within the amendment process

Jorgen gave his ideas regarding the proposal sent by Adèle

- Achille responded during the weekly meeting

CA

No response from Julie Gendron-Brundu yet

No list for industrial partners yet

Steering committee

WP7 Leader warned he will not be present at Steering committee - Adèle asked if deputy would represent WP7

- Achille will chair the Steering committee

- Adèle prepares slides for the Steering committee regarding WP9 (transversal coordination) to be checked next weekly meeting

1st Industry board meeting

30/10 9:30-10:30 am CET

Adèle invited Technology Transfer Officer from IJCLab Souleymane Kamara, in case he could make himself available

Governing Board

Provisional date & agenda sent

No list for industrial partners yet - no formal invitations sent yet

Next weekly meeting

- Adèle postpones weekly meeting to 17/10 at 11 am