iSAS weekly meeting

12th Nov 2024

Present: Jorgen D'Hondt, Achille Stocchi, Adèle de Valera

Notes:

Repository

Comments already sent to STFC IT:

-> Link to Indico page on Homepage (as well as iSAS website link)

-> Project contact w/ SharePoint admin, Project Coordinator & Scientific Coordinator

-> Milestone, Deliverable, Status report, Publication to be added as document types to choose from

-> Editorial rights for WP Leaders & Deputies on their own WP as well as the flexibility for them to add editorial rights themselves

2nd website meeting Nov 12

Difficulties to log in to GitLab - don't know if the WG could work on the testing expected to prepare the demo despite asking

CA

Meeting with Julie 5/11 - invited to weekly to discuss directly with Achille & Jorgen too

New partners can start negotiating the CA from now on already, even if they need to sign the amendment before signing the final version of the CA

* Since 1 industrial partner is hesitant, let's discuss the option of the NDA with all of them during next IB

* Adèle asks WP7 Leader about it to prepare Dec 4 at 3 pm meeting (add item to agenda, verify if all partners will be there or collects their perspective beforehand)

* CA v2 to be finalised as soon as a formal decision is reached with industrial partners

Padova 2025

No response from INFN host yet

* Adèle reminds INFN host

2nd IB Dec 4

No agenda yet

* Adèle asks WP7 Leader if WP7 Deputy takes over during WP7 Leader's holidays

Asynchronous Steering committee

Questions & comments still to be sent

ESS prefinancing

Situation still blocked

* Achille discusses it with DR4 CNRS