iSAS weekly meeting

2nd December 2024

Present: Achille Stocchi, Adèle de Valera

Absent: Jorgen D'Hondt

Notes:

AMD

PO informed of delay to 1st trimester 2025 - no response yet

Industry Board (IB)

Dec 4 at 3 pm CET

Julie's answers pending, invitation transferred, preparation notes sent to meeting participants

Agenda mostly concentrated on WP7 leadership transition and CA vs NDA, AOB could be about industrial section of website

Verifiable metric for energy-saving performances

WP9 milestone due Feb 2025 - while Report on energy saving performance of iSAS technologies is due M46 (Dec 2027)

Decision to make - will it need to be postponed? (since it's a milestone it would mean AMD)

* Achille asks Fred Bouly & Maud Baylac to discuss

Governing Board

The Chair agrees to a change in leadership

* Jorgen invites Peter McIntosh to take on the Chair responsibilities

Padova 2025

Maurizio Vretenar accepted the invitation letter to give a talk on the preparation of iFAST 2

Coordination panel meeting

* Adèle sends updated PPT w/ upcoming meetings as an added slide

Steering committee

Jan 10

* Adèle adds to agenda WP9 metrics milestone

* Jorgen sends reminder before end of year break