## WP4 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y2 | M16 | June | 2025 | M | 15 | WP4 | 4.5 RF coupler design | Design of FPC coupler | In progress | On track
Y2 | M18 | August | 2025 | M | 16 | WP4 | 4.2 HOM coupler design | Design of HOM coupler | In progress | On track | {{ Interconnexion }} w/ WP6 Task 6.4: impact WP4 -> WP6
Y2 | M24 | Feb | 2026 | M | 38 | WP4 | 4.1 Coordination of R&D on couplers | Impact risk analysis WP4 | Not started | On track
Y2 | M24 | Feb | 2026 | M | 17 | WP4 | 4.3 Fabrication of HOM couplers | Fabrication of HOM couplers | Not started | In difficulty | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
Y3 | M27 | May | 2026 | M | 18 | WP4 | 4.4 Test of HOM couplers | Test of HOM couplers | Not started | In difficulty | Test infra to be prepped & available
Y3 | M27 | May | 2026 | M | 19 | WP4 | 4.6 Fabrication of RF couplers | Fabrication of FPCs | Not started | Risk to mitigate | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
Y3 | M33 | Nov | 2026 | D | 14 | WP4 | 4.4 Test of HOM couplers | Report qualification HOM couplers on cavities at 300 K | Not started | Risk to mitigate
Y3 | M33 | Nov | 2026 | M | 20 | WP4 | 4.7 Test of RF couplers | Test of FPC couplers | Not started | Risk to mitigate | Test infra to be prepped & available
Y4 | M39 | May | 2027 | D | 15 | WP4 | 4.7 Test of RF couplers | Report on RF test of 800-MHz FPC at 50 kW CW | Not started | On track
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on M3: adele de-valera: no deviation from plans
Note on N3: adele de-valera: Task 4.5 reassigned after departure of Eric Montesinos -> ok now
Note on M4: adele de-valera: no deviation from plans
Note on N4: adele de-valera: Dependent on 800 MHz HOM coupler design delivery from WP4 - Might get delayed 4 months (cf M11 update) -> AMD
Note on M5: adele de-valera: no deviation from plans
Note on M6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on N6: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on M8: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on M9: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on N9: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on M10: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on M11: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on M13: adele de-valera: no deviation from plans

## WP4 M15
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP4 | WP4 - Higher-order mode dampers & fundamental power couplers |  | CNRS |  | Y2 | M15 | May | 2025 |  |  | Last update timestamp: 09 July 2025
|  | WP4 | 4.1 Coordination of R&D on couplers |  | CNRS
|  |  |  | WP Coordination | Yolanda Gómez Martínez | Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP4 meetings | [6 empty] | In progress | Risk level | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | Risk level | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | Risk level | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | Risk level | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | In progress | Risk level | Advisory Board WP4 recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | Risk level | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | Risk level | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | Risk level | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | Risk level | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | Risk level | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | Risk level | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | Risk level | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | Risk level | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | Risk level | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | Risk level | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | Risk level | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | Not started | Risk level | w/ relevant WP4 documentation to share
M | 38 | WP4 | 4.1 | Impact risk analysis WP4 | Yolanda Gómez Martínez | Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma | Y2 | M24 | Feb | 2026 | In progress | On track
|  |  |  | * Impact risk analysis of FPC tasks | Yolanda Gómez Martínez | Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma | Y2 | M23 | Jan | 2026 | In progress | On track
|  |  |  | * Impact risk analysis on HOM couplers tasks | Yolanda Gómez Martínez | Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma | Y2 | M23 | Jan | 2026 | In progress | On track
|  |  |  | * Close out | Yolanda Gómez Martínez |  | Y2 | M24 | Feb | 2026 | Not started | On track
|  | WP4 | 4.2 HOM coupler design |  | INFN
M | 16 | WP4 | 4.2 | Design of HOM coupler | Dario Giove | Sebastien Blivet, Karin Candera, Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Akira Miyazaki, Gilles Olivier, Guillaume Olry, Vittorio Parma, Adrien Placais… INFN participants | Y2 | M18 | August | 2025 | In progress | On track | The final studies of the 800 MHz HOM coupler & preliminaires studies on 1,3 GHz HOM to be included in the milestone 2 HOM design report
|  |  |  | * Design of 800 MHz HOM | Patricia Duchesne | Sebastien Blivet, Patricia Duchesne, Yolanda Gómez Martínez, Gilles Olivier, Guillaume Olry, Akira Miyazaki, Adrien Placais… | Y2 | M18 | August | 2025 | In progress | On track | A 800 MHz coupler ready to manufacture is planned in August 2025
|  |  |  | ** RF studies | Patricia Duchesne | Patricia Duchesne, Adrien Placais… | Y2 | M17 | July | 2025 | In progress | On track | The technical review was carried out on 13/05/2025 with invited expert members (Carmelo Barbagallo/CERN and Shahnam Gorgi Zadeh/CERN) Ongoing improvement of the feedthrough, final choice planned before August 2025.
|  |  |  | * *Thermical studies | Patricia Duchesne | Karin Candera, Patricia Duchesne, Vittorio Parma, Hervé Saugnac | Y2 | M17 | July | 2025 | In progress | On track | The technical review was carried out on 13/05/2025 with invited expert members (Carmelo Barbagallo/CERN and Shahnam Gorgi Zadeh/CERN). Latest simulations in progress, end of simulation scheduled before August 2025.
|  |  |  | ** Mechanical studies | Gilles Olivier | Sebastien Blivet, Patricia Duchesne, Gilles Olivier | Y2 | M17 | July | 2025 | Done | On track | The technical review was carried out on 13/05/2025 with invited expert members (Carmelo Barbagallo/CERN and Shahnam Gorgi Zadeh/CERN). Latest optimizations in progress, end scheduled before August 2025.
|  |  |  | * Design of 1,3 GHz HOM | Dario Giove | participants tbc | Y2 | M18 | August | 2025 | In progress | In difficulty | The presentation of BriXSinO HOM was carried out on 8/07/25. With the acceptance of IJCLab, INFN propose to scale the 800 MHz Hook HOM coupler to 1,3GHz. A detailed recovery plan will be submitted within the end of July 2025
|  |  |  | * Close out | Dario Giove |  | Y2 | M18 | August | 2025 | Not started | On track
|  | WP4 | 4.3 Fabrication of HOM couplers |  | CERN
M | 17 | WP4 | 4.3 | Fabrication of HOM couplers | Marco Garlasche, Calum Sharp | Simon Barriere, Marco Garlasche, Yolanda Gómez Martínez, Sebastien Jerome Calvo, Vittorio Parma, Calum Sharp… | Y2 | M24 | Feb | 2026 | In progress | In difficulty | The timeline M24 ( Feb 26) is no compatible for both types of HOM couplers fabrication ( 800 MHz @October 2026 and 1.3 GHz@testimation on progress). A change in the date of this milestone is necessary.
|  |  |  | * Fabrication of 4 prototypes 800 MHz HOM couplers | Marco Garlasche | participants tbc | Y2 | M24 | Feb | 2026 | In progress | In difficulty | Timeline proposed for the manufacturing of 4 prototypes of HOM 800 MHz couplers: October 2026 / M32 (not Feb26/M24)
|  |  |  | ** Feasibility production study | Marco Garlasche | Simon Barriere, Marco Garlasche, Vittorio Parma, Calum Sharp. | - | - | - | - | In progress | - | Timeline proposed for the feasibility production study: September 2025 (T0)
|  |  |  | ** Procurement of Nb | Marco Garlasche | Marco Garlasche, Calum Sharp… | - | - | - | - | Not started | - | Timeline proposed for the procurement of Nb: on January 2026 ( T1 =T0+ 4 months).
|  |  |  | ** Fabrication of 4 HOM | Marco Garlasche | Simon Barriere, Marco Garlasche… | - | - | - | - | Not started | - | Timeline proposed for the fabrication of 4 HOMs: on October 2026 (T2 = T1 + 9 months). The additional 4 HOM, if funded through iSAS, would need the same time, minus the procurement of Nb if the decision of procurement of material if made in time.
|  |  |  | * Fabrication of 1 prototype 1.3 GHz HOM couplers | Marco Garlasche | participants tbc | Y2 | M24 | Feb | 2026 | Not started | In difficulty | Timeline to be proposed once INFN will have the 800MHz Hook HOM model as they need to estimate the work to do the scaling from 800MHz to 1,3 GHz.
|  |  |  | ** Feasibility production study | Marco Garlasche | participants tbc | - | - | - | - | Not started | -
|  |  |  | ** Procurement of Nb | Marco Garlasche | participants tbc | - | - | - | - | Not started | - | 4 months for procurement of Nb
|  |  |  | ** Fabrication 1 HOM |  | participants tbc | - | - | - | - | Not started | - | 9 months for the fabrication of 1 HOM
|  |  |  | * Close out | Calum Sharp |  | Y2 | M24 | Feb | 2026 | Not started | In difficulty
|  | WP4 | 4.4 Test of HOM couplers |  | CNRS
M | 18 | WP4 | 4.4 | Test of HOM couplers | Patricia Duchesne | participants tbc | Y3 | M27 | May | 2026 | Not started | In difficulty | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6 Proposed timeline of HOM fabrication (M32) is later than the timeline of this task (M27)
|  |  |  | * 800 MHz HOM test | Patricia Duchesne | participants tbc | Y3 | M27 | May | 2026 | Not started | In difficulty | Test infra to be available. Subtasks to be defined Timeline proposed for the 800MHz HOM test : on May 2027 (according to the proposal 7 months for testing)
|  |  |  | * 1,3 GHz test | Dario Giove | participants tbc | Y3 | M27 | May | 2026 | Not started | In difficulty | Test infra to be available. Subtasks to be defined According to the proposal 7 months for testing.
|  |  |  | * Close out | Patricia Duchesne |  | Y3 | M27 | May | 2026 | Not started | In difficulty
D | 15 | WP4 | 4.4 | Report qualification HOM couplers on cavities at 300 K | Patricia Duchesne | participants tbc | Y4 | M33 | Nov | 2026 | Not started | Risk to mitigate | From M32 (the end of 800 MHz fabrication) only 1 month for testing and for writing the report .
|  |  |  | * Close out | Patricia Duchesne |  | Y4 | M33 | Nov | 2026 | Not started | Risk to mitigate
|  | WP4 | 4.5 RF coupler design |  | CERN
M | 15 | WP4 | 4.5 | Design of FPC coupler | Calum Sharp | Julien Angot, Sebastien Blivet, Karin Candera, Patricia Duchesne, Marco Garlasche, Yolanda Gómez, Shahnam Gorgi Zadeh, Sebastien Jerome Calvo, Gilles Olivier, Guillaume Olry, Vittorio Parma, A. Placais, … | Y2 | M16 | June | 2025 | In progress | On track | Report finished
|  |  |  | * RF studies | Patricia Duchesne | Julien Angot, Patricia Duchesne, Yolanda Gómez, Guillaume Olry, A. Placais, … | Y2 | M15 | May | 2025 | Done | On track | Technical review carried out on 13/05/2025
|  |  |  | * Thermical studies | Karin Candera , Calum Sharp | Karin Candera, Patricia Duchesne, Calum Sharp, Shahnam Gorgi Zadeh, Yolanda Gómez, Vittorio Parma… | Y2 | M15 | May | 2025 | Done | On track | Technical review carried out on 13/05/2025
|  |  |  | * Mechanical studies | Calum Sharp | Sebastien Blivet, Marco Garlasche , Gilles Olivier, Calum Sharp, … | Y2 | M15 | May | 2025 | Done | On track | Technical review carried out on 13/05/2025
|  |  |  | * Close out | Calum Sharp |  | Y2 | M16 | June | 2025 | In progress | On track | FPC design report sent to Adèle De Valera on 23 June 2025
|  | WP4 | 4.6 Fabrication of RF couplers |  | CERN
M | 19 | WP4 | 4.6 | Fabrication of FPCs | Calum Sharp, Marco Garlasche | Simon Barriere, Marco Garlasche, Yolanda Gómez Martínez, Vittorio Parma, Calum Sharp, … | Y3 | M27 | May | 2026 | In progress | Risk to mitigate | This is in principle OK but considering the workload that the CERN have on many other FPCs (=same technologies) which may require revising this deadline.
|  |  |  | * Feasibility production study | Calum Sharp | Participants tbc |  | - | - | - | In progress | -
|  |  |  | * Fabrication | Marco Garlasche | Simon Barriere… |  | - | - | - | Not started | -
|  |  |  | * Close out | Calum Sharp |  | Y3 | M27 | May | 2026 | Not started | Risk to mitigate
|  | WP4 | 4.7 Test of RF couplers |  | CERN | [7 empty] | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
M | 20 | WP4 | 4.7 | Test of FPC couplers | Calum Sharp | Karin Candera, Patricia Duchesne, Marco Garlasche, Yolanda Gómez, Shahnam Gorgi Zadeh, Sebastien Jerome Calvo, Guillaume Olry, Vittorio Parma, Calum Sharp… | Y3 | M33 | Nov | 2026 | In progress | On track
|  |  |  | * RF conditioning possibilities | Calum Sharp | Karin Candera, Patricia Duchesne, Marco Garlasche, Yolanda Gómez, Shahnam Gorgi Zadeh, Guillaume Olry, Vittorio Parma, Calum Sharp… | Y2 | M15 | May | 2025 | Done | On track | Technical review carried out on 13/05/2025 where the RF conditioning at 800 MHz@ 50 kW CW was chosen (type of RF conditionning proposed in the proposal).
|  |  |  | * Setting up the test bench | Calum Sharp | participants tbc |  | - | - | - | Not started | -
|  |  |  | * Couplers preparation | Calum Sharp | participants tbc |  | - | - | - | Not started | -
|  |  |  | * RF conditionning | Calum Sharp | participants tbc |  | - | - | - | Not started | - | According to the proposal 10 months for testing
|  |  |  | * Close out | Calum Sharp |  | Y3 | M33 | Nov | 2026 | Not started | On track
D | 15 | WP4 | 4.7 | Report on RF test of 800-MHz FPC at 50 kW CW | Calum Sharp | Yolanda Gómez Martínez, Guillaume Olry, Sebastien Jerome Calvo, Vittorio Parma, Calum Sharp, … | Y4 | M39 | May | 2027 | Not started | On track
|  |  |  | * Close out | Calum Sharp |  | Y4 | M39 | May | 2027 | Not started | On track
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F26: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F28: adele de-valera: HOM design report milestone
Note on F34: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F36: adele de-valera: Engineering report of the fabrication milestone
Note on F45: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F47: adele de-valera: HOM test report milestone
Note on P47: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on F50: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on O51: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F52: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on O52: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on N55: adele de-valera: after review status and before close out
Note on N56: adele de-valera: after review status and before close out
Note on N57: adele de-valera: after review status and before close out
Note on F58: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F60: adele de-valera: Engineering report of the fabrication milestone
Note on O60: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F63: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on O63: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on P64: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on F65: adele de-valera: FPC test report milestone
Note on N66: adele de-valera: after review status and before close out
Note on F70: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F72: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management