## WP7 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y1 | M10 | Oct | 2024 | M | # | WP7 | 7.1: Coordination with industry and Dissemination – M1-M4 | Industy Board definition | Accounted for | On track
Y1 | M12 | Dec | 2024 | D | # | WP7 | 7.1: Coordination with industry and Dissemination – M1-M4 | Creation of the Industrial section of the iSAS website | Accounted for | On track
Y4 | M46 | Dec | 2027 | D | # | WP7 | 7.2: Relations with industries – M1-M48 | Report from industry board | Started | On track
Y4 | M46 | Dec | 2027 | D | # | WP7 | 7.3: Business opportunities – M24-M48 | Report on actions to maximise the business opportunities | Not started | On track
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS

## WP7 M14
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP7 | WP7 Integration into Industrial Solutions |  | INFN | CNRS | Y2 | M17 | July | 2025 |  |  | Last update timestamp
|  | WP7 | 7.1 Coordination with industry and Dissemination – M1-M48 |  | INFN
|  |  |  | WP Coordination | Person respoonsible
|  |  |  | * WPX meetings (w/ WPX iSAS indico link) | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | In progress | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | Not started | On track | w/ relevant WPX documentation to share
M | # | WP7 | 7.1 | Industy Board definition | Giorgio Keppel |  | Y1 | M8 | Oct | 2024 | Done | On track
D | # | WP7 | 7.1 | Creation of the Industrial section of the iSAS website | Oscar Azzolini |  | Y1 | M10 | Dec | 2024 | Done | On track
|  | WP7 | 7.2 Relations with industries – M1-M48 |  | Institution responsible | [5 empty] | in progress | On track
D | # | WP7 | 7.2 | Report on IB activity and actions | Oscar Azzolini | Industry | Y4 | M46 | Dec | 2027 | in progress | On track
|  |  |  | IB Reviewers Definition | Oscar Azzolini | Industry | Y2 | M17 | Jul | 2025 | in progress | On track | fixed
|  |  |  | IB WPs status presentations | Oscar Azzolini | Industry | Y2 | M20 | Oct | 2025 | in progress | On track
|  |  |  | IB 1° review | Oscar Azzolini | Industry | Y3 | M26 | Apr | 2026 | in progress | On track
|  | WPX | 7.3 Business opportunities – M24-M48 |  | Institution responsible | [5 empty] | not starded | On track
D | # | WP7 | 7.3 | Report on actions to maximise the business opportunities | Oscar Azzolini | Industry | Y4 | M46 | Dec | 2027 | not starded | On track
|  |  |  | IB 2° review | Oscar Azzolini | Industry | Y3 | M32 | Oct | 2026 | not starded | On track
|  |  |  | IB 3° review | Oscar Azzolini | Industry | Y4 | M38 | Apr | 2027 | not starded | On track
|  |  |  | IB 4° review | Oscar Azzolini | Industry | Y4 | M44 | Oct | 2027 | not starded | On track
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F28: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F29: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management