## WP8 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y1 | M6 | August | 2024 | D | 33 | WP8 | 8.2 Outreach and dissemination | Creation of a Dissemination & Exploitation Plan | Accounted for | On track | Due date postponed 1 month to M7
Y1 | M6 | August | 2024 | D | 25 | WP8 | 8.4 Open science | Development of a data management plan (DMP) | Accounted for | On track | Due date postponed 1 month to M7
Y1 | M6 | August | 2024 | D | 29 | WP8 | 8.2 Outreach and dissemination | Creation of the iSAS website | Accounted for | On track | Due date postponed 1 month to M7
Y2 | M24 | Feb | 2026 | D | 27 | WP8 | 8.2 Outreach and dissemination | First update of iSAS D&E plan | Not started | On track | Comment
Y2 | M24 | Feb | 2026 | D | 28 | WP8 | 8.4 Open science | Update of the DMP | Not started | On track | Comment
Y3 | M36 | Feb | 2027 | M | 29 | WP8 | 8.3 Diversity & equity | Implement portraits of role models on iSAS website | Not started | On track | Comment
Y4 | M44 | Oct | 2027 | D | 26 | WP8 | 8.2 Outreach and dissemination | Report on the implementation of iSAS D&E | Not started | On track | Comment
Y4 | M44 | Oct | 2027 | D | 27 | WP8 | 8.3 Diversity & equity | Reports on diversity surveys | Not started | On track | Comment
Y4 | M44 | Oct | 2027 | D | 28 | WP8 | 8.4 Open science | Implement open platform solution for iSAS partners | Not started | On track | Comment
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS

## WP8 M17
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP8 | Societal impact |  | CNRS |  | Y2 | M17 | July | 2025 |  |  | Last update timestamp
|  |  |  | WP Coordination | Adèle de Valera | [5 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP8 meetings | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | Done | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** 3rd IB meeting |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | In progress | On track | w/ relevant WPX documentation to share
|  | WP8 | 8.1 Training & Early Career |  | CNRS | [7 empty] | No M or D in GANTT (GA p127) nor SyGMa for this task -> amendment
M/D | # | WP8 | 8.1 | Train early career & industrial researchers in iSAS tech | Person respoonsible | Participants | Y3 | M36 | Feb | 2027 | Not started | On track | w/ INFN? Michele Bertucci confirmed interest
|  |  |  | * New online courses to create | Person respoonsible | Participants |  | MX |  |  | Not started | On track | with European projects EURO-LABS and I.FAST
|  |  |  | ** Phase 1 to develop iSAS tech | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** Phase 2 to use iSAS tech | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** & hands-on training during validation phase | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M36 |  |  | Not started | On track | Comment
|  | WP8 | 8.2 Outreach (from WP9.3) |  | CNRS
D | 29 | WP8 | 8.2 | Creation of the iSAS website | Ketel Turzó |  | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
D | 33 | WP8 | 8.2 | Creation of a dissemination & exploitation plan | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 27 | WP8 | 8.2 | First update of iSAS D&E plan | Adèle de Valera | Ketel Turzó | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
D | 26 | WP8 | 8.2 | Report on the implementation of iSAS D&E |  |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Creation of iSAS logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Promotional mug with logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Database of com actions to create & update |  |  |  | M5 |  |  | Done | On track | Including outside scope of conferences
|  |  |  | * Website task force to set up |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Phase 1 - Skeleton |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Phase 2 - Content |  |  |  | M10 |  |  | In progress | On track | Web developpers not responsive despite reminders
|  |  |  | * News items to write, to relay | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** CERN Courier interview |  |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** Actu in2p3 interview (relayed to com@ijclab) |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ERL4ALL related topic by Maud |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Lode Vanhecke joins iSAS at the EPFL |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** Andrei Maalberg hired, by Nick |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Job opening at ESS: Junior Engineer or Scientist to innovate on Cryomodule sustainability |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** Breakthrough from our iSAS partner HZB in SRF accelerator physics |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** HZB to host First Workshop on Ferro-Electric Fast Reactive Tuners (FE-FRTs) |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Conferences to participate to | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** ICHEP, Prague, talk | Jorgen D'Hondt |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** ESSRI, Madrid, talk | Jorgen D'Hondt |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ICRI side-event, Brisbane, talk | Jorgen D'Hondt |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** IPAC'25, Taipei, paper | HZB team |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** HIAT'25, paper presented | Maud Baylac | J. D’Hondt, J. Knobloch, C. Pira, A. Stocchi |  | M16 |  |  | Done | On track | Comment
|  |  |  | * Conference Coordinator to nominate | Nicholas Shipman |  |  | M4 |  |  | Done | On track | Comment
|  |  |  | ** Conference compilation available in repository | Nicholas Shipman |  |  | MX |  |  | In progress | On track | Comment
|  | WP8 | 8.3 Diversity & equity |  | CNRS
|  |  | 8.3 | Genera Network to join | Adèle de Valera | Ketel Turzó |  |  |  |  | In progress | On track | Comment
|  |  |  | * Genera Genaral Assembly to participate to | Adèle de Valera | [5 empty] | In progress | On track | Sept 4-5 2025 in Limerick
M | 29 | WP8 | 8.3 | Implement portraits of role models on iSAS website | Person respoonsible | Ketel Turzó | Y3 | M36 | Feb | 2027 | Not started | On track | w/ HZB Genera Network?
|  |  |  | * Interviews of high-level women scientists | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M36 |  |  | Not started | On track | Comment
D | 27 | WP8 | 8.3 | Report on diversity | Person respoonsible | Ketel Turzó | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Surveys | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on existing good practices, needs and ideas | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on diversity among early career researchers | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Awareness actions | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Mentorship for female PhD students | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M44 |  |  | Not started | On track | Comment
|  | WP8 | 8.4 Open science |  | CNRS
D | 25 | WP8 | 8.4 | Development of a data management plan (DMP) | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 28 | WP8 | 8.4 | Update of the DMP | Adèle de Valera |  | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
D | 28 | WP8 | 8.4 | Implement open platform solution for iSAS partners | Person respoonsible |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out |  |  |  | M |  |  | Not started | On track | Comment
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F29: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H32: adele de-valera: Review
Note on H33: adele de-valera: Review
Note on F51: adele de-valera: International conference on high energy physics (ICHEP)
Note on F53: adele de-valera: International Conference on Research Infrastructures (ICRI)
Note on F63: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F66: adele de-valera: (of iSAS participants)
Note on F68: adele de-valera: on unconscious biases about diversity tailored to accelerator physics groups
Note on F70: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H72: adele de-valera: Review
Note on F76: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management