## WP9 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y1 | M2 | April | 2024 | M | 30 | WP9 | 9.1 Project coordination & management | Organisation of the iSAS kick-off meeting and report | Accounted for | On track | No comment
Y1 | M6 | August | 2024 | M | 31 | WP9 | 9.3 Internal communication (from 9.1) | Internal communication plan | Accounted for | On track | Due date NOT postponed (because it's a milestone)
Y1 | M12 | Feb | 2025 | M | 36 | WP9 | 9.1 Project coordination & management | Organisation of 1st project meeting and report | Accounted for | On track | LNL, INFN, Padova, 12th-14th March 2025 (including travel)
Y1 | M12 | Feb | 2025 | M | 32 | WP9 | 9.5 Peer review of the energy-saving & report | Verifiable metric for energy-saving performances | Accounted for | On track | 3 months elay -> AMD
Y2 | M24 | Feb | 2026 | M | 33 | WP9 | 9.1 Project coordination & management | Organisation of 2nd project meeting and report | In progress | On track | HZB, Berlin, April 22-24 (including travel)
Y2 | M24 | Feb | 2026 | D | 32 | WP9 | 9.4 External relations with other projects in the accelerator landscape | Policy briefing report | Not started | On track | NOT in the GANTT (GA p 127) but in SyGMA yes -> AMD
Y3 | M28 | June | 2026 | D | 34 | WP9 | 9.1 Project coordination & management | Risk analysis related to impact of iSAS technologies | Not started | On track | Comment
Y3 | M36 | Feb | 2027 | M | 34 | WP9 | 9.1 Project coordination & management | Organisation of 3rd project meeting and report | Not started | On track | Comment
Y4 | M46 | Dec | 2027 | D | 30 | WP9 | 9.5 Peer review of the energy-saving & report | Report on energy saving performance of iSAS techn. | Not started | On track | Comment
Y4 | M48 | Feb | 2028 | M | 35 | WP9 | 9.1 Project coordination & management | Organisation of 4th project meeting and report | Not started | On track | Comment
Y4 | M48 | Feb | 2028 | D | 31 | WP9 | 9.2 Scientific coordination | Final reports of the achievement in the WPs | Not started | On track | Comment
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on J9: adele de-valera: "Redaction fo a Policy Briefing report in order to ensure that our project’ impact, contribution to EU policy goals and recommendations can inform future policy and programme development. This deliverable will be updated in the second RP" Source: Continuous reporting portal

## WP9 M17
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP9 | Coordination & management |  | CNRS |  | Y2 | M17 | July | 2025 |  |  | Last update timestamp
|  | WP9 | 9.1 Project coordination & management |  | CNRS
|  |  | 9.1 | Contractual follow-up | Adèle de Valera | Julie Gendron-Brundu, Ketel Turzó, Achille Stocchi, Jorgen D'Hondt, Elena Garbarino |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Grant Agreement (GA) to sign | Julie Gendron-Brundu | Ketel Turzó, Achille Stocchi, Jorgen D'Hondt |  | M4 |  |  | Done | On track | Comment
|  |  |  | * Consortium Agreement (CA) to sign | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | Mtbd |  |  | In progress | Risk to mitigate | CA designed to protect Consortium during project duration
|  |  |  | ** v1 to send | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | M6 |  |  | Done | On track | Comment
|  |  |  | ** Questions & comments to integrate into v2 | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | M12 |  |  | Done | On track | Comment
|  |  |  | ** v2 to send | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Questions & comments to integrate into v3 | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | In progress | On track | Comment
|  |  |  | ** v3 to send | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** Signature process to open | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** Signature process to close & CA to share | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | Not started | On track | Comment
|  |  |  | * (Shared) NDA for industrial partners | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | In progress | On track | Comment
|  |  |  | ** v1 to send | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | Done | On track | Comment
|  |  |  | ** Signature process to open | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | Done | On track | Comment
|  |  |  | ** Signature process to close & NDA to share | Julie Gendron-Brundu | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | MX |  |  | In progress | On track | Cryoelectra & Plasmatherm still missing
|  |  |  | * GA Amendment (AMD) to sign | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Elena Garbarino, next PO, Julie Gendron-Brundu |  | Mtbd |  |  | In progress | On track | Comment
|  |  |  | ** Numbering mismatches to clear up | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Elena Garbarino, next PO, Julie Gendron-Brundu |  | MX |  |  | In progress | On track | Comment
|  |  |  | ** 3 new partners to integrate | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Elena Garbarino, next PO, Julie Gendron-Brundu |  | MX |  |  | In progress | On track | RTU or even IFJ PAN partners might not find the right fit now
|  |  |  | ** WP4 4 -> 16 HOM couplers? | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Elena Garbarino, next PO, Julie Gendron-Brundu |  | M18 |  |  | In progress | On track | Depends on arbitration from WP4 Design report due M18
|  |  |  | ** WP4 post-doc hire INFN-> IJCLab | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Elena Garbarino, next PO, Julie Gendron-Brundu |  | MX |  |  | In progress | On track | INFN formally accepted, PO informed and ok -> AMD
|  |  |  | ** EU Portal demand to formalise | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Elena Garbarino, next PO, Julie Gendron-Brundu |  | MX |  |  | In progress | On track | Comment
|  |  |  | ** EU Portal process to get validated by PO | Next PO | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt, Julie Gendron-Brundu |  | MX |  |  | Not started | On track | Comment
|  |  | 9.1 | Financial follow-up | Adèle de Valera | Enora Sabater, Clément Ascenção, Ketel Turzó, Achille Stocchi |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Depreciation rules for lum-sum project to clarify | Adèle de Valera | Ketel Turzó, Achille Stocchi |  | M4 |  |  | Done | On track | CNRS rules apply to lump sum projects as other projects
|  |  |  | * Prefinancing to allocate to partners | Enora Sabater | Ketel Turzó, Achille Stocchi, Jorgen D'Hondt, Adèle de Valera |  | M10 |  |  | Done | On track | Most done by M3; 1 delayed for tech reasons, solved by M10
|  |  |  | * Timesheets for participants to multiple EU projects | Clément Ascenção | Lailina Attoumane, next financial officer, Adèle de Valera |  | M14 |  |  | Done | On track | Asked by DR4 M14 - Duchesne, Kaabi & Gandolfo concerned
|  |  |  | * Budget follow-up tool | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | Comment
|  |  |  | ** Tool to settle | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Maud Baylac, Cristian Pira, Jens Knobloch, Frederic Bordry, Peter McIntosh |  | M15 |  |  | Done | On track | Comment
|  |  |  | ** 1st year to complete | Adèle de Valera | Financial officers |  | M17 |  |  | In progress | On track | Comment
|  |  |  | ** 2nd year update | Adèle de Valera | Financial officers |  | M26 | April | 2026 | Not started | On track | Comment
|  |  |  | * Risks & deviations to follow | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  | 9.1 | Milestones & deliverables follow-up | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * iSAS Work plan to create from GA & GANTT | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  | M4 |  |  | Done | On track | Comment
|  |  |  | * WP Work plan template to propose | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt, Maud Baylac, Cristian Pira, Jens Knobloch, Frederic Bordry, Peter McIntosh |  | M14 |  |  | Done | On track | Get feedback from WPs after 1st completion for adjustments
|  |  |  | * Risks & deviations to follow | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  | 9.1 | Dialogue with PO | Adèle de Valera | Achille Stocchi |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Changes to the work plan to be discussed -> AMD | Adèle de Valera | Achille Stocchi |  | M5 |  |  | Done | On track | Comment
|  |  |  | * Transition period from Elena Garbarino to next PO | Adèle de Valera | Achille Stocchi |  | M13 |  |  | In progress | On track | Elena Garbarino PO until M13 -> AMD on standby
|  |  |  | * PO to be brought up to speed when appointed | Adèle de Valera | Achille Stocchi |  | M17 |  |  | Not started | On track
M | 30 | WP9 | 9.1 | Organisation of the iSAS kick-off meeting and report | Ketel Turzó | Achille Stocchi, Jorgen D'Hondt | Y1 | M2 | April | 2024 | Accounted for | On track | Comment
M | 36 | WP9 | 9.1 | Organisation of 1st project meeting and report | Adèle de Valera | Crisitan Pira, Silvia Martin (INFN) | Y1 | M12 | Feb | 2025 | Accounted for | On track | Comment
|  |  |  | * Host to be confirmed | Adèle de Valera | Crisitan Pira |  | M7 |  |  | Done | On track | Comment
|  |  |  | * Dates to be confirmed | Adèle de Valera | Crisitan Pira |  | M7 |  |  | Done | On track | Comment
|  |  |  | * Dedicated Indico for registration to create | Adèle de Valera |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | * Save the Date to send, reminders too | Adèle de Valera |  |  | M9 |  |  | Done | On track | Comment
|  |  |  | * Agenda to design | Crisitan Pira | Adèle de Valera, Achille Stocchi, Jorgen D'Hondt |  | M12 |  |  | Done | On track | Comment
|  |  |  | * Conference room, visits, food service booked | Silvia Martin | Crisitan Pira, Adèle de Valera |  | M12 |  |  | Done | On track | Comment
|  |  |  | * Close out | Adèle de Valera | Crisitan Pira, Achille Stocchi |  | M12 |  |  | Done | On track | Milestone report to be checked still
M | 33 | WP9 | 9.1 | Organisation of 2nd project meeting and report | Adèle de Valera | Jens Knobloch | Y2 | M24 | Feb | 2026 | In progress | On track | HZB, Berlin, April 22-24 (including travel)
|  |  |  | * Host to be confirmed | Adèle de Valera | Jens Knobloch |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Dates to be confirmed | Adèle de Valera | Jens Knobloch |  | M16 |  |  | Done | On track | Comment
|  |  |  | * Dedicated Indico for registration to create | Adèle de Valera |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | * Save the Date to send, reminders too | Adèle de Valera |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | * Agenda to design | Adèle de Valera | Jens Knobloch |  | MX |  |  | In progress | On track | Comment
|  |  |  | * Conference room, visits, food service booked | Jens Knobloch | Adèle de Valera |  | MX |  |  | In progress | On track | Comment
|  |  |  | * Close out | Adèle de Valera |  |  | M24 |  |  | Not started | On track | Comment
D | 34 | WP9 | 9.1 | Risk analysis related to impact of iSAS technologies | Person responsible | Participants | Y3 | M28 | June | 2026 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M28 |  |  | Not started | On track | Comment
M | 34 | WP9 | 9.1 | Organisation of 3rd project meeting and report | Person responsible | Participants | Y3 | M36 | Feb | 2027 | Not started | On track | Comment
|  |  |  | * Host to be confirmed | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Dates to be confirmed | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Dedicated Indico for registration to create | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Save the Date to send, reminders too | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Agenda to design | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Conference room, visits, food service booked | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
M | 35 | WP9 | 9.1 | Organisation of 4th project meeting and report | Person responsible | Participants | Y4 | M48 | Feb | 2028 | Not started | On track | Comment
|  |  |  | * Host to be confirmed | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Dates to be confirmed | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Dedicated Indico for registration to create | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Save the Date to send, reminders too | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Agenda to design | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Conference room, visits, food service booked | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M48 |  |  | Not started | On track | Comment
|  | WP9 | 9.2 Scientific coordination |  | CNRS
D | 31 | WP9 | 9.2 | Final reports of the achievement in the WPs | Person respoonsible | Participants | Y4 | M48 | Feb | 2028 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M48 |  |  | Not started | On track | Comment
|  | WP9 | 9.3 Internal communication (from 9.1) |  | CNRS
|  |  |  | * Project data repository to update regularly | Adèle de Valera | Joseph Diakun, Nicholas Shipman |  |  |  |  | In progress | On track | w/ relevant documentation to share
|  |  | 9.3 | Instances follow-up | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Instances to set up | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Governing Board Chair change | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  | M12 |  |  | Done | On track | Arrival of Peter McIntosh and brought up to speed
|  |  |  | ** Advisory Board members to nominate | Adèle de Valera | GB members |  | M13 |  |  | Done | On track | Caterina Biscari & Deepa Angal-Kalinin (LEAPS) declined
|  |  |  | * Organisation diagram to update | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP9 meetings | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Coordination panel | Achille Stocchi | Jorgen D'Hondt, Maud Baylac, Cristian Pira, Jens Knobloch, Frederic Bordry, Peter McIntosh, Adèle de Valera |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | Jorgen D'Hondt | Achille Stocchi, Adèle de Valera |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Industry Board meetings | Oscar Azzolini | Giorgio Keppel |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Advisory Board meetings | Frederic Bordry | Roberto Losito, Eugenio Nappi, Maxim Titov, Wim Leemans, Achille Stocchi, Jorgen D'Hondt, Adèle de Valera |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Governing Board meetings | Peter McIntosh | Achille Stocchi, Jorgen D'Hondt… |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Yearly project meetings | Adèle de Valera | [5 empty] | In progress | On track | All throughout the project (timeline-wise)
M | 31 | WP9 | 9.3 | Internal communication plan | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date NOT postponed (because it's a milestone)
|  |  |  | * v1 to be sent for feedback | Adèle de Valera |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | * Close out | Adèle de Valera | Ketel Turzó |  | M6 |  |  | Done | On track | Comment
|  | WP9 | 9.4 External relations with other projects in the accelerator landscape |  | CNRS
|  |  | 9.4 | Liaise with current major European R&D projects | Maud Baylac | Achille Stochhi, Jorgen D'Hondt, Adèle de Valera |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Liason w/ iFAST, TIARA, LEAPS etc. to set up | Maud Baylac | Achille Stochhi, Jorgen D'Hondt, Adèle de Valera
* 1st Advisory Board report
|  |  |  | ** Presentation of report | Frederic Bordry |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** Integration of recommendations | Adèle de Valera | Achille Stocchi, Jorgen D'Hondt |  | M15 |  |  | Done | On track | Comment
D | 32 | WP9 | 9.4 | Policy briefing report | Person respoonsible | Participants | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M24 |  |  | Not started | On track | Comment
|  | WP9 | 9.5 Peer review of the energy-saving & report |  | CNRS
M | 32 | WP9 | 9.5 | Verifiable metric for energy-saving performances | Maud Baylac | F. Bouly, J. Branlard, K. Canderan, P. Duschene, Y. Gómez Martínez, A. Neuman, V. Parma, C. Pira, H. Saugnac, C. Schmidt | Y1 | M12 | Feb | 2025 | Accounted for | On track | 3 months elay -> AMD
|  |  |  | * Discussions in Steering co | Maud Baylac | Steering co |  | M11 |  |  | Done | On track | Comment
|  |  |  | * Exchanges w/ each WP | Maud Baylac | F. Bouly, J. Branlard, K. Canderan, P. Duschene, Y. Gómez Martínez, A. Neuman, V. Parma, C. Pira, H. Saugnac, C. Schmidt |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Close out | Maud Baylac | Adèle de Valera |  | M15 |  |  | Done | On track | Milestone report to be checked still
D | 30 | WP9 | 9.5 | Final reports of the achievement in the WPs | Person respoonsible | Participants | Y4 | M46 | Dec | 2027 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M46 |  |  | Not started | On track | Comment
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on O7: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F51: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F59: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F62: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F70: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F78: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F82: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F99: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F108: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F113: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F116: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management