



**iSAS weekly meeting**

20th December 2024

Present: Achille Stocchi, Adèle de Valera

Absent: Jorgen D'Hondt

Notes:

**Website integration**

\* Adèle contacts IJCLab web developer to discuss what is expected in more detail

**AMD**

\* Latvian partners: to be decided in the coming weeks if we include them in the AMD

\* Polish partners: Achille gets back in touch to finalise their participation

**Question about iSAS citations in publications**

\* Usually, a project like iSAS is to be quoted in the Acknowledgement section of the publication with the mandatory phrase "This project has received funding from the European Union’s Horizon Europe research and innovation program under grant agreement No 101131435”; the website can be mentioned; Adèle answers to WP1 Leader

**Governing Board**

\* Change in Chairperson in favour of Peter McIntosh Jan 3 to be formally set if no comments

**WP9 metrics milestone**

\* Achille has sent a reminder for Maud Baylac to contact WP Leaders to prepare Steering Committee Jan 10

**WP7 deliverable**

\* Adèle sends a reminder to WP7 Leader for the draft to be reviewed by Achille then uploaded by Adèle into the EU Portal

**Next Weekly meetings**

\* Jan 6 (after the lab reopens)

\* Jan 20 Achille not available