## Slide 1
Project Progress Review (PPR) 2-2024
WP3, task 3.2 photogun
Présenté par:
Maud BAYLAC
20 Mars 2025

## Slide 2: Périmètre et objectifs : task 3.2
laser
Photocathode
Anode at ground (or low bias)
Ultra high vacuum environment
Cathode at high voltage DC
Q bunch
f
P
e-
e-
Electrons production via photoemission : optical pumping of a photocathode by laser light
Electron current (average) :

## Slide 3: Périmètre et objectifs : task 3.2
laser
Photocathode
Anode at ground (or low bias)
Ultra high vacuum environment
Cathode at high voltage DC
Q bunch
f
P
e-
e-
Electrons production via photoemission : optical pumping of a photocathode by laser light
Electron current (average) :
Gaël’s talk
Fatematuj’s talk

## Slide 4: Périmètre et objectifs : task 3.2
4
C. Hernandez-Garcia (JLab)
CST calculations by Adrien Plaçais (LPSC)
  Source d’électrons
    Photogun pour produire le courant à injecter dans l’ERL
  Challenges
      Courant élevé (500 pC par paquet, 40 MHz soit 20 mA)
        Durée de vie élevée (jours)

## Slide 5: Requirements
  DC photogun specifications
    High DC voltage to extract high bunch charge
    350 kV
    Multi-alkali antimonide photocathode (CsK2Sb)
    Well suited for high current : typical QE (green light) considering degradation
    Load-lock configuration
    Photocathode preparation facility (PPF) connected to the gun
    Loading of photocathodes without full gun bake for fast exchange
  Laser power
    5 W (on the photocathode) of green light (500-550 nm)
    Excellent vacuum level for good operational lifetime
    10-11 mbar or better
    Anode bias to limit QE degradation
  Collaboration agreement between IN2P3 and Research Instruments (RI) for photoinjector R&D since 2023
  Photogun based on the Cornell design*
  Hardware of Lighthouse project** (terminated) transfered to IJCLab for PERLE (gun, HV system and PPF)

## Slide 6: Organization
  IN2P3 Team : approx. 8-10 FTE (IJCLab + LPSC)
    DC gun, high voltage
    Mechanics : design and assembly
    Laser system
    Vacuum
    Photocathodes
    Diagnostics
    Command control
    Safety
  Weekly meetings (Monday morning)
  Documents stored on Atrium
  Electronic logbook : Qalitel conform
  External collaborations
    JLab : Carlos Garcia-Hernandez (HV expert)
    fundings for a visit at IJCLab for initial HV startup
    STFC: Lee Jones (photocathode expert)
    official agreement to collaborate with PERLE, fundings to be found
    INFN-LASA : Daniele Sertore, Laura Monaco, discussions on HV and photocathodes

## Slide 7: Update PPF : pre-assembly
Initial assembly disconnected from the gun for restart and checks
7
December 2024

## Slide 8: Update PPF : pre-assembly
After PPF assembly, leak on the MBE detected and cured
January 2025

## Slide 9: Update : gun assembly
Gun assembly in mobile clean room installed in the igloo (particle count satisfactory)
  2 ceramics assembled
  Next : stalk with cathode

## Slide 10: Update : laser room preparation
Next : fire detection to be installed before cleaning of the optical room (April)

## Slide 11: Update vacuum
MBE chamber vacuum
  P = 4,6.10-8 mbar w/o bake
  RGA : no indication of leak
NEG activation performed
  Ready to be installed in the gun
Calculations performed
  Additional pumping added
Chart: Analyse de gaz résiduel / MBE

## Slide 12: Update PPF : residue analyzis
Metal residue from evaporator
Analysis by « Vide et Surface » (J. Yemane)
 Il s’agit bien d’antimoine sous sa forme oxyde

## Slide 13: Update diagnostics : BPM et Faraday cup
1st BPM removed from beam line for test
  Measurement of the capacitance performed
  Electrical center still to be measured (expected from capacitance measurements : -34µm, -7µm)
Faraday cup : ordered
  To be delivered by end of the year

## Slide 14: Planning et principaux jalons du WP
Février 2026

## Slide 15: Points de vigilance
  Pour remplir le 1er jalon d’ERL4ALL phase démo : what needs to be achieved to demonstrate electron beam ?
    High voltage on cathode (>300 kV?)
    Vacuum (<10-9 mbar?)
    Photocathode (some quantum efficiency : % ?)
    Laser
    Safety and controls
    Measurements (Faraday cup : purchased)
Points de vigilance
  Photocathodes : nouveau sujet à développer à IJClab
  Câblage : RH non identifiée
  Dossier ASN et Personal Safety System (PSS) : retour attendu
  Machine Protection System (MPS) : en cours par C. Joly
  Contrôle – commande : codes des automates de RI achetés, en cours par Olivier et Victor Dalifard
  Safety : laser and chemical training from SPR
To do next regarding the laser
  Laser simulations and optimization for high bunch charge
  Look into the laser possibilities in terms of duty cycle for diagnostics and tune mode
    Sync module to be purchased
Organization of the European Workshop on Photocathodes for Accelerator Applications (EWPAA) in 2026
  Need IJCLab contact to help with local organization

## Slide 16: BACK UP

## Slide 17: Photocathodes
Main requirements for high bunch charge
  High QE
  Band gap compatible with high intensity laser
   « green » photocathodes
« Green » photocathodes (emitting in green spectrum)
  Sb-based photocathodes : multi-alkali antimonide
    Cs3Sb, Cs2KSb, Na2KSb, CsNaKSb
  Widely used for PMT industry, robust for lifetime, powerful lasers available
  Technology being developed for accelerator applications
    Multi alkali photocathodes (CsKSb, NaKSb)
  QE of several %
  Requires several Watts of green laser light (500-530 nm)
  Requires UHV : 10-10 – 10-11 mbar
  Multiple results shown at EWPAA (European Workshop for Photocathode for particle Accelerator Applications), sep 2024
  High QE with CsKSb and NaKSb
  Lower QE with NaKSb than CsKSb but better lifetime

## Slide 18: Photocathodes (3)
  Full hardware of the Photocathode Preparation Facility (PPF) in IJCLab
    still the property of RI
  Assembly in a first stage disconnected from the gun to recommission and detect possible issues
    Will have to be moved and connected to the gun at a later stage
glovebox
MBE
(Molecular-Beam Epitaxy)
gun

## Slide 19: Evaporators
Sb
Cs

## Slide 20: PPF