## Slide 1
Project Progress Review (PPR) 2-2025
WP- 08: RF systems
Présenté par: C. JOLY
20 Mars2025

## Slide 2: Etat d’Avancement
Project definition (RH, WBS, Budget) in progress but difficult to consolidate
TDR with a global definition of the RF systems in progress (DMO, Timing, FTS and LLRF).
Cavity qualification facility upgrade  1kW amplifier SAT report in progress
MO & Timing : Use of IDROGEN board solution associated to one mezzanine board (FMC REFGEN) and a µRTM board locally providing the timings signal.
 First REFGEN prototype manufactured
Top
Bottom
PLL very low noise
4 channels up to 1.3GHz
FMC connector

## Slide 3: Etat d’Avancement
RF powers Amplifiers : 4 IOT + 5 SSA strategy seems the best.
- First version of the SSA requirements
 add-on to try a “w/o power circulator” operation in progress but it seems difficult to do without risks
for the amplifiers. Contacts with JEMA France and TRUMPF.
- Project of collaboration with THALES and CERN for the IOT prototype
 waiting the result of I-Démo program evaluation.
LLRF system.
- PhD student hiring for developing a superconducting cavity real time embedded simulator for PERLE
and the optimization of LLRF firmware algorithms
 Nawal Belouchrani (collaboration IJCLab / ACS France)
 preparing the documents for ANRT in progress.

## Slide 4: Etat d’Avancement
LLRF system.
- RF front-end prototype
 realized and driver modification in progress by IOXOS.

## Slide 5: Planning et Principaux Jalons du WP-8 : RF systems
DC Gun @350 keV
2024
2025
2026
2027
2028
2029
2030
2031
Injector @ 7MeV
ERL 1-LOOP
DC gun
operation
Cryogenic
installed
Injector installed
Cryomodule
tested
Cryomodule
Installed
First ERL
demonstration
Design
Procuirement / Construction / Installation
Commissioning
20 mA
2MW
TDR
PERLE 1-LOOP 89MeV
IGLOO ready
20 mA
DMO & Timing
Board proto
series
Frequency tuning system
series
Pw mod.series
& Board proto
Cavity Qualification facility upgrade
RF proc. & modification
RF power Amplifiers (5 x SSA)
(4 x IOT)
prototype
series
series
!
FeedBack system
Series proc.
Cavity Sim. and algorithms opt.
PhD student work
€
€€
€
€
€€€
€€€

## Slide 6: Points de vigilance
Disponibilité des ressources:
  Ing Conception, 2 T/AI CAO, routage , suivi de prod
  D. Charlet (~ mi 2026 ?)
Dépenses à prévoir ( à consolider) :
2025 ( budget alloué ?)
  6k€ pour développement des cartes proto (TIMGEN et C&C FTS)
  40k€ pour réaliser la série des modules de puissance FTS
  30k€ pour réaliser la série des châssis d’interfaces RF
  ? Câbles
2026
  116k€ approvisionnements cartes IOXOS (8 + 2 spares)
  ? k€ Châssis MTCA
  ? Lignes RF
  ? Circulateurs and Load (minimum 4 but perhaps 8 )
  400k€ Amplificateurs SSA (power 10kW)  En attente de la version finale des besoins
2027
  1.2M€ Amplificateurs IOT (50kW)
  ? Upgrade Amplificateurs SSA ( power 20 kW to 50kW, bandwidth-dependent)
   En attente de la version finale des besoins
Il faudrait au moins de quoi faire les prototypes
et les racks associés ~ 16k€ minimum
Il faudrait essayer de lancer un prototype avec mise à niveau de puissance jusqu’à 50kW ( 10 mois min de délai)
( 12 mois min de délai)