## Slide 1: WP3 Nb3Sn on Cu films for 4.2K cavity operation Steering Committee Meeting 16.12.25 Focus on February Milestones and Deliverables
All information contained in this presentation and any accompanying documents is for iSAS project only and must be treated as strictly confidential.
Any dissemination, distribution or other use of this information without the consent of its owner is prohibited.
Funded by the European Union. Views and opinions expressed are however those of the authors only and do not necessarily reflect those of the European Union or the European Commission. Neither the European Union nor the granting authority can be held responsible for them.

## Slide 2
WP3 – SRF: Tasks Status
Timeline in project months (M) |  |  |  | M/D | # | Related task | Description |  | Status | Risk level
Y1 | M12 | Feb | 2025 | M | 3.1 | 3.2 Flux Trapping | Modification of choke cavity for flux trapping study |  | Done submitted | On track
Y2 | M24 | Feb | 2026 | M | 3.2 | 3.4 Adaptive Layers | Developed ALD adaptive layers on Cu |  | Done (to be submitted) | On track
Y2 | M24 | Feb | 2026 | D | 3.1 | 3.3 RF Tunability | Cavity tuning Report on implementation of cavity Q vs F tuning tool |  | In progress | On track
Y2 | M24 | Feb | 2026 | M | 39 | 3.1 Coordination of R&D on SC Cavities | Impact risk analysis WP3 |  | In progress | On track
Y3 | M30 | Aug | 2026 | M | 3.3 | 3.3 RF Tunability | Report on mechanical strength test of SC coatings |  | In progress | Risk to mitigate
Y3 | M30 | Aug | 2026 | D | 3.2 | 3.2 Flux Trapping | Flux trapping Report on flux dynamics study in Nb3Sn on Cu samples |  | In progress | On track
Y3 | M34 | Dec | 2026 | M | 3.4 | 3.5 Working Cavity @4.2K | M3.4 Characterization of Nb3Sn reference cavity |  | In progress | On track
Y4 | M38 | Apr | 2027 | D | 3.3 | 3.4 Adaptive Layers | Adapt. Layer Report on QPR study of Nb3Sn on Cu & adaptive layers |  | In progress | On track
Y4 | M46 | Dec | 2027 | D | 3.4 | 3.5 Working Cavity @4.2K | 4.5-K Cavity Report on 4.5-K Cavity performance & tunability tests |  | In progress | On track

## Slide 3
WP3 – SRF: February 2026 Milestones and Deliverable

## Slide 4
WP3 – SRF
Milestone 39 Impact risk analysis WP3
Presentation M24 (INFN)
Risk # | Description | Proposed Mitigation Measures
1 | Beneficiary leaves the project [Low & Medium] | Pro-actively: document, collaborate, strong coordination; Post-facto: redistribute tasks
2 | Lack of candidates for temporary positions [Medium & Medium] | Maximize job advertisements as early as possible and as wide as possible (professional networks), leverage on the iSAS consortium
8 | Appearance of small defects on the superconducting layers dramatically affecting the RF performance [Medium & High] | Test the coatings on smaller prototypes before depositing on the 1.3 GHz prototype; thermometry measurements will identify defects and help improving deposition (Task 3.5)
9 | Scaling the SC coatings from planar samples to 3D geometry more difficult than expected [Medium & Medium] | Additional R&D on small 3D structures to find and solve technical issues in advance (Task 3.2, Task 3.4)
10 | Fragility of A15 film may results in reduced tunability of the coated cavity [Medium & High] | Initial test on small sample in Task 3.3 to optimize thin-film coating procedure, followed by coating on a 1.3 GHz cavity in Task 3.2
11 | Delamination of ALD layers on Cu at high temperature [Medium & Medium] | Test of multilayers and different alloys to mitigate this risk
12 | Further increase of costs for Helium and/or power [Low & Medium] | Proportional reduction of number of tests or test duration