## WP4 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y2 | M16 | June | 2025 | M | 15 | WP4 | 4.5 RF coupler design | Design of FPC coupler | In progress | On track
Y2 | M18 | August | 2025 | M | 16 | WP4 | 4.2 HOM coupler design | Design of HOM coupler | In progress | On track | {{ Interconnexion }} w/ WP6 Task 6.4: impact WP4 -> WP6
Y2 | M24 | Feb | 2026 | M | 38 | WP4 | 4.1 Coordination of R&D on couplers | Impact risk analysis WP4 | Not started | On track
Y2 | M24 | Feb | 2026 | M | 17 | WP4 | 4.3 Fabrication of HOM couplers | Fabrication of HOM couplers | Not started | On track | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
Y3 | M27 | May | 2026 | M | 18 | WP4 | 4.4 Test of HOM couplers | Test of HOM couplers | Not started | On track | Test infra to be prepped & available
Y3 | M27 | May | 2026 | M | 19 | WP4 | 4.6 Fabrication of RF couplers | Fabrication of FPCs | Not started | On track | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
Y3 | M33 | Nov | 2026 | D | 14 | WP4 | 4.4 Test of HOM couplers | Report qualification HOM couplers on cavities at 300 K | Not started | Risk to mitigate | Change the delivery's date to a later date than milestone March 2027 'HOM coupler test'?
Y3 | M33 | Nov | 2026 | M | 20 | WP4 | 4.7 Test of RF couplers | Test of FPC couplers | Not started | On track | Test infra to be prepped & available
Y4 | M39 | May | 2027 | D | 15 | WP4 | 4.7 Test of RF couplers | Report on RF test of 800-MHz FPC at 50 kW CW | Not started | On track | Change the delivery's date to a later date than milestone June 2027 'FPC coupler test'?
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on M3: adele de-valera: no deviation from plans
Note on N3: adele de-valera: Task 4.5 reassigned after departure of Eric Montesinos -> ok now
Note on M4: adele de-valera: no deviation from plans
Note on N4: adele de-valera: Dependent on 800 MHz HOM coupler design delivery from WP4 - Might get delayed 4 months (cf M11 update) -> AMD
Note on M5: adele de-valera: no deviation from plans
Note on M6: adele de-valera: no deviation from plans
Note on N6: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on M8: adele de-valera: no deviation from plans
Note on M9: adele de-valera: no deviation from plans
Note on N9: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on M10: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on M11: adele de-valera: no deviation from plans
Note on M13: adele de-valera: no deviation from plans

## WP4 M15
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP4 | WP4 - Higher-order mode dampers & fundamental power couplers |  | CNRS |  | Y2 | M15 | May | 2025 |  |  | Last update timestamp: 11 December 2025
|  | WP4 | 4.1 Coordination of R&D on couplers |  | CNRS
|  |  |  | WP Coordination | Yolanda Gómez Martínez | Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma |  |  |  |  | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP4 meetings | [6 empty] | In progress | Risk level | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | Risk level | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | Risk level | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | Risk level | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | In progress | Risk level | Advisory Board WP4 recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | Risk level | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | Risk level | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | Risk level | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | Risk level | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | Risk level | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | Risk level | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | Risk level | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | Risk level | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | Risk level | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | Risk level | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | Risk level | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | Not started | Risk level | w/ relevant WP4 documentation to share
M | 38 | WP4 | 4.1 | Impact risk analysis WP4 | Yolanda Gómez Martínez | Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma | Y2 | M24 | Feb | 2026 | In progress | On track
|  |  |  | * Impact risk analysis of FPC tasks | Yolanda Gómez Martínez | Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma | Y2 | M23 | Jan | 2026 | In progress | On track
|  |  |  | * Impact risk analysis on HOM couplers tasks | Yolanda Gómez Martínez | Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Guillaume Olry, Vittorio Parma | Y2 | M23 | Jan | 2026 | In progress | On track
|  |  |  | * Close out | Yolanda Gómez Martínez |  | Y2 | M24 | Feb | 2026 | Not started | On track
|  | WP4 | 4.2 HOM coupler design |  | INFN
M | 16 | WP4 | 4.2 | Design of HOM coupler | Dario Giove | Sebastien Blivet, Karin Candera, Patricia Duchesne, Dario Giove, Yolanda Gómez Martínez, Akira Miyazaki, Gilles Olivier, Guillaume Olry, Vittorio Parma, Adrien Placais. | Y2 | M18 | August | 2025 | Done
|  |  |  | * Design of 800 MHz HOM | Patricia Duchesne | Sebastien Blivet, Patricia Duchesne, Yolanda Gómez Martínez, Gilles Olivier, Guillaume Olry, Akira Miyazaki, Adrien Placais. | Y2 | M18 | August | 2025 | Done
|  |  |  | ** RF studies | Patricia Duchesne | Patricia Duchesne, Adrien Placais. | Y2 | M17 | July | 2025 | Done |  | The technical review was carried out on 13/05/2025 with invited expert members (Carmelo Barbagallo/CERN and Shahnam Gorgi Zadeh/CERN)
|  |  |  | * *Thermical studies | Patricia Duchesne | Karin Candera, Patricia Duchesne, Vittorio Parma, Hervé Saugnac | Y2 | M17 | July | 2025 | Done |  | The technical review was carried out on 13/05/2025 with invited expert members (Carmelo Barbagallo/CERN and Shahnam Gorgi Zadeh/CERN).
|  |  |  | ** Mechanical studies | Gilles Olivier | Sebastien Blivet, Patricia Duchesne, Gilles Olivier | Y2 | M17 | July | 2025 | Done |  | The technical review was carried out on 13/05/2025 with invited expert members (Carmelo Barbagallo/CERN and Shahnam Gorgi Zadeh/CERN).
|  |  |  | * Design of 1,3 GHz HOM --> BLA desing | Dario Giove | - | Y2 | M18--> M27 | August--> May | 2025--> 2026 | Not started |  | The presentation of BriXSinO HOM was carried out on 8/07/25. Nothing about 1,3 GHz included in the report. Proposition to change to BLA design for May 2026 Design report of HOM couplers’ to update with the design report of BLA or to do a new milestone deadline M27 May 2026
|  |  |  | * Close out | Dario Giove | Patricia Duchesne | Y2 | M18 | August | 2025 | Close out |  | 800MHz HOM design updated the EU continuous reporting portal on time (26/08/25 )
|  | WP4 | 4.3 Fabrication of HOM couplers |  | CERN
M | 17 | WP4 | 4.3 | Fabrication of HOM couplers | Marco Garlasche | Simon Barriere, Marco Garlasche, Yolanda Gómez Martínez, Sebastien Jerome Calvo, Vittorio Parma, Calum Sharp… | Y2 | M24--> M34 | Feb--> Dec | 2026 | In progress | On track | New milestones dates
|  |  |  | * Fabrication of 4 prototypes 800 MHz HOM couplers | Marco Garlasche | Simon Barriere, Marco Garlasche, Vittorio Parma, Calum Sharp. | Y2 | M24--> M34 | Feb--> Dec | 2026 | In progress | On track
|  |  |  | ** Feasibility production study | Marco Garlasche | Simon Barriere, Marco Garlasche, Vittorio Parma, Calum Sharp. | - | - | - | - | In progress | On track
|  |  |  | ** Procurement of Nb | Marco Garlasche | Marco Garlasche, Calum Sharp | - | - | - | - | In progress | On track | CERN is going to use the Nb in stock to manufacture the 4 HOM couplers. An order to remplace the Nb used is on progress.
|  |  |  | ** Fabrication of 4 HOM | Marco Garlasche | Simon Barriere, Marco Garlasche | - | - | - | - | Not started | - | Coupler design file ( drawings and step) sent( 8/12/2025) by IJC Lab ( P.Duchesne) to CERN taking into account the CERN request.CERN give it a second round of check and prepare it for production.
|  |  |  | * Fabrication of 1 prototype 1.3 GHz HOM couplers --> Fabrication 1 BLA | Marco Garlasche | Dario Giove | Y2 | M30 or M34? | August or Dec? | 2026 | Not started | On track | Proposition: to change to BLA manufacture. Deadline to be confirmed before 2026
|  |  |  | * Close out | Calum Sharp |  | Y2 | M24--> M34 | Feb--> Dec | 2026 | Not started | On track
|  | WP4 | 4.4 Test of HOM couplers |  | CNRS
M | 18 | WP4 | 4.4 | Test of HOM couplers | Patricia Duchesne | participants tbc | Y3 | M27 --> M37 | May--> March | 2026--> 2027 | Not started | On track | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6 New milestones dates
|  |  |  | * 800 MHz HOM test | Patricia Duchesne | participants tbc | Y3 | M27--> M37 | May--> March | 2026-->2027 | Not started | On track | Test infra to be available. Subtasks to be defined
|  |  |  | * 1,3 GHz HOM test --> Test of the ceramic of the BLA | Dario Giove | participants tbc | Y3 | M27--> M37 | May--> March | 2026-> 2027 | Not started |  | Test infra to be available. Subtasks to be defined Proposition: to change to ceramic BLA test to March 2027
|  |  |  | * Close out | Patricia Duchesne |  | Y3 | M27 | May | 2026--> 2027 | Not started | On track
D | 15 | WP4 | 4.4 | Report qualification HOM couplers on cavities at 300 K | Patricia Duchesne | participants tbc | Y4 | M33 | Nov | 2026 | Not started | Risk to mitigate | Change the delivery's date to a later date than milestone March 2027 'HOM coupler test'?
|  |  |  | * Close out | Patricia Duchesne |  | Y4 | M33 | Nov | 2026 | Not started | On track
|  | WP4 | 4.5 RF coupler design |  | CERN
M | 15 | WP4 | 4.5 | Design of FPC coupler | Calum Sharp | Julien Angot, Sebastien Blivet, Karin Candera, Patricia Duchesne, Marco Garlasche, Yolanda Gómez, Shahnam Gorgi Zadeh, Sebastien Jerome Calvo, Gilles Olivier, Guillaume Olry, Vittorio Parma, A. Placais, … | Y2 | M16 | June | 2025 | Done |  | Report finished
|  |  |  | * RF studies | Patricia Duchesne | Julien Angot, Patricia Duchesne, Yolanda Gómez, Guillaume Olry, A. Placais, … | Y2 | M15 | May | 2025 | Done |  | Technical review carried out on 13/05/2025
|  |  |  | * Thermical studies | Karin Candera , Calum Sharp | Karin Candera, Patricia Duchesne, Calum Sharp, Shahnam Gorgi Zadeh, Yolanda Gómez, Vittorio Parma… | Y2 | M15 | May | 2025 | Done |  | Technical review carried out on 13/05/2025
|  |  |  | * Mechanical studies | Calum Sharp | Sebastien Blivet, Marco Garlasche , Gilles Olivier, Calum Sharp, … | Y2 | M15 | May | 2025 | Done |  | Technical review carried out on 13/05/2025
|  |  |  | * Close out | Calum Sharp |  | Y2 | M16 | June | 2025 | Close out |  | FPC design report sent to Adèle De Valera on 23 June 2025
|  | WP4 | 4.6 Fabrication of RF couplers |  | CERN
M | 19 | WP4 | 4.6 | Fabrication of FPCs | Calum Sharp, Marco Garlasche | Simon Barriere, Marco Garlasche, Yolanda Gómez Martínez, Vittorio Parma, Calum Sharp, … | Y3 | M27--> M35 | May--> Jan | 2026--> 2027 | In progress | On track
|  |  |  | * Feasibility production study | Calum Sharp | Participants tbc |  | - | - | - | In progress | On track
|  |  |  | * Fabrication | Marco Garlasche | Simon Barriere… |  | - | - | - | Not started
|  |  |  | * Close out | Calum Sharp |  | Y3 | M27 | May--> Jan | 2026--> 2027 | Not started
|  | WP4 | 4.7 Test of RF couplers |  | CERN | [7 empty] | {{ Interconnexion }} w/ WP6 Task 6.5: impact WP4 -> WP6
M | 20 | WP4 | 4.7 | Test of FPC couplers | Calum Sharp | Karin Candera, Patricia Duchesne, Marco Garlasche, Yolanda Gómez, Shahnam Gorgi Zadeh, Sebastien Jerome Calvo, Guillaume Olry, Vittorio Parma, Calum Sharp… | Y3 | M33-->M40 | Nov--> June | 2026--> 2027 | In progress | On track
|  |  |  | * RF conditioning possibilities | Calum Sharp | Karin Candera, Patricia Duchesne, Marco Garlasche, Yolanda Gómez, Shahnam Gorgi Zadeh, Guillaume Olry, Vittorio Parma, Calum Sharp… | Y2 | M15 | May | 2025 | Done | On track | Technical review carried out on 13/05/2025 where the RF conditioning at 800 MHz@ 50 kW CW was chosen (type of RF conditionning proposed in the proposal).
|  |  |  | * Setting up the test bench | Calum Sharp | participants tbc |  | - | - | - | Not started | -
|  |  |  | * Couplers preparation | Calum Sharp | participants tbc |  | - | - | - | Not started | -
|  |  |  | * RF conditionning | Calum Sharp | participants tbc |  | - | - | - | Not started | -
|  |  |  | * Close out | Calum Sharp |  | Y3 | M33 | Nov--> June | 2026--> 2027 | Not started | On track
D | 15 | WP4 | 4.7 | Report on RF test of 800-MHz FPC at 50 kW CW | Calum Sharp | Yolanda Gómez Martínez, Guillaume Olry, Sebastien Jerome Calvo, Vittorio Parma, Calum Sharp, … | Y4 | M39 | May | 2027 | Not started | On track | Change the delivery's date to a later date than milestone June 2027 'FPC coupler test'?
|  |  |  | * Close out | Calum Sharp |  | Y4 | M39 | May | 2027 | Not started | On track
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F26: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F28: adele de-valera: HOM design report milestone
Note on N28: adele de-valera: after review status and before close out
Note on N29: adele de-valera: after review status and before close out
Note on N30: adele de-valera: after review status and before close out
Note on N31: adele de-valera: after review status and before close out
Note on N32: adele de-valera: after review status and before close out
Note on F34: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on N34: adele de-valera: after review status and before close out
Note on F36: adele de-valera: Engineering report of the fabrication milestone
Note on F42: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F44: adele de-valera: HOM test report milestone
Note on P44: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on F47: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on O48: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F49: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on N51: adele de-valera: after review status and before close out
Note on N52: adele de-valera: after review status and before close out
Note on N53: adele de-valera: after review status and before close out
Note on N54: adele de-valera: after review status and before close out
Note on F55: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on N55: adele de-valera: after review status and before close out
Note on F57: adele de-valera: Engineering report of the fabrication milestone
Note on F60: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on O60: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on P61: adele de-valera: Dependent on delivery of 4 HOM dampers and 4 FPC from WP4
Note on F62: adele de-valera: FPC test report milestone
Note on N63: adele de-valera: after review status and before close out
Note on F67: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F69: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management