## Slide 1: WP5: Integration into a new LINAC Cryomodule Steering Committee, Dec 16, 2025 (Short update) WP Leader: Nuno Elias (ESS) WP Deputy: Vittorio Parma (CERN)
All information contained in this presentation and any accompanying documents is for iSAS project only, and must be treated as strictly confidential.
Any dissemination, distribution or other use of this information without the consent of its owner is prohibited.
Funded by the European Union. Views and opinions expressed are however those of the authors only and do not necessarily reflect those of the European Union or the European Commission. Neither the European Union nor the granting authority can be held responsible for them.

## Slide 2
WP5: Integration into a new LINAC Cryomodule
ESS | CNRS | CERN | EPFL
WP Leader: Nuno Elias (ESS)
Main contacts with other partners: G. Olry (CNRS), V. Parma. CERN); M. Siedel (EPFL)
The design of any LINAC cryomodule is optimised to meet the specific research objectives of the accelerator facility, while addressing common challenges such as high-power electric fields, ultra-low temperatures, ultra-high vacuum, precise alignment, etc.
WP5's main goal is to tackle the common engineering challenges of integrating iSAS technologies into a parametric design of a new cryomodule. , building on developments made with ESS cryomodules whilst benchmarking against other facilities
In addition, to unlock the full energy-saving capability of this cryomodule, the objective of WP5 is to also address the challenging beam dynamics requirements when operating the new cryomodule in Energy Recovery Linacs with recirculating beams.

## Slide 3
WP5: Integration into a new LINAC Cryomodule
ESS | CNRS | CERN | EPFL
Convener: Nuno Elias (ESS)
Main contacts with other partners: G. Olry (CNRS), V. Parma. CERN); M. Siedel (EPFL)
Task 5.1: Coordination on cryomodule design activities– M1-M48
• General coordination by ESS as described above.
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities– M1-M36
• Compile the lesson learned from the ESS CM testing activities, technical commissioning, and initial operation.
• Benchmarking with projects in the implementation phase (worldwide).
• Develop a roadmap to develop a new, sustainable CM design.
Task 5.3: Sustainable criteria for LINAC cryomodule design– M24-M48
• Integrate findings from the other iSAS WPs into a generic CM design.
• Explore the sustainability criteria for the design.
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48
• Simulate the beam dynamics of ERL-based accelerators when the energy efficient CM is included.
• Study the lattice design to optimize the beam and energy saving performances.

## Slide 4
WP5: Integration into a new LINAC Cryomodule
ESS | CNRS | CERN | EPFL
Work Plan

## Slide 5
WP5 – Coordination: status/evolution of Task 5.1
Task 5.1: Coordination on cryomodule design activities– M1-M48
• General coordination by ESS as described above.
Milestone 5.1 : In-person WP kick-off meeting at ESS (Due date: M3 or Jun-2024)
Milestone 5.1 : Impact Risk analysis (Due date: M24 or Feb-2026
Deliverable 5.1 : Compilation of ESS CM lessons learned & benchmarks (Due date: M24 or Feb-2026)
Deliverable 5.2 : Roadmap for the CM design (Due date: M36 or Feb-2027)
Deliverable 5.3 : Parametric design for a sustainable CM with iSAS tech. (Due date: M46 or Dec-2027)
Deliverable 5.4 : Report on beam dynamics study for ERL with iSAS CM (Due date: M43 or Sep-2027)
Y0
Y1
Y2
Y3
Y4
M5.1
D5.1
D5.2
D5.3
D5.4
Task 5.1
Task 5.2
Task 5.3
Task 5.4
Task 5.1
Task 5.2
Task 5.3
Task 5.4
Mar
2024
Mar
2025
Mar
2026
Mar
2027
Feb
2028
M
D
D
D
D
D
D
D
D
D
D
M
D
D

## Slide 6
WP5 – Coordination: status/evolution of Task 5.1
Past developments
  Regular WP5 meetings + dedicated meetings task specific
    Mar24; Apr24; Jul24; Sep24; Jan25 + (12-19)Nov24_T5.2 ; (7)Mar25_T5.4; Jul25; Sep25, Oct25
  Milestone 5.1 : “In-person WP kick-off meeting at ESS” : Completed
  Recruitment PhD student (EPFL): Started: (Apr-2024) ; Completed (Oct-2024): L. Vanhecke
  Recruitment Junior Engineer/Scientist (ESS): Started: (Mar-2025) ; Completed (Oct-2025): E. Simpson
  Included Industrial Partner (ACS) to participate in the WP5 meetings.
Current developments
  Preparation of in-Person Meeting at IJCLab Planned: (28-Jan-2026):
  § Preparation to start T.5.3. /
  § Finalize M.5.1 and M.5.2 February milestones (ESS, CERN, IJCLab)
Task 5.1: Coordination on cryomodule design activities– M1-M48
• General coordination by ESS as described above.

## Slide 7
WP5 – Experience/Benchmark CMs: status of Task 5.2
Past developments
  Discussions with relevant people: ESS CM lifecycle
  Gathering of relevant high-level information
  Preliminary table-of-contents for ESS CM lessons learned report
  Developing of on the ‘ESS CM lessons learned’ report structure
  Alignment with CM ‘benchmarking template’
Current developments
  New member in place (2 year assignment), report used as a good tool for training
  Drafting Report Ongoing.
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Compile lesson learned from the ESS CM testing activities, technical commissioning, initial operation.
• Benchmarking with projects in the implementation phase (worldwide).
• Develop a roadmap to develop a new, sustainable CM design.
Deliverable 5.1 : Compilation of ESS CM lessons learned & benchmarks (Due date: M24 or Feb-2026)
Deliverable 5.2 : Roadmap for the CM design (Due date: M36 or Feb-2027)
• Compile lesson learned from the ESS CM testing activities, technical commissioning, initial operation.

## Slide 8
WP5 – Experience/Benchmark CMs: status of Task 5.2
Past developments
  Definition of benchmarking parameters
  Definition of benchmarking facilities (ESS, SNS, LHC, PIP-II, XFEL, LCLSII)
  Definition of a benchmarking questionnaire (framework structure for response)
  Identification of the contact list (experts) people in the different facilities
  Bibliographic search completed to propose a suggestion to every answer (reviewing can be easier than completing a blank questionnaire)
  Complete of the Questionnaire (pre-filled for LHC and ESS)
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Compile lesson learned from the ESS CM testing activities, technical commissioning, initial operation.
• Benchmarking with projects in the implementation phase (worldwide).
• Develop a roadmap to develop a new, sustainable CM design.
Deliverable 5.1 : Compilation of ESS CM lessons learned & benchmarks (Due date: M24 or Feb-2026)
Deliverable 5.2 : Roadmap for the CM design (Due date: M36 or Feb-2027)
• Benchmarking with projects in the implementation phase (worldwide).

## Slide 9
WP5 – Experience/Benchmark CMs: status of Task 5.2
Current developments
  First trial with LHC and ESS to get a feedback on the proposed questions
  Distribution of the questionnaire to the facilities (LHC, ESS, XFEL, SNS, LCLS-II, PIP-II)
  Received answers to the questionnaire
  Follow-up meetings ongoing to further discuss the details of the answers
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Compile lesson learned from the ESS CM testing activities, technical commissioning, initial operation.
• Benchmarking with projects in the implementation phase (worldwide).
• Develop a roadmap to develop a new, sustainable CM design.
Deliverable 5.1 : Compilation of ESS CM lessons learned & benchmarks (Due date: M24 or Feb-2026)
Deliverable 5.2 : Roadmap for the CM design (Due date: M36 or Feb-2027)
• Benchmarking with projects in the implementation phase (worldwide).

## Slide 10
WP5 – Design new CM: status/evolution of Task 5.3
Task 5.3: Sustainable criteria for LINAC cryomodule design – M24-M48
• Integrate findings from the other iSAS WPs into a generic CM design.
• Explore the sustainability criteria for the design.
Past developments
  This task is set to start on M24 (Mar26)
Current developments
  Started conversations within the WP
  Attention to Sustainability criteria strategies applied to “Technology Areas”.
  Attention to implementation of performance criteria of technology areas and its integration.
  Breakdown of CM sub-systems (<- input from benchmarking)
  Discussions on KPI associated with each sub-system.
  Brainstorming of ideas initiated in Oct (focus on design decision trees, standardization of components
  Plan in-person meeting at IJCLAB in 28-Jan-2026, to prepare for a smooth start, meeting focus mostly on task 5.3.prepare with parametric design (create a team)
Deliverable 5.3 : Parametric design for a sustainable CM with iSAS tech. (Due date: M48 or Feb-2028)

## Slide 11
Past developments:
  Meetings with PERLE collaboration, discussing details on the RF structure and HOM’s
  Evaluated and tested beam dynamics codes to enable ERL simulations
  Written code to enable flexible simulations and gathering of results
  Benchmarking of beam dynamics tracking codes
  Development of Multi bunch and multi pass simulation
Current developments:
  General SRF cavity beam dynamic studies
    short-range and long-range wakefields (HOM’S)
    Development of Wakefield and Beam Loading models in RF track
    single- and multi-bunch instabilities (iSAS/PERLE) cavity / lattice in RF-Track
  General energy recovery efficiency studies after the degrading of beams throughout an ERL or ERL collider
  Evaluate ERL collider/light source applications for iSAS technology and perform studies on these applications
WP5 – Design new CM: status/evolution of Task 5.4
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48
• Simulate the beam dynamics of ERL-based accelerators when the energy efficient CM is included.
• Study the lattice design to optimize the beam and energy saving performances.
Deliverable 5.4 : Report on beam dynamics study for ERL with iSAS CM (Due date: M43 or SEP-2027)

## Slide 12
WP5 – Title: points of attention
Points of attention: (none)
  Setup of regular meetings (1/month)
  Aligning with WP6 on design and integration
  Deadline of Task 5.4 (ERL beam studies in Sep-2027: 5month earlier than eop)

## Slide 13
WP5 – Title: financial status
Financial status :
  No deviations reported

## Slide 14
Thank you