## GANTT
Task | Description | YEAR 1 | [7 empty] | YEAR 2 |  |  |  |  | YEAR 3 | [7 empty] | YEAR 4
WP1 | Ferro-Eletric Fast Reactive Tuners
1.1 | Coordination of R&D on FE-FRT | [12 empty] | M
1.2 | FE-FRT for Transient Beam Loading | [12 empty] | M | [7 empty] | M |  |  |  | D
1.3 | FE-FRT for Microphonics | [12 empty] | M | [7 empty] | M |  |  |  | D |  |  | M |  |  |  | D
1.4 | FE-FRT in Energy-Recovery LINAC (ERL) mode | [16 empty] | M |  |  |  | D
WP2 | Low Level RF Controls
2.1 | Coordination of R&D on LLRF |  |  |  |  | D | [7 empty] | M
2.2 | Efficient field control for high loaded-quality factor cavities | [20 empty] | M | [8 empty] | D
2.3 | Vibration analysis and detuning control of cavities | [17 empty] | M |  |  | D
2.4 | Integrated LLRF control using Ferro-Electric Fast Reactive Tuners | [28 empty] | M |  |  | D
2.5 | Energy efficient supervisory control and fault diagnosis | [16 empty] | M |  |  |  | D |  |  |  |  | M |  |  |  |  | D
WP3 | Nb3Sn-on-Cu films for 4.2-K cavity operation
3.1 | Coordination of R&D on SC cavities | [12 empty] | M
3.2 | Flux trapping | [7 empty] | M | [8 empty] | D
3.3 | RF Tunability | [12 empty] | D |  |  |  | M
3.4 | Adaptative layers | [12 empty] | M | [9 empty] | D
3.5 | Working Cavity @ 4.2 K | [18 empty] | M | [10 empty] | D
WP4 | Higher-Order Mode dampers and Fundamental Power Couplers
4.1 | Coordination of R&D on couplers | [12 empty] | M
4.2 | HOM coupler design | [11 empty] | M
4.3 | Fabrication of HOM couplers | [12 empty] | M | [5 empty] | M
4.4 | Test of HOM couplers | [14 empty] | M |  |  | D |  |  |  | M |  | D
4.5 | RF coupler design | [10 empty] | M
4.6 | Fabrication of RF couplers | [14 empty] | M |  |  |  |  | M
4.7 | Test of the RF couplers | [14 empty] | M |  |  | M | [5 empty] | D | M | D
4.8 | BLA design | [16 empty] | M
4.9 | Fabrication of BLA | [21 empty] | M
4.10 | Tests of ceramics for BLA | [26 empty] | D
WP5 | Integration into a new LINAC Cryomodule
5.1 | Coordination on cryomodule design activities |  |  | M | [9 empty] | M
5.2 | ESS cryomodules experience & benchmarking with other recent facilities | [12 empty] | D | [7 empty] | D
5.3 | Sustainability criteria for LINAC cryomodule design | [29 empty] | D
5.4 | Beam Dynamics for ERL-based accelerators with energy-efficient CMs | [26 empty] | D
WP6 | Integration into Accelerator and Collider RIs
6.1 | Coordination of integration in existing cryomodules | [12 empty] | M
6.2 | Retrofitting FE-FRTs into existing cryomodules HL-LHC oriented | [12 empty] | D |  |  |  | D
6.3 | Adapt the existing ESS cryomodule | [11 empty] | M
6.4 | Fabrication and validation of cryomodule components | [16 empty] | M | [9 empty] | M
6.5 | Assembly and test of adapted cryomodule | [23 empty] | M | [5 empty] | D
WP7 | Integration into Industrial Solutions
7.1 | Coordination with industry and Dissemination |  |  |  | M
7.2 | Relations with industries | [6 empty] | D | [22 empty] | D
7.3 | Business opportunities | [29 empty] | D
WP8 | Societal Impact
8.1 | Training & Early Career
8.2 | Outreach & Dissemination |  |  |  |  | D | D | [6 empty] | M | [14 empty] | D
8.3 | Diversity & Equity | [20 empty] | M | [6 empty] | D
8.4 | Open Science |  |  |  |  | D | D | [6 empty] | M | [14 empty] | D
WP9 | Coordination & Management
9.1 | Project Coordination and Management |  | M |  |  | M |  |  | M |  |  |  |  | M |  |  | D |  |  |  |  | M | [10 empty] | M
9.2 | Scientific Coordination | [31 empty] | D
9.3 | Internal communication |  |  |  |  | D | D
9.4 | External relations with other projects in the accelerator landscape | [12 empty] | D
9.5 | Peer review of the energy-saving performance | [7 empty] | M |  | M | [19 empty] | D
Note on AK22: adele de-valera: Delay from M24 Feb 2025 to M34 Dec 2026 -> AMD
Note on AN23: adele de-valera: Delay from M27 May 2026 to M37 March 2027 -> AMD
Note on AP23: adele de-valera: Delay from M33 Nov 2026 to M39 May 2027 -> AMD
Note on AL25: adele de-valera: Delay from M27 May 2026 to M35 Jan 2027 -> AMD
Note on AD26: adele de-valera: New milestone • M4.7: Design report of BLA. Deadline M27 May 2026
Note on AQ26: adele de-valera: Delay from M33 Nov 2026 to M40 June 2027 -> AMD
Note on AS26: adele de-valera: Delay from M39 May 2027 to M42 August 2027 -> AMD
Note on AG27: adele de-valera: New milestone • M4.8: Engineering report of the fabrication of BLA. Deadline M30 August 2026
Note on AN28: adele de-valera: New milestone • M4.9: Test report of ceramics for BLA. Deadline M37 March 2027
Note on AT29: adele de-valera: New deliverable • D4.3: Report qualification of ceramics for BLA test. Deadline M43 Septembre 2027
Note on AG37: adele de-valera: Delay from M24 Feb 2025 to M30 August 2026 -> AMD
Note on AT39: adele de-valera: Delay from M30 August 2026 to M43 Sept 2027 -> AMD
Note on J47: adele de-valera: Due date postponed 1 month to M7
Note on J49: adele de-valera: Due date postponed 1 month to M7
Note on O51: adele de-valera: Milestone report to be checked still
Note on J53: adele de-valera: Due date postponed 1 month to M7
Note on O55: adele de-valera: Delayed 3 months to M15 in AMD to be validated
Note on R55: adele de-valera: if greenlight form PO in AMD, new due date forseen for delayed milestone due M12

## Key
Status | Risk level | Timestamp
Not started | On track
In progress | Risk to mitigate
To review | In difficulty
Done
To validate
Accounted for
Displaced
Note on F2: adele de-valera: project month at the time of updating the GANTT chart
Note on D4: adele de-valera: no deviation from plans
Note on D5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on B6: adele de-valera: in-between in progress status and done status
Note on D6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on B7: adele de-valera: after review status and before close out
Note on B8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on B9: adele de-valera: on EU continuous reporting portal by project management
Note on B11: adele de-valera: delayed to an ulterior due date