## WP1 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description |  | Status | Risk level | Comments
Y1 | MX | M name | 2024 | M/D | # | WPX | X.1 Task 1 name | M/D description |  | Accounted for | On track | Comment
Y1 | MX | M name | 2024 | M/D | # | WPX | X.3 Task 3 name | M/D description |  | Accounted for | On track | {{ Interconnexion }} w/ WPY Task Y.?: impact WPX -> WPY
Y1 | MX | M name | 2025 | M/D | # | WPX | X.1 Task 1 name | M/D description |  | Accounted for | On track | Comment
Y1 | MX | M name | 2025 | M/D | # | WPX | X.5 Task 5 name | M/D description |  | Accounted for | On track | Test infra to be prepped
Y2 | MX | M name | 2025 | M/D | # | WPX | X.1 Task 1 name | M/D description |  | In progress | On track | Comment
Y2 | MX | M name | 2026 | M/D | # | WPX | X.4 Task 4 name | M/D description |  | In progress | In difficulty | To warn coordination asap
Y3 | MX | M name | 2026 | M/D | # | WPX | X.1 Task 1 name | M/D description |  | Not started | On track | Comment
Y3 | MX | M name | 2027 | M/D | # | WPX | X.1 Task 1 name | M/D description |  | Not started | On track | Comment
Y4 | MX | M name | 2027 | M/D | # | WPX | X.5 Task 5 name | M/D description |  | Not started | On track | Test infra to be available
Y4 | MX | M name | 2028 | M/D | # | WPX | X.1 Task 1 name | M/D description |  | Not started | Risk to mitigate | Mitigation proposed
Y4 | MX | M name | 2028 | M/D | # | WPX | X.2 Task 2 name | M/D description |  | Not started | On track | Comment
WP1 - Ferro-electric fast reactive tuners
| M | 41 | WP1 | 1.1 Coordination of R&D on FE-FRT | Impact risk analysis WP1 | HZB | Y2 | M24 | Feb | 2026 | In progress | On track
| M | ? | WP1 | 1.2 FE-FRT for transient beam loading | ? | CERN | Y2 | M24 | Feb | 2026 |  |  | Deleted
| M | 3 | WP1 | 1.2 FE-FRT for transient beam loading | Test of 400 MHz cavity with FE-FRT | CERN | Y3 | M36 | Feb | 2027 | In progress | On track | Dependent on WP6 task 6.2
| D | 2 | WP1 | 1.2 FE-FRT for transient beam loading | Report 400 MHz high-power RF test (transient detuning) | CERN | Y4 | M40 | June | 2027 | Not started | On track
| M | 1 | WP1 | 1.3 FE-FRT for microphonics | FE material characterised | HZB | Y2 | M24 | Feb | 2026 | In progress | On track
| M | 4 | WP1 | 1.3 FE-FRT for microphonics | Test of single-cell 1.3 GHz cavity with FE-FRT | HZB | Y3 | M36 | Feb | 2027 | In progress | On track
| D | 3 | WP1 | 1.3 FE-FRT for microphonics | Report on 1.3 GHz single-cell test with FE-FRT | HZB | Y4 | M40 | June | 2027 | Not started | On track
| M | 5 | WP1 | 1.3 FE-FRT for microphonics | Test of multi-cell 1.3 GHz cavity with FE-FRT | HZB | Y4 | M44 | Oct | 2027 | Not started | On track
| D | 4 | WP1 | 1.3 FE-FRT for microphonics | Report on RF test with FE-FRT & LLRF for microphonics | HZB | Y4 | M48 | Feb | 2028 | Not started | On track
| M | 2 | WP1 | 1.4 FE-FRT in energy-recovery LINAC (ERL) mode | Design ready for FE-FRT integration in 802 MHz cavity | CNRS | Y3 | M30 | August | 2026 | In progress | Risk to mitigate | Relies on task 6.2
| D | 1 | WP1 | 1.4 FE-FRT in energy-recovery LINAC (ERL) mode | Report of FE-FRT integration with PERLE cavities | CNRS | Y3 | M36 | Feb | 2027 | Not started | On track
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS

## WP1 M17
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP1 | Energy savings from the RF power use (FRT) |  | HZB, CERN | CERN, HZB, IJCLab/CNRS, U Lancaster (associated WP6) | Y2 | M17 | July | 2025 |  |  | Last update timestamp
|  | WP1 | 1.1 Coordination energy savings from the RF power use |  | HZB, CERN
|  |  |  | WP Coordination | Axel Neumann, Alec Macperhson (deputy) | Alick Macpherson, Sam Smith, Nicholas Shipman, Walid Kabi, Graeme Burt etal. |  |  |  |  | In progress | On track | A more detailed plan with internal milestones is being developed
|  |  |  | * WPX meetings (w/ WPX iSAS indico link) | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | In progress | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | Not started | On track | w/ relevant WPX documentation to share
|  | WP1 |  | General description | Axel Neumann, Alick Macperhson (deputy) |  | YX | MX | M name | Year | In progress | On track | Interconnection with WP6 Task 6.2 and WP2 Task 2.3
|  |  |  | Coordinate work package and interlink to partner work packages | Axel Neumann | Alick Macpherson, Graeme Burt |  | MX |  |  | Done | On track | U Lancaster from WP6 forms a strong partner for task 1.2 and fundamental FRT studies
|  |  |  | *Bi-weekly work package meetings | Axel Neumann | all |  | MX |  |  | Done | On track | Started out with every four weeks, increased to bi-weekly
|  |  |  | * Yearly iSAS meetings |  |  |  | MX |  |  | In progress | On track
|  |  |  | Paris 2024 |  | all |  | MX |  |  | Done | On track
|  |  |  | Padova 2025 |  | all |  | MX |  |  | Done | On track
|  |  |  | Berlin 2026 |  | all |  | MX |  |  | In progress | On track | Preparation started, date fixed, first LOC iSAS meeting 09.10.25
|  |  |  | * Exchange of personnel | Axel Neumann, Alick Macperhson | all |  | MX |  |  | In progress | On track | First exhange between CERN and HZB took place, more is planned with measurement campaings at CERN
|  |  |  | * Topical workshop | Nicholas Shipman | open to iSAS plus beyond |  | MX |  |  | In progress | On track | HZB organizes an FE-FRT workshop in November 2025
M | 41 | WP1 | 1.1 | Impact risk analysis WP1 | Axel Neumann | all | Y1 | M24 | Feb | 2026 | In progress | On track | During the first one and a half year, the evaluation of risks becomes more clear
|  |  |  | Risk analysis Task 1.2 FRT for transient beam-loading | Alick Macperhson | [5 empty] | Done | On track | Comment
|  |  |  | Risk analysis Task 1.3 FRT for microphonics | Axel Neumann, Nicholas Shipman | [5 empty] | Done | On track | Comment
|  | WP1 | 1.2 FRT for Transient Beam Loading |  | CERN
|  |  | 1.2.0 | * Design of Tuner for Transient Detuning Demonstrator at 400MHz | Alick Macpherson, Sam Smith | CERN TDD Team, Ilan Ben-Zvi, Paul Schneider, Graeme Burt, Nicholas Shipman |  |  | Nov | 2024 | Done |  | iSAS design contribution with existing CERN design effort that has taken several years of development. iSAS members have taken the RF and mechanical design to completion. This work has produced a submitted puplication ( https://doi.org/10.48550/arXiv.2504.19825)
|  |  | 1.2.1 | * Fabrication of TDD Tuner | Alick Macpherson, Sam Smith | CERN TDD Team, CERN Main Workshop, Ilan Ben-Zvi, Mickael Crouvizier |  |  | June | 2025 | Done |  | Fabrication done by the central CERN workshop, with iSAS funded contribution to the processing/evalustion of ferroelectrics material
|  |  | 1.2.2 | * Design and Fabrication of supporting Infrstructure | Alick Macpherson, Sam Smith | CERN TDD Team, Ilan Ben-Zvi, Paul Schneider |  |  | July | 2024 | Done |  | Extensive support infrastructure put in place to enable the TDD to be tested in CERN's Verttical Test cryostat, with and a simplified LHC 400MHz Nb-on-Cu cavity
|  |  | 1.2.2.0 | ** Design and fabrication of tooling for processing and characterisation of ferroelectric material | Alick Macpherson, Sam Smith | CERN TDD Team, Ilan Ben-Zvi, Paul Schneider |  |  |  |  | Done |  | Fabrication of material test stand done in CERN main workshop, while preparation of ferroelctric material done by joint CERN and local company develpoment
|  |  | 1.2.2.1 | ** Design and fabrication of infrastructre for integration in the CERN cryostat, including a dedicated Anti-Cryostat insert | Alick Macpherson, Sam Smith | CERN TDD Team, Ilan Ben-Zvi, Paul Schneider |  |  |  |  | Done |  | Anticryostat done in the CERN central design office and main workshop. Custom HV pulsers and RF Amplifers sourced through European suppliers.
|  |  | 1.2.3 | * Development of measuerment stand LLRF | Alick Macpherson, Sam Smith | CERN TDD team & CERN LLRF support: Diego Barrientos, Leonardo Balocchi, Tomasz Wlostowski |  |  | April | 2025 | To validate | On track | LLRF and readout based on CERN 's Universal Cavity Controller used for standard cavity tests. iSAS related upgrades for TDD include dedicated high ganularity buffer data for fast frequency tracking and emulation of beam loading by manipulation of the LLRF control loop.
|  |  | 1.2.4 | * Commisioning TDD and Beam Loading Emulation (BLEEP) at 4.2K | Alick Macpherson, Sam Smith | CERN TDD team & CERN LLRF support: Diego Barrientos, Leonardo Balocchi, Nicholas Shipman |  |  | Oct | 2025 | In progress | On track | Roll out of VME readout systems using upgraded tool chains is ongoing, with both iSAS and non-iSAS personnel involved.
|  |  | 1.2.5 | * Low power performance of TDD at 400MHz | Alick Macpherson, Sam Smith | CERN TDD team + Ilan Ben-Zvi + participants tbc |  |  | Jan | 2026 | In progress | On track | Test was shifted towards October to rework the cryostat
|  |  | 1.2.6 | * Review of results and feasibility | Alick Macpherson, Sam Smith | [5 empty] | In progress | On track
|  |  | 1.2.7 | * Adaptation for high power operation in Vertical test cryostat |  | CERN TDD team + Ilan Ben-Zvi + participants tbc |  |  | May | 2026 | In progress | On track | Modifications will be contingent on results from low power RF tests
|  |  | 1.2.8 | * High power RF performance | Alick Macpherson, Sam Smith | CERN TDD team + Ilan Ben-Zvi + participants tbc |  |  | Sept | 2026 | In progress | On track | RF design of TDD anticipateds high power scheme
M | 3 |  | 1.2 | FE-FRT for transient beam loading: Test of 400 MHz cavity with FE-FRT | Alick Macpherson, Sam Smith |  | Y3 | M36 | Feb | 2027 | Not started
|  |  | 1.2.9 | * Integration study into LHC cryomodule design |  | CERN TDD team + Ilan Ben-Zvi + participants tbc |  |  |  |  | Not started |  | Initial Design comcepts discussed and will seek access to LHC protoype cryomodule for testing Expecting approved fellow slot to be filled shortly
D | 2 |  | 1.2 | * Report 400 MHz high-power RF test (transient detuning) | Alick Macpherson, Sam Smith | CERN TDD team + Ilan Ben-Zvi + participants tbc | Y4 | M40 | June | 2027 | Not started
|  |  | 1.2.10 | Close out
|  | WP1 | 1.3 FRT for Microphonics |  | HZB
|  |  | 1.3.0 | RF and mechanical design reviewe | Nicholas Shipman, Axel Neumann, André Frahm | Axel Neumann, André Frahm, Alena Prudnikava |  |  | March | 2024 | Done |  | The first design was reviewed, further optimizations during production are on-going
|  |  | 1.3.1 | FRT RF design ready | Nicholas Shipman | Axel Neumann, André Frahm, Andrey Ushakov |  |  | Mai | 2025 | Done |  | Design for the single cell prototype is done, procurement of parts on-going
|  |  | 1.3.2 | FRT Mechanical design ready | André Frahm | Nicholas Shipman, Axel Neumann |  |  | June | 2025 | Done |  | Procurement is on-going. 3D model printed, assembly tested, risk with ceramic assembly?
|  |  | 1.3.3 | FRT ceramic sample preparation and analysis | Nicholas Shipman | Alena Prudnikava, André Frahm |  |  | Dec | 2025 | In progress | Risk to mitigate | Sample prepration impacts RF performance in teststand, recipe being developed. Not initially planned
M | 1 | WP1 | 1.3 | FE material characterized at 1300 MHz | Nicholas Shipman | Axel Neumann, André Frahm, Alena Prudnikava | Y2 | M24 | Feb | 2026 | In progress | On track | Issues with the FE characterization teststand are being resolved by Euclid, preparation and analysis of sampke became more of a topic
|  |  | 1.3.4 | Prepare 2-cell cavity for M4 test | Nicholas Shipman | Axel Neumann |  |  | Sept | 2025 | In progress | On track | Helium vessel welding and HPR required at minimum
|  |  | 1.3.5 | Design and fabricate FPC for FRT test | Nicholas Shipman | Axel Neumann |  |  | Oct | 2026 | Not started |  | A different coupling is required compared to high Q test antennas
|  |  | 1.3.6 | Link to 2.3: Develop controller for FRT (LLRF) | Andrey Ushakov | Axel Neumann |  |  | Nov | 2026 | In progress | On track | Will be based on RFSoC using e.g. SEL with HV control for microphonics compensation via FRT
|  |  | 1.3.7 | Reference test of prepared 2-cell cavity | Axel Neumann | Nicholas Shipman |  |  | May | 2026 | In progress | On track | Reference test to evaluate impact of FRT in SRF cavity performance
|  |  | 1.3.8 | Low power FRT test with VNA | Nicholas Shipman | Axel Neumann |  |  | June 2026 |  | Not started |  | Analyze RF performance at low power level at RT
M | 4 | WP1 | 1.3 | Test of single-cell 1.3 GHz cavity with FE-FRT | Nicholas Shipman | Axel Neumann, André Frahm, Jan Ullrich, Andrey Ushakov | Y3 | M36 | Feb | 2027 | Not started
|  |  |  | * Assembly and integration into HoBiCaT teststand | André Frahm | Jan Ullrich, Nicholas Shipman |  |  |  |  | Not started |  | Assembly is planned, but a trial needs to be performed prior to final assembly
|  |  |  | * Cleanroom assembly of antenna with cavity | Jan Ullrich | Nicholas Shipman, Axel Neumann |  |  |  |  | Not started
D | 3 | WP1 | 1.3 | Report on 1.3 GHz single-cell test with FE-FRT | Nicholas Shipman, Axel Neumann | Andriy Ushakov, Alena Prudnikava, André Frahm | Y4 | M40 | June | 2027 | Not started
|  |  | 1.3.9 | Preparation of multi-cell cavity with mechanical tuner and FPC | Axel Neumann | André Frahm, Nicholas Shipman, Jan Ullrich, Michael Schuster |  |  | June | 2026 | Not started
|  |  | 1.3.10 | Upgrade and rework of FE-FRT for multi-cell test | Nicholas Shipman | André Frahm, Axel Neumann, Alena Prudnikava, Andrey Ushakov, Jan Ullrich, Michael Schuster |  |  | March | 2027 | Not started | Risk to mitigate | Tight schedule, only minor modifications possible after M4, eventually fabricate second unit earlier?
|  |  | 1.3.11 | Cleanroom assembly of multi-cell, assembly strategy | Jan Ullrich | André Frahm, Michael Schuster, Axel Neumann |  |  | Sept | 2027 | Not started
M | 5 | WP1 | 1.3 | Test of multi-cell 1.3 Ghz cavity with FE-FRT | Nicholas Shipman, Axel Neumann | Axel Neumann, André Frahm, Jan Ullrich, Andrey Ushakov | Y4 | M44 | Oct | 2027 | Not started | Risk to mitigate | Planning towards this milestone needs more detailing and also depends on lab resources
|  |  |  | * Demonstrate power savings | [6 empty] | Not started |  | As described in energy metrics
D | 4 | WP1 | 1.3 | Report on RF test with FE-FRT and LLRF for microphonics | Nicholas Shipman, Axel Neumann | Andrey Ushakov | Y4 | M48 | Feb | 2028 | Not started
|  |  | 1.3.11 | Close out
|  | WP1 | 1.4 | FRT in ERL mode | IJCLab
M | 2 | WP1 | 1.4 | Design ready for FE-FRT integration into 802 MHz cavity | Walid Kaabi | na | Y3 | M30 | August | 2026 | Not started | Risk to mitigate | Unclear at the moment, whether a phd student can be assigned to this task. Contribution from patners depend on FCC use case and work of CERN for 800 MHz plus studies from WP6.2
D | 1 | WP1 | 1.4 | Report of FE-FRT integration with PERLE cavities | Walid Kaabi | na | Y3 | M36 | Feb | 2027 | Not started |  | Not planned for first cryo-module, but an option for second, who studies this, see M2
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F32: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F35: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F39: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F43: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F66: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management