## WP3 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y1 | M12 | Feb | 2025 | M | 3.1 | WP3 | 3.2 Flux Trapping | Modification of choke cavity for flux trapping study | Done | On track | Submitted on March 2024
Y2 | M24 | Feb | 2026 | M | 3.2 | WP3 | 3.4 Adaptive Layers | Developed ALD adaptive layers on Cu | Done | On track | To be submitted. Document ready
Y2 | M24 | Feb | 2026 | D | 3.1 | WP3 | 3.3 RF Tunability | Cavity tuning Report on implementation of cavity Q vs F tuning tool | In progress | On track
Y2 | M24 | Feb | 2026 | M | 39 | WP3 | 3.1 Coordination of R&D on SC Cavities | Impact risk analysis WP3 | In progress | On track | Dedicated discussion during next WP3 meeting in November
Y3 | M30 | Aug | 2026 | M | 3.3 | WP3 | 3.3 RF Tunability | Report on mechanical strength test of SC coatings | In progress | Risk to mitigate | Sample preparation will start soon
Y3 | M30 | Aug | 2026 | D | 3.2 | WP3 | 3.2 Flux Trapping | Flux trapping Report on flux dynamics study in Nb3Sn on Cu samples | In progress | On track
Y3 | M34 | Dec | 2026 | M | 3.4 | WP3 | 3.5 Working Cavity @4.2K | M3.4 Characterization of Nb3Sn reference cavity | In progress | On track | Waiting I.FAST cavity finalization - characterization facility almost ready
Y4 | M38 | Apr | 2027 | D | 3.3 | WP3 | 3.4 Adaptive Layers | Adapt. Layer Report on QPR study of Nb3Sn on Cu & adaptive layers | In progress | On track
Y4 | M46 | Dec | 2027 | D | 3.4 | WP3 | 3.5 Working Cavity @4.2K | 4.5-K Cavity Report on 4.5-K Cavity performance & tunability tests | In progress | On track | Starting
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS

## WP3 M17
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP3 | Nb3Sn on Cu films for 4.2K cavity operation |  | INFN |  | Y2 | M17 | July | 2025 |  |  | Last update timestamp
|  | WP3 | 3.1 Coordination of R&D on SC Cavities |  | INFN
|  |  |  | WP Coordination | Cristian Pira | T. Proslier (CEA), O.Kugeler (HZB), O. Malyshev and R. Valizadeh (UKRI) | YX | MX | M name | Year | In progress | On track
|  |  |  | * WPX meetings (w/ WPX iSAS indico link) | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | In progress | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | Not started | On track | w/ relevant WPX documentation to share
|  |  |  | * WP3 meetings | [6 empty] | In progress | On track
|  |  |  | WP3 Meeting 01 - Task leaders Pre-Kick-Off remote meeting | Cristian Pira | WP3 team | Y1 | M0 | Feb | 2024 | Done | On track
|  |  |  | WP3 Meeting 02 - Kick-Off meeting in Paris (hybrid) (in collaboration with I.FAST WP9) | Cristian Pira | WP3 team | Y1 | M2 | Apr | 2024 | Done | On track
|  |  |  | WP3 Meeting 03 - Task Leaders remote meeting (in collaboration with I.FAST WP9) | Cristian Pira | WP3 team | Y1 | M5 | Jul | 2024 | Done | On track
|  |  |  | WP3 Meeting 04 – Hybrid meeting in Berlin (in collaboration with I.FAST WP9) | Cristian Pira | WP3 team | Y1 | M10 | Dec | 2024 | Done | On track
|  |  |  | WP3 Meeting 05 – Annual meeting in LNL (hybrid) | Cristian Pira | WP3 team | Y2 | M13 | Mar | 2025 | Done | On track
|  |  |  | WP3 Meeting 06 – I.FAST Annual meeting in Cracow (hybrid) | Cristian Pira | WP3 team | Y2 | M14 | Apr | 2025 | Done | On track
|  |  |  | WP3 Meeting 07 - Online meeting in November | Cristian Pira | WP3 team | Y2 | M21 | Nov | 2025 | In progress | On track
|  |  |  | * Steering Committee | [6 empty] | In progress | On track
|  |  |  | ** Oct Steering Co |  |  | Y1 | M8 | Oct | 2024 | Done | On track
|  |  |  | ** Jan Steering Co |  |  | Y1 | M11 | Jan | 2025 | Done | On track
|  |  |  | ** April Steering Co |  |  | Y2 | M14 | Apr | 2025 | In progress | On track | Advisory Board WP4 recos to integrate
|  |  |  | ** July Steering Co |  |  | Y2 | M17 | Jul | 2025 | Not started | On track
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track
|  |  |  | ** 1st IB meeting |  |  | Y1 | M8 | Oct | 2024 | Done | On track
|  |  |  | ** 2nd IB meeting |  |  | Y1 | M10 | Dec | 2024 | Done | On track
|  |  |  | ** Industry Workshop in Padova |  |  | Y2 | M13 | Mar | 2025 | Done | On track
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track
|  |  |  | ** Kick-off meeting at IJCLab |  |  | Y1 | M2 | Apr | 2024 | Done | On track
|  |  |  | ** Padova meeting |  |  | Y2 | M13 | Mar | 2025 | Done | On track
|  |  |  | ** Berlin meeting |  |  | Y3 | M25 | Apr | 2026 | Not started | On track
|  |  |  | ** Lund meeting |  |  | Y4 | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  | Y4 | M48 |  |  | Not started | On track | Host tbc
M | 39 | WP1 | 1.1 | Impact risk analysis WP3 | Cristian Pira | WP3 team | Y1 | M24 | Feb | 2026
|  |  |  | * Project data repository to update regularly | Cristian Pira | T. Proslier (CEA), O.Kugeler (HZB), O. Malyshev and R. Valizadeh (UKRI) |  |  |  |  | Not started | Risk to mitigate | w/ relevant WP3 documentation to share
|  | WP3 | 3.2 Flux Trapping |  | UKRI
M | 3.1 | WP3 | 3.2 | Modification of choke cavity for flux trapping study | Oleg Malyshev (UKRI) |  | Y1 | M12 | Feb | 2025 | Accounted for | On track
|  |  |  | *Design and procurement of choke cavity facility upgrade | Oleg Malyshev (UKRI) | D. Seal (UKRI) | Y1 | M12 | Feb | 2025 | Done | On track
|  |  |  | * Close out |  |  | Y1 | M12 | Feb | 2025 | Accounted for | On track
D | 3.2 | WP3 | 3.2 | Flux trapping Report on flux dynamics study in Nb3Sn on Cu samples | Oliver Kugeler (HZB) |  | Y3 | M30 | Aug | 2026 | In progress | On track
|  |  |  | *Measurement on Nb3Sn sample with and without buffer layer | Oliver Kugeler (HZB) | Felix Kramer | Y2 | M14 | May | 2025 | Done | On track | 2 Samples tested
|  |  |  | *New test on STFC and INFN samples | Oliver Kugeler (HZB) | Felix Kramer | Y3 | M28 | Jul | 2026 | In progress | On track
|  |  |  | **Sample preparation at STFC | C. Pira (INFN) |  | Y2 | M20 | Oct | 2025 | In progress | On track
|  |  |  | **Sample preparation at INFN | C. Pira (INFN) | D. Fonnesu, D. Ford, M. Lazzari, E. Chyhyrynets | Y2 | M20 | Oct | 2025 | Done | On track
|  |  |  | *Manufactoring a miniature 3D Hall probe and a new sample holder | Dan Seal (UKRI) | O. Malyshev (UKRI) | Y2 | M18 | Aug | 2025 | In progress | On track
|  |  |  | *Study of sensitivity to trapped magnetic field | Oleg Malyshev (UKRI) | D. Seal (UKRI) | Y2 | M20 | Oct | 2025 | Not started | On track
|  |  |  | *Sample measurement | Dan Seal (UKRI) | O. Malyshev, R. Valizadeh, C. Benjamin (UKRI) | Y3 | M28 | Jul | 2026 | Not started | On track
|  |  |  | * Close out | [6 empty] | In progress | On track
|  | WP3 | 3.3 RF Tunability |  | HZB
D | 3.1 | WP3 | 3.3 | Cavity tuning Report on implementation of cavity Q vs F tuning tool | Oliver Kugeler (HZB) |  | Y2 | M24 | Feb | 2026 | In progress | On track
|  |  |  | *Design of tuning mechanism | Oliver Kugeler (HZB) | Andre Frahm | Y1 | M12 | Feb | 2025 | Done | On track
|  |  |  | *Fabrication of tuning mechanism | Oliver Kugeler (HZB) | Andre Frahm | Y1 | M12 | Feb | 2025 | Done | On track
|  |  |  | *Report preparation | Oliver Kugeler (HZB) |  | Y2 | M23 | Jan | 2026 | In progress | On track
|  |  |  | * Close out | [6 empty] | Not started | On track
M | 3.3 | WP3 | 3.3 | Report on mechanical strength test of SC coatings | T. Proslier (CEA) |  | Y3 | M30 | Aug | 2026 | In progress | Risk to mitigate | The task was set-up by Claire and transfer to other resposible is in progress
|  |  |  | *Design meachanical test samples | T. Proslier (CEA) | R. VallCorba Carbonell | Y1 | M10 | Dec | 2024 |  | On track
|  |  |  | *Produce samples in Cu | T. Proslier (CEA) | ? | Y2 | M19 | Sep | 2025 | Not started | Risk to mitigate | Thomas Proslier is taking care of this task
|  |  |  | *Surface treatments (EP) | C. Pira (INF) | E. Chyhyrynets, E. | Y2 | M20 | Oct | 2025 | Not started | On track
|  |  |  | *ALD coating | T. Proslier (CEA) | T. Proslier | Y2 | M22 | Dec | 2025 | Not started | On track
|  |  |  | *Nb3Sn coating with and without ALD layers | C. Pira (INFN) | D. Fonnesu, R. Valizadeh, C. Pira | Y3 | M24 | Feb | 2026 | Not started | On track
|  |  |  | *Mechanical tests at cryogenic temperature | T. Proslier (CEA) | ? | Y3 | M28 | Jul | 2026 | Not started | Risk to mitigate | Thomas Proslier is taking care of this task
|  |  |  | * Close out | [6 empty] | Not started | On track
|  | WP3 | 3.4 Adaptive Layers |  | CEA
M | 3.2 | WP3 | 3.4 | Developed ALD adaptive layers on Cu | T. Proslier (CEA) |  | Y2 | M24 | Feb | 2026 | In progress | On track | To be submitted. Document ready, Waiting last test from CERN
|  |  |  | *Insulating layers on Cu that can whistand 700°C in Vacuum. | T. Proslier (CEA) | F. Miserque, T. Proslier | Y2 | M13 | Mar | 2025 | Done | On track | Several candidates ALD layers show no cracks after annealing at 700°C for 2 hrs in vacuum. XPS reveal no Cu diffusion through ALD layers
|  |  |  | *Insulating layers on Cu that can whistand 700°C in vaccum and HPR. | T. Proslier (CEA) | F. Miserque, T. Proslier | Y2 | M13 | Mar | 2025 | Done | On track | The same ALD layers showed no peal off or structure and composition modifications after HPR.
|  |  |  | *Deposition of ALD layer in Cu cavity | T. Proslier (CEA) | T. Proslier | Y2 | M16 | Jun | 2025 | Done | On track | 2 Cu 1.3 GHz cavities from CERN coated and sent back to CERN
|  |  |  | *Nb deposition on ALD layer in Cu cavity | T. Proslier (CEA) | G. Rosaz | Y2 | M16 | Jun | 2025 | Done | On track | 2 Cu 1.3 GHz cavities coated at CERN with Nb films.
|  |  |  | *RF test on Cu cavities | T. Proslier (CEA) | G. Rosaz | Y2 | M19 | Nov | 2025 | In progress | On track | HPR tests successfull (no Nb film delamination). Sucessfull mitigation of thermo-electric currents even in high thermal gradient cool down.
|  |  |  | * Close out | [6 empty] | In progress | On track
D | 3.3 | WP3 | 3.4 | Adapt. Layer Report on QPR study of Nb3Sn on Cu & adaptive layers | T. Proslier (CEA) |  | Y4 | M38 | Apr | 2027
|  |  |  | *Test Nb3Sn deposition on ALD adapative layers | T. Proslier (CEA) | D. Fonnesu, T. Proslier, G. Rosaz | Y2 | M22 | Dec | 2025 | In progress | On track | EP Cu samples received from INFN and coated by ALD. Samples sent back to INFN: deposition of Nb3Sn on top of ALD layers (test in progress)
|  |  |  | *Test superconducting properties and chemical composition of Nb3Sn-ALD-Cu | T. Proslier (CEA) | T. Proslier, I. Curci and F. Miserque, G. Rosaz | Y3 | M28 | Jul | 2026 | In progress | On track | Tunneling spectroscopy and XPS measurements of Nb3Sn on ALD layer on Cu.
|  |  |  | *Test HPR of Nb3Sn-ALD-Cu multilayers | T. Proslier (CEA) | T. Proslier | Y3 | M28 | Jul | 2026 | Not started | On track | HPR tests will be done at CEA.
|  |  |  | *Design and order QPR coating chamber | T. Proslier (CEA) | D. Longuevergne. | Y1 | M12 | Feb | 2025 | Done |  | Parts received and to be tested in ALD system.
|  |  |  | *Deposition ALD layers on Cu QPR | T. Proslier (CEA) | T. Proslier, Y. Kalboussi | Y3 | M32 | Oct | 2026 | Not started | On track | Depends on the results obtained on coupons
|  |  |  | *Nb3Sn deposition on QPR. | R Valizadeh (UKRI) | D. Fonnesu, R. Valizadeh, C. Pira | Y3 | M35 | Jan | 2027 | In progress | On track | copper QPR is received and a facility for depositing Nb as a first layer is being constructed
|  |  |  | *test QPR | O. Kugeler (HZB) | O. Kugeler, S. Keckert | Y4 | M37 | Mar | 2027 | Not started | On track
|  |  |  | * Close out | [6 empty] | Not started | On track
|  | WP3 | 3.5 Working Cavity @4.2K |  | UKRI
M | 3.4 | WP3 | 3.5 | M3.4 Characterization of Nb3Sn reference cavity | Reza Valizadeh (UKRI) |  | Y3 | M34 | Dec | 2026 | In progress | On track
|  |  |  | *Design of cavity deposition facility for Nb3Sn on copper | Reza Valizadeh (UKRI) | R. Valizadeh, C. Benjamim | Y2 | M15 | May | 2025 | Done | On track | A facility is designed and all parts have been order and some has been received (part of IFAST project)
|  |  |  | * Calibration magnetron and cavity heating assembly | R. Valizadeh | R.Valizadeh, Stephan Simon | Y2 | M16 | Jun | 2025 | Done | On track | Durability of the newly designed planar magnetron and heater assembly been tested and calibrated (part of IFAST project)
|  |  |  | *First Nb cavity deposition with Nb3Sn (IFAST) | R. Valizadeh | R. Valizadeh, C. Benjamin | Y2 | M18 | Aug | 2025 | Done | On track | Nb cavity coated with Nb3Sn film on September 2025
|  |  |  | *standard RF test | Oliver Kugeler (HZB) |  | Y2 | M19 | Oct | 2025 | In progress | On track | RF test of 1.3 GHz cavity with standard set-up by end of October
|  |  |  | *Tunability and Flux trappping test | Oliver Kugeler (HZB) |  | Y3 | M24 | Feb | 2026 | Not started | On track
|  |  |  | * Close out | [6 empty] | Not started | On track
D | 3.4 | WP3 | 3.5 | 4.5-K Cavity Report on 4.5-K Cavity performance & tunability tests | Cristian Pira (INFN) |  | Y4 | M46 | Dec | 2027
|  |  |  | *Upgrade of Coating deposition system at LNL | C. Pira (INFN) | D. Fonnesu, D. Ford, M. Lazzari, E. Chyhyrynets | Y3 | M30 | Sep | 2026 | in progress | On track | Rectangular Magnetron testing in progress
|  |  |  | *Upgrade of Coating deposition system at STFC | Reza Valizadeh (UKRI) | R. Valizadeh, C. Benjamin | Y3 | M30 | Sep | 2026 | in progress | On track
|  |  |  | *Deposition of ISAS Nb3Sn on Cu 1.3 GHz at INFN | C. Pira (INFN) | D. Fonnesu, D. Ford, M. Lazzari, E. Chyhyrynets | Y4 | M40 | Jun | 2027 | Not started | On track
|  |  |  | *Deposition of ISAS Nb3Sn on Cu 1.3 GHz at STFC | Reza Valizadeh (UKRI) | R. Valizadeh, C. Benjamin | Y4 | M40 | Jun | 2027 | Not started | On track
|  |  |  | *RF test + Tunability and Flux trappping test INFN cavity | Oliver Kugeler (HZB) |  | Y4 | M44 | Oct | 2027 | Not started | On track
|  |  |  | *RF test + Tunability and Flux trappping test STFC cavity | Oliver Kugeler (HZB) |  | Y4 | M44 | Oct | 2027 | Not started | On track
|  |  |  | * Close out | [6 empty] | Not started | On track
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F46: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on O47: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on N49: adele de-valera: on EU continuous reporting portal by project management
Note on F51: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on N51: adele de-valera: on EU continuous reporting portal by project management
Note on F60: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F66: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F82: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F91: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F99: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F107: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management