iSAS weekly meeting

26th May 2025

Present: Jorgen D'Hondt, Achille Stocchi, Adèle de Valera

Notes:

WP9.5 Verifiable metric for energy-saving performances

Checked

* Caveat (is there a risk that we cannot deliver what we promise in the document, and should we mention this in the document?) formulated in revision mode and sent back by Achille to Maud for ok & to WP conveners to keep them in the loop on final version

* Adèle updates EU portal & adds final version to repository for future reference

WP4

WP4 work plan template illustration to be completed & sent to other WPs along with WPX work plan template

* Adèle sends a reminder to the WP4 convener to complete the last template version post Coordination panel

WP4 deputy at INFN Milano does not respond, and 100k for post-doc remains unused (INFN responsible for task 4.2 HOM coupler design)

* Achille sends a reminder to Dario Giove

* Achille asks Cristian Pira in Coordination panel and INFN to see if post-doc could be under the responsibility of CNRS (as responsible for WP4)

WP7

Thematic reviews process to be shared in next Steering committee: Oscar informed & proposed July 10 at 3 pm for next IB

* Adèle asks if another timeslot option is possible, as it overlaps with a main conference, which might drain participation

WP8

* Ana Anselmo (HZB) contacted after no contact persons on 8.1 or 8.3 despite various reminders (following Ketel's advice)

* Thomas Berghoefer had proposed the iSAS consortium to integrate the network - should we join formally?

* Genera GA in Sept 4/5, 2025 proposed by Ketel - should I go?

Berlin 2026

* Adèle sends a reminder to Jens to propose 2 other sets of dates as agreed in Coordination panel

KIT

Survey for analysing the performance of the research infrastructures

* To be shared with iSAS consortium? Jorgen responds proposing to share contacts of main RI

Ca v3 & shared NDA

Julie absent all May, CA v3 not sent yet, update on NDA completion not sent yet

* Adèle sends a reminder to Julie again