## Slide 1
Project Progress Review (PPR) 2-2025
WP05
Présenté par:
Mohammed Ben Abdillah
22 Mai 2025

## Slide 2
Task 5.1 : BPM; Leader : M. Ben Abdillah
Accomplished:
Injector BPMs:
Mechanical study
RF Front end electronics discussed
FW needs discussed
Libera Brilliance module for Gun BPMs
LINAC BPMs:
Path length Monitoring under development
Planned for next 2 months:
Injector BPMs:
Mechanical drawing with steerers
Front end and FW qualification
SW needs to be discussed
Gun BPM cabling specs
LINAC BPMs:
FW and SW to be discussed
Existing BPMs
Booster
Buncher
BPMs
BPM
Merger
Diagnostics Line
BPMs
BPMs
BPMs
LINAC
Beam Dump
Line

## Slide 3
Task 5.2 : BCM; Leaders : M. Ben Abdillah (Temporary)
Accomplished:
Gun Faraday cup
Confirmation of realization and delivery schedule
ACCTs:
Task Force temporarily reallocated
Discussion on localization on the injector
Planned for next 2 months:
ACCT:
Discussion on localization on the injector
Discussion for a 1st version of specifications document
Design discussions with GANIL
Gun Faraday cup: Delivery expected early 09/25
Needs:
ACCT:
Beam Dynamics inputs
Magnets inputs
Task Force for electronics

## Slide 4
Task 5.3 : BLM; Leader : H. Guler
Accomplished:
Study proposal from Libera: operational
Planned for next 2 months:
Get better estimations for BLM location (injector)  BD studies
Estimate use of BLM in MPS and general interlock + see possibilities for causal search for losses.
Study of alternative solution to Libera
Needs:
Timing + C&C : post mortem implementation

## Slide 5
Task 5.6 : Beam Longitudinal length; Leader : R. Roux
Accomplished:
Deflecting Cavity RF design
Planned for next 2 months:
Mechanical design (8 weeks internship starting June 10th)
Discussion on View screen
Frequency= 3GHz, pulsed mode
If L = 1 m => E0 = 5,38 MV/m => P = 9,33 kW
If L = 2 m => E0 = 2,69 MV/m => P = 2,3 kW

## Slide 6
Tasks 5.5 & 5.8 : Energy & View screens; Leader : S.Wallon
Accomplished:
Energy meas
script for energy spread simulations to be migrated to Bmad simulation
Interns:
  1 currently on energy simulations (10 w)
  1 on dipole magnet (June & July 25)
RI gun’s screen : Actuator tested
Planned for next 2 months:
RI gun’s screen :
camera tests & in-situ reintegration
Pneumatic distribution to be tested
Bmad exe to simulate energy meas in order to assess energy spread resolution w.r.t operation schemes
Inputs from dipole task: Field map + specifications
Needs:
Task force for:
mechanical design
Inputs from : BD, magnets, …
Example: energy spread resolution 10-3 eventually upgraded by a factor of 2

## Slide 7: Summary
Points of vigilance:
  Inputs: Beam Dynamics, Magnets, Mechanics
  Task forces: mechanical, electronics, C&C
  BLM: Back up solution to be studied
Gun planning: seems ok, focus on C&C and cabling
Injector planning: to be consolidated
  BPM front end and FW to be consolidated
  SW and C&C to be addressed. Backup solutions to be completed.
PERLE 1 turn planning: to be consolidated
  BPMs progress pace seems OK
  BLMs scope to be updated