## Slide 1
Project Progress Review (PPR) 3-2025
WP- 08: RF systems
Présenté par C. JOLY pour le compte de l’équipe

## Slide 2: Etat d’Avancement
Project definition (RH, WBS, Budget) in progress : P2I call for proposals, IP2I collaboration and Electronic department discussion for the future recruitments.
TDR with a global definition of the RF systems in progress (DMO, Timing, FTS, RF FPC interfaces with LLRF, C&C EPICS, SSA).
Cavity qualification facility upgrade  1 kW amplifier SAT report in progress with additional tests
with the RF components added for the SRF cavity qualification test bench.
MO & Timing : Use of IDROGEN board solution associated to one mezzanine board (FMC REFGEN) and a µRTM board locally providing the timings signal.
 First REFGEN prototype manufactured , firmware development by Engineering pole in progress
 two IDROGEN v3 manufactured for our new LLRF test Bench. Tests and configuration in progress
by TimeD team

## Slide 3: Etat d’Avancement
 integration to the TimeD team of the PhD student Nawal Belouchrani : Software dev. Phase noise
and jitter calculations, Phase noise measurements versus configs,… linked to our objectives for PERLE.

## Slide 4: Etat d’Avancement
FTS (Frequency Tuning System) C&C board
 First design in µRTM format close to be finished  review to plan
 IP2I Electronic department is ok to realize the layout ( to be confirmed)

## Slide 5: Etat d’Avancement
RF powers Amplifiers : 4 IOT + 5 SSA strategy seems the best.
- First version of the SSA requirements
 waiting a first quotation from JEMA from a prototype upgradable until 60kW
implying 3 racks ( 2 racks for 30kW)
 TrumpF (standby)
- Project of collaboration with THALES and CERN for the IOT prototype
 I-Demo program not approved

## Slide 6: Etat d’Avancement
LLRF system.
- RF front-end prototype
 Realized and Driver modification in progress by IOXOS.
 Evaluation of a use of the two versions (v1 and V2) with BPM in progress

## Slide 7: Planning et Principaux Jalons du WP-8 : RF systems
DC Gun @350 keV
2024
2025
2026
2027
2028
2029
2030
2031
Injector @ 7MeV
ERL 1-LOOP
DC gun
operation
Cryogenic
installed
Injector installed
Cryomodule
tested
Cryomodule
Installed
First ERL
demonstration
Design
Procuirement / Construction / Installation
Commissioning
20 mA
2MW
TDR
PERLE 1-LOOP 89MeV
IGLOO ready
20 mA
DMO & Timing
Board proto
series
Frequency tuning system
series
Pw mod.series
& Board proto
Cavity Qualification facility upgrade
RF proc. & modification
RF power Amplifiers (5 x SSA)
(4 x IOT)
prototype
series
series
!
FeedBack system
Series proc.
Cavity Sim. and algorithms opt.
PhD student work
€
€€
€
€
€€€
€€€

## Slide 8: Points de vigilance
Disponibilité des ressources:
  Ing Conception, 1 T/AI CAO, routage , suivi de prod
  D. Charlet (~ mi 2026 ?)
  M. Taurigna (fin 2025)
Dépenses à prévoir ( à consolider) :
2025 ( budget alloué ?)
  6k€ pour développement des cartes proto (TIMGEN et C&C FTS)
  40k€ pour réaliser la série des modules de puissance FTS
  30k€ pour réaliser la série des châssis d’interfaces RF
  ? Câbles
2026
  116k€ approvisionnements cartes IOXOS (8 + 2 spares)
  ? k€ Châssis MTCA
  ? Lignes RF
  ? Circulateurs and Load (minimum 4 but perhaps 8 )
  400k€ Amplificateurs SSA (power 10kW)  En attente de la version finale des besoins
2027
  1.2M€ Amplificateurs IOT (50kW)
  ? Upgrade Amplificateurs SSA ( power 20 kW to 50kW, bandwidth-dependent)
   En attente de la version finale des besoins
Il faudrait au moins de quoi faire les prototypes
et les racks associés ~ 16k€ minimum
Il faudrait essayer de lancer un prototype avec mise à niveau de puissance jusqu’à 50kW ( 10 mois min de délai)
( 12 mois min de délai)

## Slide 9: Highlights : Couplage cavité et enjeux
Couplages et facteur de qualité
Puissance incidente (ampli RF) necessaire : cas général
Puissance incidente (ampli RF) nécessaire : au « detuning » optimal
Couplage incident optimal pour une cavité

## Slide 10: Booster side
Paramètres | Cavité elliptique mono-cellule
Freq. [MHz] | 801,58
βopt | 1
Q0 | 1.1010
r/Q [Ω] | 109.25
Lacc [m] | 0.187
Qt | 4.1011
Paramètres cavité considérés
Configuration des réglages envisagés
Nombre de cavités | Type de réglage | Numéro de cavité | Réglages |  |  | Delta W (MeV) | Energie Totale en sortie du Booster (MeV)
 |  |  | Vc (MV/m) | Phis (°) | Eacc (MV/m) |  | 
4 | Basique | 1 | 1,532 | 0,000 | 8,194 | 1,532 | 7,00
 |  | 2 | 1,532 | 0,000 | 8,194 | 1,532 | 
 |  | 3 | 1,532 | 0,000 | 8,194 | 1,532 | 
 |  | 4 | 1,532 | 0,000 | 8,194 | 1,532 | 
 | Optimisé | 1 | 1,449 | 25,850 | 7,749 | 1,304 | 7,01
 |  | 2 | 1,633 | -19,008 | 8,734 | 1,544 | 
 |  | 3 | 1,533 | 1,296 | 8,196 | 1,532 | 
 |  | 4 | 1,778 | -9,116 | 9,511 | 1,756 | 
3 | Basique | 1 | 2,043 | 0,000 | 10,925 | 2,043 | 7,00
 |  | 2 | 2,043 | 0,000 | 10,925 | 2,043 | 
 |  | 3 | 2,043 | 0,000 | 10,925 | 2,043 | 
 | Optimisé | 1 | 1,979 | 33,026 | 10,582 | 1,659 | 6,91
 |  | 2 | 2,187 | -4,301 | 11,693 | 2,180 | 
 |  | 3 | 2,198 | -0,217 | 11,753 | 2,198 | 
Basique = accélération ‘on-crest’ et toutes les cavités ont la même tension accélératrice.
Optimisé = réglage après étude de dynamique faisceau (ref : C. Monnaghan + R. Roux)

## Slide 11: Booster side
Configuration de réglage envisagés
Basique = accélération ‘on-crest’ et toutes les cavités ont la même tension accélératrice.
Optimisé = réglage après étude de dynamique (ref : C. Monaghan + R. Roux)
Nombre de cavité | Type de réglage | numéro de cavité | Réglages |  |  | Qiopt/ cavité @ 20 mA | Qiopt booster @20 mA | Pinc (Qioptb) @ 20 mA | Pinc (Qioptb)@ 20 mA total | Pinc (Qioptb)@ 5 mA | Pinc (Qioptb)@ 5 mA total
 |  |  | Vc (MV/m) | Phis (°) | Eacc (MV/m) |  |  |  |  |  | 
4 | Basique | 1 | 1,532 | 0,000 | 8,194 | 7,01E+05 | 7,01E+05 | 30,64 | 122,56 | 11,97 | 47,88
 |  | 2 | 1,532 | 0,000 | 8,194 | 7,01E+05 |  | 30,64 |  | 11,97 | 
 |  | 3 | 1,532 | 0,000 | 8,194 | 7,01E+05 |  | 30,64 |  | 11,97 | 
 |  | 4 | 1,532 | 0,000 | 8,194 | 7,01E+05 |  | 30,64 |  | 11,97 | 
 | optimisé | 1 | 1,449 | 25,850 | 7,749 | 7,37E+05 | 7,65E+05 | 26,09 | 122,86 | 9,96 | 48,01
 |  | 2 | 1,633 | -19,008 | 8,734 | 7,90E+05 |  | 30,89 |  | 12,31 | 
 |  | 3 | 1,533 | 1,296 | 8,196 | 7,02E+05 |  | 30,71 |  | 11,38 | 
 |  | 4 | 1,778 | -9,116 | 9,511 | 8,24E+05 |  | 35,16 |  | 14,36 | 
3 | Basique | 1 | 2,043 | 0,000 | 10,925 | 9,35E+05 | 9,35E+05 | 40,86 | 122,59 | 15,96 | 47,89
 |  | 2 | 2,043 | 0,000 | 10,925 | 9,35E+05 |  | 40,86 |  | 15,96 | 
 |  | 3 | 2,043 | 0,000 | 10,925 | 9,35E+05 |  | 40,86 |  | 15,96 | 
 | optimisé | 1 | 1,979 | 33,026 | 10,582 | 1,08E+06 | 1,03E+06 | 33,21 | 120,81 | 13,39 | 47,20
 |  | 2 | 2,187 | -4,301 | 11,693 | 1,00E+06 |  | 43,63 |  | 16,83 | 
 |  | 3 | 2,198 | -0,217 | 11,753 | 1,36E+06 |  | 43,97 |  | 16,98 | 

## Slide 12: ERL side
Exemple d’un macro-pulse de 80 bunchs (~ 2 µs)
Courant perçu par une cavité mode ERL
« Beam loading » dans la cavité
Régime établi du mode de fonctionnement ERL  Courant perçu par la cavité = 0 mA

## Slide 13: ERL side
Paramètres cavité

## Slide 14: ERL side
Puissance RF et couplage
Bande passante

## Slide 15: Conclusion : Choix des couplages
Cavité booster
Couplage envisagé/préconisé : Qi = 7,6 105
Besoin RF mini par cavité :
  @ 5mA : 10 -> 15 kW
  @ 20 mA : 27 -> 36 kW
Cavité ERL
Couplage envisagé pour une bande passante de 100 Hz Qi = 8,0 106
Besoin RF mini par cavité : 26 kW
Finalisation du rapport en cours, valeurs à confirmer.