## Slide 1: Experience with recommissioning of the European XFEL after Long Installation and Maintenance Period
Mateusz Wiencek – on behalf of XFEL recommissioning team
TTC 26, 11.06.2026

## Slide 2: OUTLINE
  Eu - XFEL small reminder
  Long Installation and Maintenance Period 2025 (LIMP25)
  Eu-XFEL LINAC recommissioning:
    Expectations based on experience
    Commissioning strategy and timeline
    Radiation measurement in the tunnel
    Cavities tuning to resonance
    Coupler conditioning
    Cavities conditioning
    Status after recommissioning
  Summary

## Slide 3: European XFEL small reminder
97 x 1.3GHz Cryomodules, 776 SRF TESLA type cavities
Out of 776 installed cavities, 26 are detuned:
7 x based on initial AMTF test
9 x due to high FE
2 x initial commissioning
8 x to optimize Vector Sum
Tailored waveguide system
No radiation monitors in the tunnel dedicated to measure radiation from cavities. However we do have MARWIN – radiation measurement robot

## Slide 4: Eu-XFEL Energy status before LIMP
Predefined energy modes:
  8 GeV
  10.5 GeV
  11.5 GeV
  14 GeV
  16.1 GeV
  16.3 GeV
Chart: Nominal Setpoint for RF Station
| A2 | A3 | A4 | A5 | A6 | A7 | A8 | A9 | A10 | A11 | A12 | A13 | A14 | A15 | A16 | A17 | A18 | A19 | A20 | A21 | A22 | A23 | A24 | A25
 | 680 | 700 | 750 | 746 | 665 | 680 | 810 | 655 | 800 | 800 | 785 | 765 | 635 | 605 | 810 | 725 | 830 | 710 | 795 | 845 | 800 | 842 | 755 | 635
97 x 1.3GHz Cryomodules, 776 SRF TESLA type cavities

## Slide 5: Eu-XFEL Energy status before LIMP
Predefined energy modes:
  8 GeV
  10.5 GeV
  11.5 GeV
  14 GeV
  16.1 GeV
  16.3 GeV
During user run always one spare OFF crest station available
Chart: Nominal Setpoint for RF Station
| A2 | A3 | A4 | A5 | A6 | A7 | A8 | A9 | A10 | A11 | A12 | A13 | A14 | A15 | A16 | A17 | A18 | A19 | A20 | A21 | A22 | A23 | A24 | A25
 | 680 | 700 | 750 | 746 | 665 | 680 | 810 | 655 | 800 | 800 | 785 | 765 | 635 | 605 | 810 | 725 | 830 | 710 | 795 | 845 | 800 | 842 | 755 | 635
2.4 GeV at BC2
97 x 1.3GHz Cryomodules, 776 SRF TESLA type cavities

## Slide 6: Long Maintenance and Installation Period 2025
  In Eu-XFEL there is a necessity to test cryogenic safety valves regularly
  Before LIMP: Warming up the LINAC is needed to perform safety valves check
  After LIMP:
    Doubling safety valves
    One valve can be tested while the second one is in operation
      No warming – up is needed to perform this operation
      In – situ check
Most important modification: cryogenic safety valves

## Slide 7: Long Maintenance and Installation Period 2025
7 months of extensive effort
In addition, plenty of other upgrades were introduced:
Gun5 installation
SCU / S-PRESSO (XTD1, SASE2)
ASPECT (XTD2, SASE1 modification)
Streaker North (XTD4, passive streaker)
STERN (XS4 – XTD8)
Master oscillator upgrade
RF distribution update
RF hardware maintenance
Electrical safety checks
Preventive maintenance (fans, power supplies, filters, …)
Inventory check
Some numbers on cryogenic modifications:
  150 safety valves including piping system have been modified
  600 new flanges have been installed
  1500 welded connections with zero leaks
  In 2031: Internal check of safety valves
  In 2036: Check of safety valves by authority

## Slide 8: LIMP 2025
From the SRF cavities / cryomodules perspective
What we did:
Cavity detuning to safe positions
Warm – up entire LINAC
What we did not:
vent beam vacuum
vent coupler vacuum
vent cryomodules insulation vacuum

## Slide 9: LIMP 2025
From the SRF cavities / cryomodules perspective
What we did:
Cavity detuning to safe positions
Warm – up entire LINAC
What we did not:
vent beam vacuum
vent coupler vacuum
vent cryomodules insulation vacuum
100 kHz or 200 kHz from 1.3 GHz (depending on initial cavity frequency). Avoiding plastic deformation while saving lifetime of the stepping motor tuners. Done with automatic system

## Slide 10: LIMP 2025
From the SRF cavities / cryomodules perspective
What we did:
Cavity detuning to safe positions
Warm – up entire LINAC
What we did not:
vent beam vacuum
vent coupler vacuum
vent cryomodules insulation vacuum
Outgassing on cavities RF surface
100 kHz or 200 kHz from 1.3 GHz (depending on initial cavity frequency). Avoiding plastic deformation while saving lifetime of the stepping motor tuners. Done with automatic system

## Slide 11: LIMP 2025
From the SRF cavities / cryomodules perspective
What we did:
Cavity detuning to safe positions
Warm – up entire LINAC
What we did not:
vent beam vacuum
vent coupler vacuum
vent cryomodules insulation vacuum
Outgassing on cavities RF surface
Should secure good performance of the couplers and cavities.
100 kHz or 200 kHz from 1.3 GHz (depending on initial cavity frequency). Avoiding plastic deformation while saving lifetime of the stepping motor tuners. Done with automatic system

## Slide 12: General considerations or what did we expect?
Reaching nominal energy after initial commissioning took long
During initial commissioning of the Eu-XFEL, plenty of challenges with regards to achieve desired energy were spotted
Special Task Force was established to analyze the problem and push LINAC Energy to its maximum
In parallel with XFEL user operation we scheduled dedicated study time to achieve 17.5 GeV which was finally reached after 1.5 years
Nick Walker - TTC Meeting - UBC, Vancouver, 5.02.2019

## Slide 13: General considerations or what did we expect?
FLASH experience
FLASH, being a user facility, was the basis which can be seen also as prototype for European XFEL
  It was extensively used to develop technology
  Since the course of almost 30 years of operation it was cryo cycled several times
  Some of the cryomodules were added or exchanged during years of operation
  For FLASH 2020+ upgrade, 2 cryomodules were exchanged
    Those modules showed quite good performance, nevertheless they needed a long processing
    After each cryo cycle they need processing

## Slide 14: General considerations or what did we expect?
FLASH ACC2 and ACC3 conditioning
Both of the FLASH2020+ upgrade cryomodules required several weeks of processing in AMTF tests stand
For the initial commissioning it was decided to install additional radiation monitors for processing
Around one week of processing reduced field emission significantly
https://proceedings.jacow.org/srf2023/papers/mopmb082.pdf

## Slide 15: Goals for EuXFEL recommissioning
750 Cavities up and running
Before Warm - up
Preserve energy and amount of cavities in use

## Slide 16: Goals for EuXFEL recommissioning
750 Cavities up and running
Before Warm - up
750 Cavities up and running
After LIMP
Preserve energy and amount of cavities in use

## Slide 17: Goals for EuXFEL recommissioning
750 Cavities up and running
Before Warm - up
750 Cavities up and running
After LIMP
We assumed that 3 to 5 RF station will need long processing. We predicted that other will go rather smoothly – few hours per station.
Therefore we scheduled 2 weeks for processing.
Preserve energy and amount of cavities in use

## Slide 18: Conditioning strategies…
the safest…
Power rise one cavity at a time
Very safe approach
A lot of experience and statistics can be collected
Detailed radiation profile for each cavity can be obtained
Very long and unpredictable amount of time needed

## Slide 19: Conditioning strategies…
…the fastest…
Load machine configuration file and press START
In case everything goes smoothly takes very little amount of time
Not predictable behavior of the entire system
According to our experience high risk of spoiling cavities with radiation

## Slide 20: Conditioning strategies…
…the compromise
Power up RF station (32 cavities) carefully
Observe all signals
Ramp – up speed dependent on cavities behavior
Time needed could be predicted
Requires skilled operators for each RF station

## Slide 21: The recommissioning team
6 LLRF experts
  Treat cavities as black box which always behaves the same way
3 SRF cavities experts
  Treat cavities as a piece of Niobium, everything can happen there
9 people in total

## Slide 22: The recommissioning team
6 LLRF experts
  Treat cavities as black box which always behaves the same way
3 SRF cavities experts
  Treat cavities as a piece of Niobium, everything can happen there
9 people in total
One RF station as a training and explaining the algorithm for both groups

## Slide 23: The recommissioning team
6 LLRF experts
  Treat cavities as black box which always behaves the same way
3 SRF cavities experts
  Treat cavities as a piece of Niobium, everything can happen there
9 people in total
One RF station as a training and explaining the algorithm for both groups
One LLRF expert and one cavity expert make a conditioning of RF station together.

## Slide 24: The recommissioning team
6 LLRF experts
  Treat cavities as black box which always behaves the same way
3 SRF cavities experts
  Treat cavities as a piece of Niobium, everything can happen there
9 people in total
One RF station as a training and explaining the algorithm for both groups
One LLRF expert and one cavity expert make a conditioning of RF station together.
Each operator took RF station and make conditioning

## Slide 25: The recommissioning team
6 LLRF experts
  Treat cavities as black box which always behaves the same way
3 SRF cavities experts
  Treat cavities as a piece of Niobium, everything can happen there
9 people in total
One RF station as a training and explaining the algorithm for both groups
One LLRF expert and one cavity expert make a conditioning of RF station together.
Each operator took RF station and make conditioning
Coordinator is always available to address special cases or challenges

## Slide 26: Cavities conditioning algorithm
Flat top length:
200 us
400 us
650 us
Preparation
Radiation?
Vacuum events?
SP=600 MV
Flat-top = 100us
Increase SP by 10 MV
Wait until radiation goes down or stabilize
Nominal SP?
SP=Nominal – 50MV
Flat-top = x00us
Increase SP by 10 MV
Radiation?
Vacuum events?
Wait until radiation goes down or stabilize
Nominal SP?
Flat – top 650us?
YES
NO
YES
NO
YES
NO
YES
NO
RF STATION CONDITIONED
Nominal setpoints [MV]
A2:680
A3:700
A4:750
A5:746
A6:665
A7:680
A8:810
A9:655
A10:800
A11:800
A12:785
A13:765
A14:635
A15:605
A16:810
A17:725
A18:830
A19:710
A20:795
A21:845
A22:800
A23:842
A24:755
A25:635
YES
NO

## Slide 27: Radiation measurement for processing
For FLASH radiation studies, X-rays detectors were installed temporarily
  This option was not possible for entire 1.5 km long LINAC
On the other hand in order to perform cavities processing, some radiation monitoring is needed.
A real-time Gamma Dosimeter for XFEL using PIN-Diode-Sensors
Radiation?
Vacuum events?

## Slide 28: Radiation measurement for processing
A real-time Gamma Dosimeter for XFEL using PIN-Diode-Sensors
For FLASH radiation studies, X-rays detectors were installed temporarily
  This option was not possible for entire 1.5 km long LINAC
On the other hand in order to perform cavities processing, some radiation monitoring is needed.

## Slide 29: RadCon…
Developed by DESY (MSK Group)
Placed in the electronic rack underneath RF station, protected by radiation shielding
Can measure only Gamma radiation
Qualitative, not quantitative measurement
BUT WE ARE NOT BLIND
A real-time Gamma Dosimeter for XFEL using PIN-Diode-Sensors

## Slide 30: Cavities tuning to resonance after cool down
Using semi – automatic tool
Cool down to 2K took around 6 weeks
All cavities were tuned with semi – automatic tool developed for emergency detuning
  Nevertheless cavities resonant frequencies were observed in order to not exceed 1.3 GHz
2 operators for 2 RF stations
Takes one shift (8 hours)
One motor driver failure (16 cavities)  needs intervention in the tunnel

## Slide 31: Coupler conditioning
All cavities tuned  took time until late afternoon
We decided to leave entire machine over night with short pulse and low setpoint  check if everything is stable
After cryo cycle it is worth to check what happened with power couplers

## Slide 32: Cavities conditioning – most common case
RF Station: A4.L2 example
Conditioning took 1h
Final steps another 0,5 hour

## Slide 33: Cavities conditioning – worst case
RF Station: A12.L3

## Slide 34: Cavities conditioning – worst case
RF Station: A12.L3
Took 7 hours overall

## Slide 35: LINAC conditioning – final steps
Fine tuning with mechanical tuners and piezos
Set everything for the beam
  Feedback
  Feedforward correction
  Learning Feed forward
After few hours
  Qext correction
Get everything prepared for the beam

## Slide 36: Cavities conditioning – All RF station statistics
9 people
2 working shifts
In average 2 hours needed for RF station
2 days instead of planned 2 weeks!
Chart: 
| A2 | A3 | A4 | A5 | A6 | A7 | A8 | A9 | A10 | A11 | A12 | A13 | A14 | A15 | A16 | A17 | A18 | A19 | A20 | A21 | A22 | A23 | A24 | A25
Time [h] | 1 | 1 | 1.5 | 2.5 | 5.5 | 0.5 | 1 | 1.5 | 3 | 1 | 7 | 1.5 | 0.75 | 0.1 | 2 | 0.75 | 1.5 | 3 | 4 | 3 | 1.5 | 2 | 1.5 | 1

## Slide 37: Energy before and after LIMP
Before

## Slide 38: Energy before and after LIMP
After

## Slide 39: MARWIN SCAN
Before and after LIMP25

## Slide 40: Summary
After 8 years of successful operation, European XFEL underwent its first cryo cycle
  Main purpose of the LIMP was to make cryogenic modifications
  Warming up the machine as well as cooling down showed no major technical problems
  No vacuum leaks during cryogenic cycle
RF commissioning was planned taking into account experience from FLASH and Eu – XFEL
RF recommissioning of the entire LINAC took 2 days instead of planned 2 weeks.
We preserve Energy of the EuXFEL and not lose any cavity during the process
Recomissiong was a great sucess!

## Slide 41
Mateusz Wiencek
MSL
mateusz.wiencek@desy.de
Thank you
I will be happy to answer Your questions…