## Slide 1: Production and Quality Lessons from Large Cryomodule Projects at JLab
June 10th, 2026
Naeem Huque
Notes: Tip: Keep titles under 60 characters for readability
To change the photo: Right-click on photo and select change photo

## Slide 2: OUTLINE
JLab SRF History
Production Strategies
Copper Plating
Non-Conformances
Procurement Considerations
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 3: INTRODUCTION
PROCUREMENT
ASSEMBLY AND TESTING
QA/QC
Inventory
Non-Conformance
Inspection
Specification
Vendor Selection
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 4: HISTORY AT JLAB SRF
CEBAF C20
Early 1990s
CEBAF C50
2000s - date
CEBAF C100
2010s
CEBAF C75
2020s to date
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 5: HISTORY AT JLAB SRF
LCLS-II
2010s
LCLS-II-HE
2020s
SNS-PPU
2020s
SNS
Early 2000s
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 6: FUTURE AT JLAB SRF
2020s/2030s – EIC 591 MHZ
2020s/2030s – EIC 197/394 MHZ
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 7: PRODUCTION STRATEGIES

## Slide 8: PPU PRODUCTION STRATEGIES
PROCUREMENT
INVENTORY
INSPECTION
ASSEMBLY
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 9: PPU PRODUCTION STRATEGIES
PROCUREMENT
INVENTORY
INSPECTION
ASSEMBLY
VENDOR 1
VENDOR 2
PRE-ASSEMBLY
Vendor Sub-Assemblies
Thermal Shield, MLI, Spaceframe
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 10: PPU PRODUCTION STRATEGIES
PROCUREMENT
INVENTORY
INSPECTION
ASSEMBLY
Third-Party Inspections
3RD PARTY INSP.
Vacuum Vessel
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 11: PRODUCTION STRATEGIES
PROCUREMENT
INVENTORY
INSPECTION
ASSEMBLY
KIT GENERATION
Kit Generation
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 12: COPPER PLATING

## Slide 13: COPPER PLATING – LCLS-II BELLOWS
Chart: 
| Plating | Non Plating
 | 332 | 414
Chart: 
| Use-As-Is | Reject | Other
 | 511 | 144 | 35
Non-Conformance Source
Non-Conformance Disposition
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 14: COPPER PLATING – L2HE FPC
Contract required third-party qualification of bellows and plating
  Sectioning
  Fatigue test
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 15: COPPER PLATING – L2HE FPC
Initial samples failed qualification; bubbles in plating
Successful qualification after several iterations
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 16: COPPER PLATING – L2HE FPC
Before
After
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 17: SPEAKING OF BELLOWS…
Leak found in thermal shield bellows, after final CM assembly
Found after pressure test
Vendor had spares
Repair through access port
Repair was successful
Another unit had similar problem, caught earlier
Lesson: Consider spares of critical/fragile subcomponents
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 18: CAVITY PERFORMANCE

## Slide 19: CAVITY PERFORMANCE – C100
Chart: C100 Qo @ 16 MV/m
| C100-1-1 (010) | C100-1-2 (006) | C100-1-3 (012) | C100-1-4 (004) | C100-1-5 (007) | C100-1-6 (003) | C100-1-7 (005) | C100-1-8 (011) | C100-2-1 (013) | C100-2-2 (002) | C100-2-3 (018) | C100-2-4 (019) | C100-2-5 (015) | C100-2-6 (020) | C100-2-7 (001) | C100-2-8 (017) | C100-3-1 (029) | C100-3-2 (031) | C100-3-3 (021) | C100-3-4 (014) | C100-3-5 (022) | C100-3-6 (030) | C100-3-7 (025) | C100-3-8 (028) | C100-4-1 (037) | C100-4-2 (023) | C100-4-3 (048) | C100-4-4 (035) | C100-4-5 (036) | C100-4-6 (033) | C100-4-7 (038) | C100-4-8 (034) | C100-5-1 (042) | C100-5-2 (041) | C100-5-3 (040) | C100-5-4 (046) | C100-5-5 (045) | C100-5-6 (044) | C100-5-7 (032) | C100-5-8 (008) | C100-7-1 (060) | C100-7-2 (071) | C100-7-3 (061) | C100-7-4 (054) | C100-7-5 (057) | C100-7-6 (052) | C100-7-7 (058) | C100-7-8 (050)
VTA 16 | 11286020612.2 | 15677345356.3 | 10464911113.7 | 11173435102.3 | 12073128063.2 | 9134972470.11 | 12435571943.6 | 14055472264.9 | 9814367314.1 | 14344441563.1 | 9569673962.72 | 10701773620.7 | 12247250781.2 | 11247660683.5 | 8886702974.28 | 10874789998.5 | 10039198757.4 | 10429904351.5 | 10721865029.2 | 10163521115.6 | 13072342713.6 | 11194734120.4 | 8486869191.96 | 8800076299.09 | 13031202413.5 | 12159854315.7 | 11236673131.3 | 11394474100.4 | 12790590404 | 12164643583.7 | 13314863605.8 | 11209882664 | 15100000000 | 7778885574.99 | 12055713765.8 | 8701978899.28 | 11645614081.3 | 10979164987.1 | 10045924674.5 | 12061704855.2 | 9701842499.54 | 10484734090.4 | 11400709634.2 | 11688594526.3 | 10034284098.4 | 12273426390.8 | 9387841840.05 | 9747023317.85
Acceptance 16 | 9449120000 | 7787200000 | 9735200000 | 9036000000 | 10148960000 | 10102720000 | 10295200000 | 8792800000 | 11198400000 | 10521440000 | 10742800000 | 10135296000 | 10144000000 | 9304480000 | 8808512000 | 9022560000 | 9920800000 | 9544960000 | 9574720000 | 11375200000 | 9396800000 | 8727520000 | 9383200000 | 9536480000 | 11554400000 | 10628480000 | 11081600000 | 11212800000 | 12762560000 | 12609120000 | 14607200000 | 9567680000 | 6705200000 | 9500480000 | 6392000000 | 9482560000 | 10511840000 | 9887680000 | 3946400000 | 10795200000 | 10507200000 | 11725920000 | 9023680000 | 10197440000 | 10122400000 | 7937600000 | 12185600000
Commissioning 16 | 9664160000 | 9492000000 | 8409600000 | 8524160000 | 9333600000 | 9595840000 | 10150800000 | 9811200000 | 10005120000 | 11008800000 | 10022080000 | 11934400000 | 10667200000 | 10856800000 | 7222400000 | 9521600000 | 12299360000 | 8180000000 | 10609152000 | 9112000000 | 10813920000 | 9426720000 | 9956000000 | 8960160000 | 8324000000 | 7778720000 | 8257600000 | 9670400000 | 9282400000 | 10213600000 | 4358400000 | 4358400000 | 12299360000 | 794096000 | 9466522322.5806 | 1482274691.2955
Chart: Q0 @ 16 MV/m
| VTA | CMTF | Commissioning
 | 10742844521.916 | 9578343894.8218 | 8128089904.6279
Total Cavities: 80
Spares: 7.5%
Retest Rate: 85%
- 25%
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 20: CAVITY PERFORMANCE – LCLS-II
Chart: Gradient (MV/m)
| VTA | CMTF (Max) | CMTF (Usable)
 | 20.191 | 20.1917 | 18.8044
Chart: Q0 @ 16 MV/m
| VTA | CMTF
 | 31017493839.0391 | 28745244984.5533
- 7%
- 7%
Total Cavities (JLab): 168
Spares (JLab & FNAL): 26%
Cavity Retest Rate (JLab): 60%
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 21: CAVITY PERFORMANCE – LCLS-II-HE
Chart: Gradient (MV/m)
| VTA | LERF (Max) | LERF (Usable) | 27.3 | 24.0 | 23.1
 | 27.3187 | 24.0062 | 23.0896
- 13%
- 12%
Total Cavities (JLab & FNAL): 184
Spares (JLab & FNAL): 13%
Cavity Retest Rate (JLab): 90%
- 15%
Chart: Q0 @ 20.8 MV/m
| VTA | LERF
 | 31547500000 | 27527500000
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 22: CAVITY PERFORMANCE – SNS-PPU
P. Dhakal et. al. Performance of Oak Ridge National Laboratory spallation neutron source proton power upgrade cavities and cryomodule production, Phys. Rev. Accel. Beams 27, 102001
Total Cavities: 32
Spares: 0.0%
Retest Rate: 120%
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 23: NON-CONFORMANCES

## Slide 24: NCRs
Chart: LCLS-II
| Use As Is | Other
 | 1496 | 472
Chart: SNS-PPU
| Use As Is | Other
 | 529 | 145
Chart: CEBAF C50/C75
| Use As Is | Other
 | 937 | 263
Non-Conformance Report (NCR) Dispositions
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 25: PROCUREMENT LESSONS

## Slide 26: LONG-TERM PROCUREMENT LESSONS
Rectangular Waveguide
Vendor no longer makes the part; no alternative vendor
Re-plated and reused as needed
20 spares, no known source for more
Cryogenic Feedthrough
Developed for C20s in early 1990s
30% failure of later batch
Personnel change
Rotary Feedthru
Vendor no longer produces component
Parts have been repaired as needed; now reverse engineering
Notes: Guidelines: 6-8 bullets per slide; Use sentence fragments for bullets
To change the photo: Right-click on photo and select change photo

## Slide 27: SUMMARY
Notes: Before sharing your presentation, confirm:
Fonts are consistent
Images meet quality standards
Charts use template colors
Footer information is current
Spell check completed
Links are working
File size is optimized