iSAS weekly meeting

12th December 2025

Present: Achille Stocchi, Adèle de Valera

Absent: Jorgen D'Hondt

Notes:

CORDIS

* Adèle checks with Achille & Jorgen if they have feedback on project summary, then responds for the coordination

CA v4

No final version yet

* Achille sends a reminder to Julie

Follow-up project RF2.0 & iSAS

HE Main Work Programme 2026-2027) has just been published

https://rf20.eu/

Achille discussed with In2p3, CERN, TIARA copil, no competition in 2026

* Ketel asked what about Christophe Joly to take more responsibilities, like WP convener?

* Giovanni de Carne asks the opinion & support of Ulrich Husemann, former professor at KIT, who recently became Director of Particle Physics as DESY

https://www.linkedin.com/in/ulrich-husemann-ba454aa/

Concept paper

- We finalize this document and we send it around to our project partners. As suggested by Jorgen, we should focus to get the attention of CERN and DESY from the physics side.

- In the while, I will contact the Helmholtz contact in the EC, to ask him support and feedback

- If all the lights are green, I would suggest to have a working meeting in January, where we can begin the structure of the proposal

* Achille sends concept paper completed w/ track changes to Jorgen for his comments, then sends again to RF2.0 Coordinator & Steering committee

WP4

Convener ok w/ mid-Dec & sent LASA's presentation

Anna Francescon requires digital signature for post-doc hire, as well as AMD completed

* Adèle sends draft message to Achille for Anna

WP9

Policy briefing report: external relations representative could work on 1st draft from January - ok

Steering committee

Dec 16

To prepare

* PPT to share beforehand

* Presentation by Giovani 30': Adèle sends invitation details to join the meeting

* Timing extended by 30' + 10’ discussion afterward, and WP presentations shortened to 5’ each & focused on Feb milestones

Berlin 2026

The organising team has the contacts to invite Advisory board members & invited speaker directly

The Indico page is being completed

Axel has to check for the spending limits:

regarding the limits for the meals I need to check, whether the boundaries are meant for the whole workshop or separately for the lunches and the dinner.

So far, we were told a maximum of 40-60 Euros per person, which I have assumed for the dinner only. But let me confirm this please.

This includes the rent for the location etc. Above 50 or 60 (I need to confirm the exact number) we need an extra approval by our directors, I assume.

I will come back with more information. In the meantime, we are also already contacting first places to block them for those dates and receive an offer.

* Adèle sends a reminder to get update

Communication

News article proposed for internal com' & could be published on iSAS website as well

Agate-Tempo

Achille valideur projet iSAS pour W. Kaabi, P. Duchesne & N. Gandolfo?

* Adèle asks Guillaume O who does validate for iSAS