## Slide 1: WP5: Integration into a new LINAC Cryomodule Zoom meeting, Dec 03, 2025 WP Leader: Nuno Elias (ESS) WP Deputy: Vittorio Parma (CERN)
All information contained in this presentation and any accompanying documents is for iSAS project only, and must be treated as strictly confidential.
Any dissemination, distribution or other use of this information without the consent of its owner is prohibited.
Funded by the European Union. Views and opinions expressed are however those of the authors only and do not necessarily reflect those of the European Union or the European Commission. Neither the European Union nor the granting authority can be held responsible for them.

## Slide 2
WP5: Integration into a new LINAC Cryomodule
ESS | CNRS | CERN | EPFL
Convener: Nuno Elias (ESS)
Main contacts with other partners: G. Olry (CNRS), V. Parma. CERN); M. Siedel (EPFL)
The design of any LINAC cryomodule is optimised to meet the specific research objectives of the accelerator facility, while addressing common challenges such as high-power electric fields, ultra-low temperatures, ultra-high vacuum, precise alignment, etc.
WP5's main goal is to tackle the common engineering challenges of integrating iSAS technologies into a parametric design of a new cryomodule, building on developments made with ESS cryomodules whilst benchmarking against other facilities.
In addition, to unlock the full energy-saving capability of this cryomodule, the objective of WP5 is to also address the challenging beam dynamics requirements when operating the new cryomodule in Energy Recovery Linacs with recirculating beams.

## Slide 3
WP5: Integration into a new LINAC Cryomodule
ESS | CNRS | CERN | EPFL
Convener: Nuno Elias (ESS)
Main contacts with other partners: G. Olry (CNRS), V. Parma. CERN); M. Siedel (EPFL)
Task 5.1: Coordination on cryomodule design activities– M1-M48
• General coordination by ESS as described above.
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities– M1-M36
• Compile the lesson learned from the ESS CM testing activities, technical commissioning, and initial operation.
• Benchmarking with projects in the implementation phase (worldwide).
• Develop a roadmap to develop a new, sustainable CM design.
Task 5.3: Sustainable criteria for LINAC cryomodule design– M24-M48
• Integrate findings from the other iSAS WPs into a generic CM design.
• Explore the sustainability criteria for the design.
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48
• Simulate the beam dynamics of ERL-based accelerators when the energy efficient CM is included.
• Study the lattice design to optimize the beam and energy saving performances.

## Slide 4
WP5: Integration into a new LINAC Cryomodule
ESS | CNRS | CERN | EPFL
Work Plan

## Slide 5
WP5 – Coordination: status/evolution of Task 5.1
Task 5.1: Coordination on cryomodule design activities– M1-M48
• General coordination by ESS as described above.
Milestone 5.1 : In-person WP kick-off meeting at ESS (Due date: M3 or Jun-2024)
Milestone 5.1 : Impact Risk analysis (Due date: M24 or Feb-2026
Deliverable 5.1 : Compilation of ESS CM lessons learned & benchmarks (Due date: M24 or Feb-2026)
Deliverable 5.2 : Roadmap for the CM design (Due date: M36 or Feb-2027)
Deliverable 5.3 : Parametric design for a sustainable CM with iSAS tech. (Due date: M46 or Dec-2027)
Deliverable 5.4 : Report on beam dynamics study for ERL with iSAS CM (Due date: M43 or Sep-2027)
Y0
Y1
Y2
Y3
Y4
M5.1
D5.1
D5.2
D5.3
D5.4
Task 5.1
Task 5.2
Task 5.3
Task 5.4
Task 5.1
Task 5.2
Task 5.3
Task 5.4
Mar
2024
Mar
2025
Mar
2026
Mar
2027
Feb
2028
M
D
D
D
D
D
D
D
D
D
D
M
D
D

## Slide 6
WP5 – Coordination: status/evolution of Task 5.1
Past developments
  Regular WP5 meetings + dedicated meetings task specific
    Mar24; Apr24; Jul24; Sep24; Jan25 + (12-19)Nov24_T5.2 ; (7)Mar25_T5.4; Jul25; Sep25, Oct25
  Milestone 5.1 : “In-person WP kick-off meeting at ESS” : Completed
  Recruitment PhD student (EPFL): Started: (Apr-2024) ; Completed (Oct-2024)
Current developments
  Ongoing Recruitment of junior engineer/ scientist (ESS) : Start: (Mar-25) ;
    Assignment of 2 years to be supporting activities related to WP5 and WP6
    Possible extension to be considered, to cover up to the end of project
    More than 40 candidates, 2selected for interviews.1st interview done (18-Aug and Aug-21)
    Final site interview 04-Sep-2025, selection Complete (Oct-25). Started 20-Oct-2025
Task 5.1: Coordination on cryomodule design activities– M1-M48
• General coordination by ESS as described above.

## Slide 7
WP5 – Experience/Benchmark CMs: status of Task 5.2
Past developments
  Discussions with relevant people: ESS CM lifecycle
  Gathering of relevant high-level information
  Preliminary table-of-contents for ESS CM lessons learned report
Current developments
  Developing of on the ‘ESS CM lessons learned’ report structure
  Alignment with CM ‘benchmarking template’
  New member in place, report used as a good tool for training
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Compile lesson learned from the ESS CM testing activities, technical commissioning, initial operation.
• Benchmarking with projects in the implementation phase (worldwide).
• Develop a roadmap to develop a new, sustainable CM design.
Deliverable 5.1 : Compilation of ESS CM lessons learned & benchmarks (Due date: M24 or Feb-2026)
Deliverable 5.2 : Roadmap for the CM design (Due date: M36 or Feb-2027)
• Compile lesson learned from the ESS CM testing activities, technical commissioning, initial operation.

## Slide 8
WP5 – Experience/Benchmark CMs: status of Task 5.2
Past developments
  Benchmarking parameters defined in the previous point (5.2.1)
  Benchmarking facilities: SNS, LHC, PIP-II, XFEL, LCLSII
  Definition of a questionnaire to receive a uniform response from the facilities
  Identification of the contact people in the different facilities
  Bibliographic search completed to propose a suggestion to every answer (reviewing can be easier than completing a blank questionnaire)
  Draft of the Questionnaire (pre-filled for all labs LHC and ESS)
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Benchmarking with projects in the implementation phase (worldwide).

## Slide 9
WP5 – Experience/Benchmark CMs: status of Task 5.2
Current developments
  Questionnaire finalization
  Contact list finalization
  First trial with LHC and ESS to get a feedback on the proposed questions
  Distribution of the questionnaire to the facilities (LHC, ESS, XFEL, SNS, LCLS-II, PIP-II)
Next Steps
  Finalization of meetings with some of the labs
  Follow-up meeting foreseen to discuss the answers
  Last part of the questionnaire focuses on lessons learned in the implementation or upgrade phases (PIP-II, XFEL CW upgrade - topics presented at TTC)
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Benchmarking with projects in the implementation phase (worldwide).
LHC: https://docs.google.com/forms/d/1wqlIFyOtbY00YnkxaNhExeMHGPyX6kKb7QaqQRTjmgM/edit
ESS: https://docs.google.com/forms/d/1td3yb0P23F1IB4Cw-KodH_P-IiHvcFamlbIpEZXD0KQ/edit
https://cernbox.cern.ch/s/3lQ9qoYJCciadwh

## Slide 10
WP5 – Experience/Benchmark CMs: status of Task 5.2
Current developments
Task 5.2: ESS cryomodules experience and benchmarking with other recent facilities – M1-M36
• Benchmarking with projects in the implementation phase (worldwide).
LHC: https://docs.google.com/forms/d/1wqlIFyOtbY00YnkxaNhExeMHGPyX6kKb7QaqQRTjmgM/edit
ESS: https://docs.google.com/forms/d/1td3yb0P23F1IB4Cw-KodH_P-IiHvcFamlbIpEZXD0KQ/edit

## Slide 11
WP5 – Design new CM: status/evolution of Task 5.3
Task 5.3: Sustainable criteria for LINAC cryomodule design – M24-M48
• Integrate findings from the other iSAS WPs into a generic CM design.
• Explore the sustainability criteria for the design.
Past developments
  This task is set to start on M24 (Mar26)
Current developments
  Attention to Sustainability criteria strategies applied to “Technology Areas”.
  Attention to implementation of performance criteria of technology areas and its integration.
  Breakdown of CM sub-systems (<- input from benchmarking)
  Discussions on KPI associated with each sub-system.
  Brainstorming of ideas initiated in Oct
  Plan in-person meeting at IJCLAB in 28-Jan-2026, to prepare for a smooth start, meeting focus mostly on task 5.3.prepare with parametric design (create a team)
Deliverable 5.3 : Parametric design for a sustainable CM with iSAS tech. (Due date: M48 or Feb-2028)

## Slide 12
Past developments:
  Meetings with PERLE collaboration, discussing details on the RF structure and HOM’s
  Evaluated and tested beam dynamics codes to enable ERL simulations
  Written code to enable flexible simulations and gathering of results
Current developments:
  General SRF cavity beam dynamic studies
    short-range and long-range wakefields (HOM’S)
    single- and multi-bunch instabilities
  General energy recovery efficiency studies after the degrading of beams throughout an ERL or ERL collider
  Evaluate ERL collider/light source applications for iSAS technology and perform studies on these applications
WP5 – Design new CM: status/evolution of Task 5.4
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48
• Simulate the beam dynamics of ERL-based accelerators when the energy efficient CM is included.
• Study the lattice design to optimize the beam and energy saving performances.

## Slide 13
Current developments:
  Benchmarking of RF-Track
  iSAS/PERLE SW SRF 5-cell cavity:
    1D axial electric field in -mode fieldmap
    Monopole and dipole cavity eigenmodes
    Cavity geometry
  Single-bunch through iSAS/PERLE cavity / lattice in RF-Track:
    Single bunch at transverse normalised emittance of 6 mm mrad and bunch energy of 7 MeV (PERLE injection)
    Short-range wakefields: beam loading, SBBU
    Search for instabilities: parameter scans for dependency of bunch charge, distribution, etc.
  Developing RF-Track/Xsuite Wrapper: PyERL
     Fast and customisable beam dynamics simulations
WP5 – Design new CM: status/evolution of Task 5.4
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48
Figure 5: Normalised axial electric field amplitude of the TM010-π mode at 801.58 MHz in the 5 half-wave cell bare-cavity for PERLE, with an energy gain of 20.5 MeV [C. Barbagallo, “Design and optimization of higher order mode couplers for the superconducting cavities of the PERLE energy recovery linac”].

## Slide 14
Simulate the beam dynamics of ERL-based accelerators when the energy efficient CM is included - FEB 2028
  Benchmarking of beam dynamics tracking codes - OCT 2025
  Development of Multi bunch and multi pass simulation - OCT 2025
  Single and multi-bunch instability analysis of ISAS typical cavity in PERLE lattice - AUG 2026
Energy recovery performances - FEB 2028
  Evaluation of ERL proposed applications - JUL 2027
  Energy recovery efficiency studies - JUL 2027
Final report - Sep 2027
Under completion
Timeline
Following Phase
WP5 – Design new CM: status/evolution of Task 5.4
Deliverable 5.4 : Report on beam dynamics study for ERL with iSAS CM (Due date: M43 or SEP-2027)
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48
Next Step

## Slide 15
Current developments
  Long range wake field model
  Beam loading model update
  Latice (new) needs input from Alex
  Multi-pass recirculation simulation (including collective effects)
  Instability studies ( multi bunch, iSAS cavity), participate on PERLE workshop
WP5 – Design new CM: status/evolution of Task 5.4
Task 5.4: Beam Dynamics for ERL-based accelerators with energy-efficient cryomodules – M1-M48

## Slide 16
WP5 – Title: points of attention
Points of attention: Setup meeting schedule in advance
This Meeting, Wednesday (Oct-01, 11AM)
Next Meeting, 1st week of the month Wednesday (Nov-05, 11AM)
Following meeting, 1st week of the month Wednesday (Dec-03, 11AM)

## Slide 17
WP5 – Title: financial status
Financial status :
any developments?
  New developments

## Slide 18
Thank you