## Slide 1
Project advancements & collaboration matters
PERLE Collaboration Board Meeting
Walid Kaabi, Maud Baylac & Achille Stocchi
June, 3rd 2026

## Slide 2: PERLE global planning
Design
Procurement/Construction/Installation
Commissioning
2031
5 MW
TDR
Civil engineering work
2025
2029
2030
2028
2027
2026
ERL 3-loop
First electrons April 2026
DC Gun @ 350 keV
Injector @ 7 MeV
Buncher installation
ERL 1-loop @ 89 Mev
20 mA
5 mA
Cryomodule installation
0.5 MW
5 mA
20 mA
2 MW
Booster installation
Booster
RF sources upgrade
Upgrade
Laser
We are here

## Slide 3
HV system
Photocathode Preparation Facility (PPF)
DC Photogun
Buncher
Booster
Merger
Diagnostics line
The injection line
"This work received government funding managed by the Agence Nationale de la Recheche (ANR) in the France 2030 framework - reference ANR-24-RRII-0001"

## Slide 4: PERLE e- Source:
Electron source Installation in the « Igloo »:
DC Gun & HV system
Photocathodes Production Facility (PPF)
DC Gun
Photocathode Laser room
Laser system
"This work received government funding managed by the Agence Nationale de la Recheche (ANR) in the France 2030 framework - reference ANR-24-RRII-0001"

## Slide 5: Design of the buncher cavity:
Specifications :
Frequency = 801 MHz
Maximum length = 200 mm
Targeted temperature = 30°C
Power dissipated = 1kW
Material : OFHC
Beam axes flange : CF50
Antenna port : CF 16
Plunger port : CF 40
Vacuum port : CF63
RF power coupler port : CF63
Courtesy to Samuel Marchal

## Slide 6: Design of the buncher cavity:
Cooling scheme optimization
Thermal & mechanical studies
RF studies & geometry optimization
W/2
Lcav/2
g/2
Mechanical drawings folder preparation
The call for tender was lunched end of May

## Slide 7: The booster cryomodule:
Booster :
4 mono-cell cavities cooled at 2 K
Length ≈ 3150 mm
Diameter : 1216 mm
Injection Energie: 7 MeV
Slides from Samuel Marchal

## Slide 8: Booster status:
Cryo. valve
Level gauge
Tie rod
Instrument. Ports
Alignment target support
Vacuum pump
Vacuum Vessel
Tuner trapdoor
Slides from Samuel Marchal

## Slide 9: Booster status:
Rupture disc
Valve
Magnetic shielding
Biphasic tube
Thermal shielding
He tank
Cavity
Wave guide
Lifting ring
Jumper
Exchanger
Flat bottom
Valve
Tuner
Power coupler
CF transition
support

## Slide 10: Booster cryogenic distribution:
Booster Cryogenic PID

## Slide 11: Booster single cell cavity and FPC
4 mono-cell cavities for booster:
  Order placed with Zanon
  Nb sheets sent and received by the manufacturer
  3D step file sent for approval by Zanon, some modifications to implement.
4 RF Fundamental Power Couplers (FPC):
  Same design as Linac cryomodule power couplers
  Set of technical drawings under completion at CERN
  Fabrication planned by CERN mid-June 2026
  RF conditioning will be done at CERN
4 double-wall tube for FPC:
  Same design as the ones of the Linac cryomodule
  Technical specification under review
  Call for tender under completion
4 tuners:
  Design adaptation terminated
  Order to be lunched before summer

## Slide 12: Booster vacuum vessel
The set of technical drawings for the vacuum vessel, flat bottoms and flanges is being finalized, same for the technical specifications.

## Slide 13: Planning of the booster:
 |  |  |  |  |  |  |  |  |  |  |  |  |  | TRAVAUX IGLOO |  |  |  |  |  |  |  |  |  |  |  | 
 |  | janv-26 | févr-26 | mars-26 | avr-26 | mai-26 | juin-26 | juil-26 | août-26 | sept-26 | oct-26 | nov-26 | déc-26 | janv-27 | févr-27 | mars-27 | avr-27 | mai-27 | juin-27 | juil-27 | août-27 | sept-27 | oct-27 | nov-27 | déc-27 | janv-28
1000 | Train Cavité |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Montage et test au 106 |  |  | 
1110 | Monocell |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1120 | Tank |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1130 | SAF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1160 | Blindage |  |  |  |  |  | Appel d’offres |  |  | Fab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1300 | Vanne a vide tout metal |  |  |  |  |  | Appel d’offres |  |  |  |  |  |  |  | Fab |  |  |  |  |  |  |  |  |  |  | 
1170 | Support tirants |  | Simulation |  |  |  | Dossier de Plan + CCTP |  |  | Appel d’offres |  |  |  | Fab |  |  |  |  |  |  |  |  |  |  |  | 
1200 | Soufflet IC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1300 | Transition CF |  | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6610 | Soufflet tube diph. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2000 | Ecran |  |  |  |  |  | Dossier de Plan + CCTP |  |  | Appel d’offres |  |  |  | Fab |  |  |  |  |  |  |  |  |  |  |  | 
2101 | Flanc gauche | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2102 | Flanc droit | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2200 | Fond | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2300 | Ecran Jumper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2400 | Ecran disque rupt. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2500 | Trappe | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3000 | Tirants |  | Simulation |  |  |  |  |  |  | Dossier de plan + CCTP |  |  |  | Marché |  |  |  | Fab |  |  |  |  |  |  |  | 
4000 | Enceinte |  |  |  | Dossier de Plan + CCTP |  | Appel d’offres |  |  |  | Fab |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4001 | Enceinte à vide |  | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4101 | Fond plat |  | Simulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4201 | Rallonge jumper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4202 | Coude jumper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4301 | Trappe accès SAF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4701 | Barre |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4711 | Barre verticale |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4900 | Ensemble Soupape |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4901 | Soupape |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5000 | Coupleur |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5000 | cloche coupleur |  |  |  |  |  | Appel d’offres |  | Fab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6000 | Cryo |  |  |  |  |  |  | Dossier de plan + CCTP |  |  |  | Appel d’offres |  |  |  | Fab |  |  |  |  |  |  |  |  |  | 
9000 | MLI |  |  |  |  |  |  |  |  | Dossier de plan + CCTP |  |  |  | Appel d’offres |  |  |  | Fab |  |  |  |  |  |  |  | 
8000 | Outillages et autres | Cycle de montage |  |  |  |  |  |  |  |  |  |  | Dossier de plan |  |  |  | Fab |  |  |  |  |  |  |  |  | 
Call for tender
Fabrication
Set of drawings & tech. specifications
Simulation
Assembly & test

## Slide 14: Status of the Linac cryomodule
Completed developments:
  New 5cell cavity design
  Mechanical integration of HOM and power couplers
  New cold and warm magnetic shields designs
  Adaptation of the ESS/MYRRHA cold tuning systems
  First cold Beam line absorber mechanical design
  New end-cap design including warm-to-cold transition
  New cryo lines for HOM couplers and beam line absorbers
  Definition of the P&ID (Piping and Instrumentation Diagram)
Current developments:
  Cold BLAs: characterization studies of several samples, thermal and RF calculations  cryo cooling
  Finalization of the cryogenic circuit design to include fast cooling possibility and BLAs cooling.
  Final configuration of the Instrumentation and cabling (temperature sensors, heaters)
Slides from Guillaume Olry

## Slide 15: Status of the Linac cryomodule
PERLE Cryomodule should look like this...

## Slide 16: Design status of Linac components
3D model of the BLA
HOM coupler
FPC
Cold tuning system
5-cell cavity
BLA
c/o G.Olivier
c/o P.Duchesne
c/o S.Blivet
c/o S.Blivet
c/o P.Duchesne

## Slide 17: Design status of Linac components
Warm + Cold magnetic shields integration:
Goal: residual B field < 1mG at the cavity surfaces (due to high sensitivity to trapped flux after mid-T bake)
 double the magnetic shielding, consisting of a 2 mm-thick layer of µ-metal and a 2 mm-thick layer of Cryophy around the cavities
c/o S.Blivet
c/o P.Duchesne
CST simulations

## Slide 18: Design status of Linac components
Cryogenic circuits:
No sub-cooling heat exchanger, nor JT valve into the cryomodule (main difference with ESS cryomodule)
New circuits: Cavities fast cooling down (red line #1),HOM couplers (green connexions to the bi-phase pipe), BLA cooling (ligth blue line #3)
Preliminary PID

## Slide 19: Status of Linac cryomodule components
Tasks accomplished:
  Niobium material : delivered and shipped to Zanon.
  5-cell cavities : call for tender #2 in 2025. Zanon awarded. Kick-off meeting 16 January 2026. Manufacturing file received for approval (technical drawings approved)...final approval soon then fabrication will start. First bare cavities expected in T1 2027.
  Magnetic shields: material (cryophy and µmetal) ordered. 6 months delay for 2mm thick µmetal...delivery in September 2026.
Still to come:
  HOM couplers (4 additional units w.r. to iSAS-WP4): call for tender in preparation. Publication before summer break.
  Double-wall tubes (for FPC): call for tender in preparation. Publication before summer break.
  Cold tuning systems: all quotations received (~30k€/CTS). Ordering phase is about to start.
  All metal gate valves: quotation received. Super expensive! Ongoing discussion with another supplier (VSE Vakuumtechnik)
  Magnetic shields: call for tender postponed to October 2026
  Cryomodule dished-ends: technical drawings in progress...

## Slide 20: Status of Linac cryomodule components
In addition:
As In-kind contribution of ESS to iSAS, the cryomodule of the linac will reuse ESS medium beta prototype components:
Vacuum vessel
Spaceframe
Thermal shield

## Slide 21: Organization of the beam dynamics review:
Goal:
Validation of the scientific choices related to lattice design and beam dynamics studies.
Inputs to be provided:
Final lattice design will be presented in details, including optical functions, optical elements parameters and the phasing strategy.
Current state of diagnostics studies, error studies and various beam dynamics studies will also be shown.
The reports will be sent to the reviewers at least a month in advance, along with a list of questions for the reviewers.
Practical Information:
The review will be held at IJCLab, by Mid/End June 2026, so it does not overlap with the IPAC conference.
A hybrid (zoom-presential) format can be envisaged, considering potential travel issues.
PERLE collaboration will afford all expenses (travel, meals, accomodation) of reviewers if they wish to attend in person.
A visit of the installation is planned.
Postponed to fall 2026, some studies still ongoing + need to make all the documents available in advance for the reviewer.

## Slide 22: Contributions PERLE à IPAC’26
14 abstracts submitted
11 contributors, including 3 PhDs
+
A contributed Talk by Alex Fomin

## Slide 23: Contributions PERLE à IPAC’26

## Slide 24: IN-KIND : News of the Collaboration:
Signature of the Cooperation Agreement between IJCLab/LPSC and Helmholtz Zentrum Berlin (HZB) for the transfer of the Cryo-plant and related equipment and collaboration on SRF activities of mutual interest and activities related to ERLs.
We started to discuss technical details for the Cryo-plant transfer (boxing, handing, transportation), responsibilities…
Cycle compressors
Helium pumping station for 2 K operation
Cold Box
C&C cabinets
Gas management panel

## Slide 25: IN-KIND : Status of Magnets- Discussions with Daresbury (I)
STFC-Darsebury: Mail exchange & Meeting during IPAC’26 at Deauville
  ALICE Injector Quad Type D
Parameter | Gap [mm] | L [mm] | G [T/m] | number | Cost [k€]/unit
PERLE | 76 | 50 | 6 | 7 (21 total) | 21
STFC (Alice) | 106 | 180 (phys.270) | 2.2 | 11 | transport
Parameter | Gap [mm] | L [mm] | G [T/m] | number | Cost [k€]/unit
PERLE | 76 | 50 |  | 7 (21 total) | 21
STFC (Alice) | 106 | 180 (phys.270) | 2.2 | 11 | transport
Big aperture  not suitable for the stacked turns
Small Gradient
Length is more suitable for ERL quads -> place in merger?
 Not a suitable option
Slides from Rasha Abukeshek

## Slide 26: IN-KIND : Status of Magnets- Discussions with Daresbury (II)
STFC-Darsebury: Mail exchange & Meeting during IPAC’26 at Deauville
  ALICE Injector dipole
Parameter | Gap [mm] | L [mm] | B [T] | number | Cost [k€]/unit
PERLE | 76 | 150 300 | 0.08 0.08 | 3(8 total) 2 | 40 42
STFC (Alice) | 71 | 310 | 0.08 | 3 | transport
Used to bend 8 MeV electrons by 30°
Twice the length of PERLE merger dipole reduce the current (field)
Well compatible option
To consider!
For the merger commission, one dipole can be used for the injector chicane
Must be replaced with a shorter magnet for the single-tour phase
Two options:
  2 in merger + 1 in mirror
  2 for the middle chicane (inj.+dump)

## Slide 27: IN-KIND : Status of Magnets- Discussions with Daresbury (III)
STFC-Darsebury: Mail exchange & Meeting during IPAC’26 at Deauville
  Alice injector dipole
    Mechanical integration from 2D drawings: Alice quads are not suitable, dipoles can fit with compact quadrupoles
Dipole integration specs
230 kg, assembled in 2 parts (measurements on the bench?)
No support or fiducials
No power supply: ±6A/12V
HT test for the coils needed
Air cooled
STEP file of a simplified 3D model is provided (to be implemented)
Opera 3D provided  Beam Dynamics simulation with field map

## Slide 28: IN-KIND : Status of Magnets- Discussions with Daresbury (IV)
STFC-Darsebury: Meeting during IPAC’26 at Deauville
  EMMA ring quad (new option suggested)
Parameter | Gap [mm] | L [mm] | G [T/m] | number | Cost [k€]/unit
PERLE | 76 | 50 | 6 | 7 (21 total) | 21
STFC (EMMA) | 72 | 88.86 (phys.55) | 6.68 (at 345A) | 20 | transport
Parameter | Gap [mm] | L [mm] | G [T/m] | number | Cost [k€]/unit
PERLE | 76 | 50 |  | 7 (21 total) | 21
STFC (EMMA) | 72 | 88.86 (phys.55) | 6.68 (at 345A) | 20 | transport
Physical length is compact (55mm)
Gradient is compatible
Water cooled, with high current/small voltage power supply as the number of turns is small
STEP file of 3D model is provided (to be implemented)

## Slide 29: IN-KIND : Status of Magnets- Other discussions
CERN: last exchange with Jérémie Bauche (Normal Conducting Magnets group) on May 12th 2026
An addendum to the PERLE Collaboration Agreement in preparation for the long-term loan of identified MDX dipoles for the Arc in phase 1 (PERLE single turn)  12 units.
SEF (French company): last exchange during IPAC26
Main specs and parameters of needed magnets were sent to the company (May 26) following a first discussion.
Agreement on the staged strategy for magnets order/fabrication/delivery  Focus on merger (3 dipoles, 7 quads).
SEF prefers small series production, starting with a prototype.
IJCLab will deliver the magnetic design, SEF will perform the mechanical design.

## Slide 30: NEW POSSIBLE FUNDINGS : Application for funding: SESAME program
  Submission of application for funding (SESAME program- Région Ile de France)  Project CRISP (CRyogénie et Injecteur Supraconducteur de PERLE) to Fund of the Inter-Connection Box (ICB): Total cost 550k€.
  After the first selection at the university level, CRISP is among the 8 projects selected for the final selection by Région Ile de France.

## Slide 31: NEW POSSIBLE FUNDINGS : Preparation for application of E2-SCALE:
Commun project between current European projects iSAS (coordinated by IJCLab) et RF 2.0 (coordinated by KIT- Germany) for the European call INFRA-TECH-2026-01-01.
Development of high efficiency Solid State Amplifier (SSA) @ 800 MHz- 60 kW, (collaboration with JEMA-France and CERN.
PERLE proposed as a facility for the integration, test and validation of the developed SSA, and the Cryomodule FCC developed in the project.
Innovate for Sustainable
Accelerating Systems
E2-SCALE:
Energy Efficient and Sustainable Collider, Accelerator, and Light-source research infrastructures for Europe

## Slide 32: Collaboration Agreement Extension

## Slide 33
Thank you for your attention!

## Slide 34: TDR- Structure and advancement:
Avancement
a < 25% : pas de plan ou de détails d’avancement
a=25% : plan reçu mais V0 en cours de rédaction
a= 50 % : V0 reçue en relecture ou en correction
a > 50 % : V1 corrigée
a ≥ 75% : version finale prête et /ou corrections mineures
a = 100 % : version finale intégrée au TDR. Relue & approuvée par Coord. chapitre et Coord. Board.
Les p’tites flèches indiquent les changements par rapport à la PPR précédente ou les points d’attention supplémentaires