## Slide 1
Project Progress Review (PPR) 1-2026
WP- 08: RF systems
Présenté par C. JOLY pour le compte de l’équipe
X. Lafay, S. Berthelot, J-F. Yaniche, O. Frossard, A. Martens, P. Gauron, F. Bouly, A. Buthod, C. Guérin with a strong interaction with the IDROGEN Team :
D. Charlet, A. Back, C. Esnault, C. Cheik-ali , C. Soulet, Gaetan Seuillot, Mathias Vecchio, Sid Ali Cherrati in collaboration with P-E. Potty , Michel Lours( LTE lab) , Cédric Viou (ORN lab).

## Slide 2: Etat d’Avancement TDR
TDR with a global definition of the RF systems in progress :
  - VIII. RF systems (indicatif: ~ 25 pages max)  revision version send end of March
    A. Introduction
    B. Requirements
    C. Distributed Master Oscillator
    D. Timing system
    E. Frequency Tuning System
    F. RF power system
    LLRF system
    And a chapiter on MPS :  in progress in collaboration with Maud, Aurore and Fred
  - IX. Machine protection System
      A. Introduction
      B. Requirements
      C. MPS architecture and solutions

## Slide 3: Etat d’Avancement : TIMING with WR synchronisation
Cavity qualification facility upgrade  1 kW amplifier SAT : tests realized and SSA out of order. Big problem for transistor procurement by the SSA manufacturer RPFA. NXP stop RF market but hopefull transistors found at a USA broker. Need to explain the breakdown  SSA delivery in September.
             PLL tested and validated (S. Berthelot, J-F. Yaniche, C. Joly). (Power supplies board will be upgraded for allowing an operation until 2GHz by J-F Yaniche)
MO & Timing :  New Electronic design in progress more simple and new functions. VHDL implantation into the IDROGEN Board validated with 2.5ns of resolution step.
(X. Lafay & C. Joly)
Layout ? See with IP2I Lyon

## Slide 4: Etat d’Avancement : Distributed Master Oscillator
 REFGEN prototype manufactured , firmware developed by Engineering pole. Firsts tests realized with REFGEN + IDROGEN. Improvements in progress with a new PLL allowing to generate RF signals until 3.2GHz and probably a new low noise amplifier per channel new version planned for the series : Tests show T° variation impact on the REFGEN performance : decision to realize a REFGEN version with the µRTM form factor instead of the FMC form factor (too small to allow a encapsulation of the PLL for regulating the T°).
 two IDROGEN v3 manufactured for our new LLRF test Bench. One is configured into master and
Another in Slave. A measurement campaign has been realized showing for the moment the difficulties to achieve a jitter@100MHz in the offset range [1Hz to 1MHz] inferior to 1ps with some problems of reliability. To do the same measurements with the best optimization of the IDROGEN Master and slave boards but for the moment, it is sure that it is not enough then in standby waiting new improvements.
N. Belouchrani, D. Charlet, A. Back, C. CHEIK-Ali, C. joly

## Slide 5: Etat d’Avancement : Frequency Tuning System (FTS)
FTS C&C board
 The CAD is finished at IP2I Lyon (A. Buthod) , Gerbers files and Bill of material update in progress for a realization by Würth Elektronik.
FTS Power module prototype for Piezo actuators
 Power module PCB wiring of the two boards and water cooling exchanger in progress (J-F. Yaniche, S. Berthelot, G. Olivier and IJCLab mechanics workshop)

## Slide 6: Etat d’Avancement : LLRF system
LLRF
 4 RF front-end RDC1470 v2 received.
Configuration is complicated : a new driver compilation has been realized thanks to P. Gauron but we discovered that this only partially updated the features preventing the use of the EPICS tools already in operation to test the electronic boards. The situation is now critical because we need to validate the new RF front-end at 801.58MHz associated to the IFC1420. It is the heart of the system
This task needs to be made a priority with
An increase the availability of P. Gauron on PERLE
To be discuss with Phillipe and Vincent, absent
this week.
In parallel, try to use the driver alone (without EPICS)
trying to bypass the board configuration in EPICS.

## Slide 7: Etat d’Avancement : RF Power systems
RF powers Amplifiers
 a prototype of RF Power solid state Amplifier :
  Kick off meeting realized in January with a delivery planned end of November.
  CDR meeting reported with a pre meeting planned 1st July
   Delivery panned in November should be delayed in the first quarter of 2027
(M. Adnane, S. Berthelot & C. Joly)
RF powers Amplifiers implantation in the IGLOO
 Booster
  RF circuits and RFPAs implantation upgrade and First version of the PID
  (E. Bourdelas, S. Brault, S. Berthelot, C. Joly)
  Quotation asked for a first version of bill of material to manufacturer EXIR and the representative of Microwave Techniques (Mega Industries)
  Exir quotation ~160k€
 ERL Linac
  RF circuits implantation upgrade in progress

## Slide 8: Planning et Principaux Jalons du WP-8 : RF systems
DC Gun @350 keV
2024
2025
2026
2027
2028
2029
2030
2031
Injector @ 7MeV
ERL 1-LOOP
DC gun
operation
Cryogenic
installed
Cryomodule
installation
First ERL
demonstration
0.5MW
Design
Procuirement / Construction / Installation
Commissioning
20 mA
2MW
TDR
PERLE 1-LOOP 89MeV
IGLOO ready
20 mA
DMO & Timing
Board proto
series
Frequency tuning system
series
Pw mod proto
& Board proto
Cavity Qualification facility upgrade
RF proc. & modification
RF power Amplifiers (9 x SSA)
series
series
FeedBack system
Series proc.
Cavity Sim. and algorithms opt.
PhD student work
€
€€
€
€
€€€
SSA prototype
8.8kW ordered
First electrons
5 mA
Buncher installation
Booster installation
5 mA
Booster
RF sources upgrade

## Slide 9: Points de vigilance
Disponibilité des ressources:
  Ing Conception  C. Joly, 1 T/AI CAO, routage  IP2I Lyon , suivi de prod – discussion pour routage 2ème carte
  D. Charlet (~ mi 2027)
Dépenses à prévoir ( à consolider) :
2025 ( budget demandé en en grande partie à reporter sur 2026 et 2027)
  6k€ pour développement des cartes proto (TIMGEN et C&C FTS)
  40k€ pour réaliser la série des modules de puissance FTS
  30k€ pour réaliser la série des châssis d’interfaces RF
  ? Câbles
2026
  116k€ approvisionnements cartes IOXOS (8 + 2 spares)  Call for tender in preparation CCTP
  ? Series IDROGEN+ REFGEN+ TIMGEN depending of needs (LLRF + others systems) +C&C FTS (8 + 2 spares)
  80 k€ Châssis MTCA (9 native-R5 allowing to implement others needs )  discussion with Diags Team NAT or Vadatech
  ~ 400k€ Lignes RF , RF cables and Timing
  500k€ Circulateurs (nb: 8 for 60kW) and Loads (nb 8 : 240k€ for 80kW and RL = 30dB or 175k€ for 60kW and RL=26dB)
    One circulator and 2 loads of SSA validation  need a decision about the max power for them. See Booster case below :
  270k€ k€ Amplificateurs SSA (nb : 3 at 8.8 kW) Phase 1 (~5mA) for the injector
prototype rack Module puissance Piezo
~5k€ TBC
Using its for the ERL linac when booster tested if necessary to change it.

## Slide 10: Points de vigilance suite
2027
  1.4M€ ? Amplificateurs SSA (nb 4 at 35kW)  Reflexion en cours avec G. Olry, R. Roux, …
2028
  ? Upgrade Amplificateurs SSA for the injector( power 10 kW to 50kW, bandwidth-dependent)