## WP8 timeline
Timeline in project months (M) |  |  |  | M/D | # | Related WP | Related task | Description | Status | Risk level | Comments
Y1 | M6 | August | 2024 | D | 33 | WP8 | 8.2 Outreach and dissemination | Creation of a Dissemination & Exploitation Plan | Accounted for | On track | Due date postponed 1 month to M7
Y1 | M6 | August | 2024 | D | 25 | WP8 | 8.4 Open science | Development of a data management plan (DMP) | Accounted for | On track | Due date postponed 1 month to M7
Y2 | M24 | Feb | 2026 | M | 27 | WP8 | 8.2 Outreach and dissemination | First update of iSAS D&E plan | Accounted for | On track | Comment
Y2 | M24 | Feb | 2026 | M | 28 | WP8 | 8.4 Open science | Update of the DMP | Accounted for | On track | Comment
Y3 | M36 | Feb | 2027 | M | 29 | WP8 | 8.3 Diversity & equity | Implement portraits of role models on iSAS website | In progress | On track | Comment
Y4 | M44 | Oct | 2027 | D | 26 | WP8 | 8.2 Outreach and dissemination | Report on the implementation of iSAS D&E | Not started | On track | Comment
Y4 | M44 | Oct | 2027 | D | 27 | WP8 | 8.3 Diversity & equity | Reports on diversity surveys | Not started | On track | Comment
Y4 | M44 | Oct | 2027 | D | 28 | WP8 | 8.4 Open science | Implement open platform solution for iSAS partners | Not started | On track | Comment
Note on B1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F1: adele de-valera: Milestone or Deliverable
Note on G1: adele de-valera: milestone or deliverable number
Note on H1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS

## WP8 M17
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP8 | Societal impact |  | CNRS |  | Y2 | M17 | July | 2025 |  |  | Last update timestamp
|  |  |  | WP Coordination | Adèle de Valera | [5 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP8 meetings | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | Done | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** 3rd IB meeting |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person respoonsible | Participants |  |  |  |  | In progress | On track | w/ relevant WPX documentation to share
|  | WP8 | 8.1 Training & Early Career |  | CNRS | [7 empty] | No M or D in GANTT (GA p127) nor SyGMa for this task -> amendment
M/D | # | WP8 | 8.1 | Train early career & industrial researchers in iSAS tech | Person respoonsible | Participants | Y3 | M36 | Feb | 2027 | Not started | On track | w/ INFN? Michele Bertucci confirmed interest
|  |  |  | * New online courses to create | Person respoonsible | Participants |  | MX |  |  | Not started | On track | with European projects EURO-LABS and I.FAST
|  |  |  | ** Phase 1 to develop iSAS tech | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** Phase 2 to use iSAS tech | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** & hands-on training during validation phase | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M36 |  |  | Not started | On track | Comment
|  | WP8 | 8.2 Outreach (from WP9.3) |  | CNRS
D | 29 | WP8 | 8.2 | Creation of the iSAS website | Ketel Turzó |  | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
D | 33 | WP8 | 8.2 | Creation of a dissemination & exploitation plan | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 27 | WP8 | 8.2 | First update of iSAS D&E plan | Adèle de Valera | Ketel Turzó | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
D | 26 | WP8 | 8.2 | Report on the implementation of iSAS D&E |  |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Creation of iSAS logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Promotional mug with logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Database of com actions to create & update |  |  |  | M5 |  |  | Done | On track | Including outside scope of conferences
|  |  |  | * Website task force to set up |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Phase 1 - Skeleton |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Phase 2 - Content |  |  |  | M10 |  |  | In progress | On track | Web developpers not responsive despite reminders
|  |  |  | * News items to write, to relay | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** CERN Courier interview |  |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** Actu in2p3 interview (relayed to com@ijclab) |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ERL4ALL related topic by Maud |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Lode Vanhecke joins iSAS at the EPFL |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** Andrei Maalberg hired, by Nick |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Job opening at ESS: Junior Engineer or Scientist to innovate on Cryomodule sustainability |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** Breakthrough from our iSAS partner HZB in SRF accelerator physics |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** HZB to host First Workshop on Ferro-Electric Fast Reactive Tuners (FE-FRTs) |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Conferences to participate to | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** ICHEP, Prague, talk | Jorgen D'Hondt |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** ESSRI, Madrid, talk | Jorgen D'Hondt |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ICRI side-event, Brisbane, talk | Jorgen D'Hondt |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** IPAC'25, Taipei, paper | HZB team |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** HIAT'25, paper presented | Maud Baylac | J. D’Hondt, J. Knobloch, C. Pira, A. Stocchi |  | M16 |  |  | Done | On track | Comment
|  |  |  | * Conference Coordinator to nominate | Nicholas Shipman |  |  | M4 |  |  | Done | On track | Comment
|  |  |  | ** Conference compilation available in repository | Nicholas Shipman |  |  | M18 |  |  | Done | On track | Comment
|  | WP8 | 8.3 Diversity & equity |  | CNRS
|  |  | 8.3 | Genera Network to join | Adèle de Valera | Ketel Turzó |  |  |  |  | In progress | On track | Comment
|  |  |  | * Genera Genaral Assembly to participate to | Adèle de Valera | Ketel Turzó |  | M19 |  |  | Done | On track | Sept 4-5 2025 in Limerick
|  |  |  | * New MoU to sign | Achille Stocchi | Adèle de Valera |  | M19 |  |  | In progress | On track | To be discussed in Limerick
M | 29 | WP8 | 8.3 | Implement portraits of role models on iSAS website | Person respoonsible | Ketel Turzó | Y3 | M36 | Feb | 2027 | Not started | On track | w/ HZB Genera Network?
|  |  |  | * Interviews of high-level women scientists | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M36 |  |  | Not started | On track | Comment
D | 27 | WP8 | 8.3 | Report on diversity | Person respoonsible | Ketel Turzó | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Surveys | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on existing good practices, needs and ideas | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on diversity among early career researchers | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Awareness actions | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Mentorship for female PhD students | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person respoonsible | Participants |  | M44 |  |  | Not started | On track | Comment
|  | WP8 | 8.4 Open science |  | CNRS
D | 25 | WP8 | 8.4 | Development of a data management plan (DMP) | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 28 | WP8 | 8.4 | Update of the DMP | Adèle de Valera |  | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
D | 28 | WP8 | 8.4 | Implement open platform solution for iSAS partners | Person respoonsible |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person respoonsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out |  |  |  | M |  |  | Not started | On track | Comment
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F29: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H32: adele de-valera: Review
Note on H33: adele de-valera: Review
Note on F51: adele de-valera: International conference on high energy physics (ICHEP)
Note on F53: adele de-valera: International Conference on Research Infrastructures (ICRI)
Note on F64: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F67: adele de-valera: (of iSAS participants)
Note on F69: adele de-valera: on unconscious biases about diversity tailored to accelerator physics groups
Note on F71: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H73: adele de-valera: Review
Note on F75: adele de-valera: "During the project, iSAS will select an open platform to make results available to industries and institutions. This will be done in collaboration with the H2020 ESCAPE Science Cluster open collaboration, to benefit from their work and solutions for FAIR data-intensive research and open science. iSAS will be a highlighted “innovation use-case” for ESCAPE in its aim to further structure the EOSC ecosystem as the European data space for science, research and innovation. For iSAS, an even greater impact can be expected due to its disciplinary context and its forward-looking approach that strengthens synergies between researchers and industries. Accordingly, iSAS is well positioned to foster the connection between EOSC and the other sector data spaces outlined in the European Strategy for Data (e.g., Industrial & Manufacturing, Green Deal). Maximizing the legacy of iSAS will be achieved with its plan to maintain data and services after the project, so adhering to the strategy of creating a single market for data that will ensure Europe’s global competitiveness and data sovereignty. In such a context, leveraging the collaboration with ESCAPE and the participation of some industries in the Gaia-X network, iSAS offers a potential pilot project to help in bridging collaborations for the implementation of the European cloud data federation" GA p121
Note on F77: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## WP8 M19
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP8 | Societal impact |  | CNRS |  | Y2 | M19 | Sept | 2025 |  |  | Last update timestamp
|  |  |  | WP Coordination | Adèle de Valera | [5 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP8 meetings | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April Steering Co |  |  |  | M14 |  |  | Done | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July Steering Co |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** 3rd IB meeting |  |  |  | M17 |  |  | Not started | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Not started | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | Not started | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person responsible | Participants |  |  |  |  | In progress | On track | w/ relevant WPX documentation to share
|  | WP8 | 8.1 Training & Early Career |  | CNRS | [7 empty] | No M or D in GANTT (GA p127) nor SyGMa for this task -> amendment
M/D | # | WP8 | 8.1 | Train early career & industrial researchers in iSAS tech | Person respoonsible | Participants | Y3 | M36 | Feb | 2027 | In progress | On track | w/ INFN Michele Bertucci confirmed interest
|  |  |  | * New online courses to create | Person responsible | Participants |  | MX |  |  | Not started | On track | with European projects EURO-LABS and I.FAST
|  |  |  | ** Phase 1 to develop iSAS tech | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** Phase 2 to use iSAS tech | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** & hands-on training during validation phase | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
|  | WP8 | 8.2 Outreach (from WP9.3) |  | CNRS
D | 29 | WP8 | 8.2 | Creation of the iSAS website | Ketel Turzó |  | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
D | 33 | WP8 | 8.2 | Creation of a dissemination & exploitation plan | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 27 | WP8 | 8.2 | First update of iSAS D&E plan | Adèle de Valera | Ketel Turzó | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
D | 26 | WP8 | 8.2 | Report on the implementation of iSAS D&E |  |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Creation of iSAS logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Promotional mug with logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Database of com actions to create & update |  |  |  | M5 |  |  | Done | On track | Including outside scope of conferences
|  |  |  | * Website task force to set up |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Phase 1 - Skeleton |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Phase 2 - Content |  |  |  | M10 |  |  | In progress | On track | Web developpers not responsive despite reminders
|  |  |  | * News items to write, to relay | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** CERN Courier interview |  |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** Actu in2p3 interview (relayed to com@ijclab) |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ERL4ALL related topic by Maud |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Lode Vanhecke joins iSAS at the EPFL |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** Andrei Maalberg hired, by Nick |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Job opening at ESS: Junior Engineer or Scientist to innovate on Cryomodule sustainability |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** Breakthrough from our iSAS partner HZB in SRF accelerator physics |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** HZB to host First Workshop on Ferro-Electric Fast Reactive Tuners (FE-FRTs) |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Conferences to participate to | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** ICHEP, Prague, talk | Jorgen D'Hondt |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** ESSRI, Madrid, talk | Jorgen D'Hondt |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ICRI side-event, Brisbane, talk | Jorgen D'Hondt |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** IPAC'25, Taipei, paper | HZB team |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** HIAT'25, paper presented | Maud Baylac | J. D’Hondt, J. Knobloch, C. Pira, A. Stocchi |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** Workshop on FE-FRTs hosted by HZB | Nicholas Shipman |  |  | M21 |  |  | In progress | On track | Comment
|  |  |  | * Conference Coordinator to nominate | Nicholas Shipman |  |  | M4 |  |  | Done | On track | Comment
|  |  |  | ** Conference compilation available in repository | Nicholas Shipman |  |  | M18 |  |  | Done | On track | Comment
|  | WP8 | 8.3 Diversity & equity |  | CNRS
|  |  | 8.3 | Genera Network to join | Adèle de Valera | Ketel Turzó |  |  |  |  | In progress | On track | As the iSAS Consortium
|  |  |  | * Genera Genaral Assembly to participate to | Adèle de Valera | Ketel Turzó |  | M19 |  |  | Done | On track | Sept 4-5 2025 in Limerick
|  |  |  | * New MoU to sign | Achille Stocchi | Adèle de Valera |  | M19 |  |  | In progress | On track | Discussed in Limerick
M | 29 | WP8 | 8.3 | Implement portraits of role models on iSAS website | Adèle de Valera | Ketel Turzó | Y3 | M36 | Feb | 2027 | In progress | On track | w/ Genera Network input
|  |  |  | * Interviews of high-level women scientists | Adèle de Valera | Participants |  | MX |  |  | In progress | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
D | 27 | WP8 | 8.3 | Report on diversity | Person responsible | Ketel Turzó | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Surveys | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on existing good practices, needs and ideas | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on diversity among early career researchers | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Awareness actions | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Mentorship for female PhD students | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M44 |  |  | Not started | On track | Comment
|  | WP8 | 8.4 Open science |  | CNRS
D | 25 | WP8 | 8.4 | Development of a data management plan (DMP) | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 28 | WP8 | 8.4 | Update of the DMP | Adèle de Valera |  | Y2 | M24 | Feb | 2026 | Not started | On track | Comment
D | 28 | WP8 | 8.4 | Implement open platform solution for iSAS partners | Person responsible |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out |  |  |  | M |  |  | Not started | On track | Comment
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F29: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H32: adele de-valera: Review
Note on H33: adele de-valera: Review
Note on F51: adele de-valera: International conference on high energy physics (ICHEP)
Note on F53: adele de-valera: International Conference on Research Infrastructures (ICRI)
Note on F65: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F68: adele de-valera: (of iSAS participants)
Note on F70: adele de-valera: on unconscious biases about diversity tailored to accelerator physics groups
Note on F72: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H74: adele de-valera: Review
Note on F76: adele de-valera: "During the project, iSAS will select an open platform to make results available to industries and institutions. This will be done in collaboration with the H2020 ESCAPE Science Cluster open collaboration, to benefit from their work and solutions for FAIR data-intensive research and open science. iSAS will be a highlighted “innovation use-case” for ESCAPE in its aim to further structure the EOSC ecosystem as the European data space for science, research and innovation. For iSAS, an even greater impact can be expected due to its disciplinary context and its forward-looking approach that strengthens synergies between researchers and industries. Accordingly, iSAS is well positioned to foster the connection between EOSC and the other sector data spaces outlined in the European Strategy for Data (e.g., Industrial & Manufacturing, Green Deal). Maximizing the legacy of iSAS will be achieved with its plan to maintain data and services after the project, so adhering to the strategy of creating a single market for data that will ensure Europe’s global competitiveness and data sovereignty. In such a context, leveraging the collaboration with ESCAPE and the participation of some industries in the Gaia-X network, iSAS offers a potential pilot project to help in bridging collaborations for the implementation of the European cloud data federation" GA p121
Note on F78: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## WP8 M26
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP8 | Societal impact |  | CNRS |  | Y3 | M26 | April | 2026 |  |  | Last update timestamp
|  |  |  | WP Coordination | Adèle de Valera | [5 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP8 meetings | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct 2024 Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan 2025 Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April 2025 Steering Co |  |  |  | M14 |  |  | Done | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July 2025 Steering Co |  |  |  | M17 |  |  | Done | On track | Comment
|  |  |  | ** Dec 2025 Steering Co |  |  |  | M22 |  |  | Done | On track | Comment
|  |  |  | ** Jan 2026 Steering Co |  |  |  | M23 |  |  | Done | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** 3rd IB meeting |  |  |  | M17 |  |  | Done | On track | Comment
|  |  |  | ** 1st Review meeting in Berlin |  |  |  | M26 |  |  | In progress | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Done | On track | Comment
|  |  |  | ** Lund meeting (tbc) |  |  |  | M37 |  |  | In progress | On track | Host tbc
|  |  |  | ** Closure annual meeting at Nikhef (tbc) |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person responsible | Participants |  |  |  |  | In progress | On track | w/ relevant WPX documentation to share
|  | WP8 | 8.1 Training & Early Career |  | CNRS | [7 empty] | No M or D in GANTT (GA p127) nor SyGMa for this task -> amendment
M/D | # | WP8 | 8.1 | Train early career & industrial researchers in iSAS tech | Person respoonsible | Participants | Y3 | M36 | Feb | 2027 | In progress | On track | w/ INFN Michele Bertucci confirmed interest
|  |  |  | * New online courses to create | Person responsible | Participants |  | MX |  |  | In progress | On track | with European projects EURO-LABS and I.FAST
|  |  |  | ** Phase 1 to develop iSAS tech | Person responsible | Participants |  | MX |  |  | In progress | On track | Comment
|  |  |  | ** Phase 2 to use iSAS tech | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** & hands-on training during validation phase | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
|  | WP8 | 8.1 | Counting of young researchers in the project | Person responsible | Participants |  | MX |  |  | In progress | On track | Comment
|  |  |  | Def of postdocs tbd | Person responsible | Participants |  | MX |  |  | In progress | On track | PhD + 7 years consensual within Consortium?
|  |  |  | Def of profiles of young researcher to count | Person responsible | Participants |  | MX |  |  | In progress | On track | Postdocs, PhDs, Interns (by profile), hired by iSAS, working on other subjects too (by impact), etc.
|  | WP8 | 8.2 Outreach (from WP9.3) |  | CNRS
D | 29 | WP8 | 8.2 | Creation of the iSAS website | Ketel Turzó |  | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
D | 33 | WP8 | 8.2 | Creation of a dissemination & exploitation plan | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 27 | WP8 | 8.2 | First update of iSAS D&E plan | Adèle de Valera | Ketel Turzó | Y2 | M24 | Feb | 2026 | Accounted for | On track | Comment
D | 26 | WP8 | 8.2 | Report on the implementation of iSAS D&E |  |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Creation of iSAS logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Promotional mug with logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Database of com actions to create & update |  |  |  | M5 |  |  | Done | On track | Including outside scope of conferences
|  |  |  | * Website task force to set up |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Phase 1 - Skeleton |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Phase 2 - Content |  |  |  | M10 |  |  | In progress | On track | Web developpers not responsive despite reminders
|  |  |  | * News items to write, to relay | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** CERN Courier interview |  |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** Actu in2p3 interview (relayed to com@ijclab) |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ERL4ALL related topic by Maud |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Lode Vanhecke joins iSAS at the EPFL |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** Andrei Maalberg hired, by Nick |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Job opening at ESS: Junior Engineer or Scientist to innovate on Cryomodule sustainability |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** Breakthrough from our iSAS partner HZB in SRF accelerator physics |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** HZB to host First Workshop on Ferro-Electric Fast Reactive Tuners (FE-FRTs) |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Conferences to participate to | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** ICHEP, Prague, talk | Jorgen D'Hondt |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** ESSRI, Madrid, talk | Jorgen D'Hondt |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ICRI side-event, Brisbane, talk | Jorgen D'Hondt |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** IPAC'25, Taipei, paper | HZB team |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** HIAT'25, paper presented | Maud Baylac | J. D’Hondt, J. Knobloch, C. Pira, A. Stocchi |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** Workshop on FE-FRTs hosted by HZB | Nicholas Shipman |  |  | M21 |  |  | In progress | On track | Comment
|  |  |  | * Conference Coordinator to nominate | Nicholas Shipman |  |  | M4 |  |  | Done | On track | Comment
|  |  |  | ** Conference compilation available in repository | Nicholas Shipman |  |  | M18 |  |  | Done | On track | Comment
|  | WP8 | 8.3 Diversity & equity |  | CNRS
|  |  | 8.3 | Genera Network to join | Adèle de Valera | Ketel Turzó |  |  |  |  | In progress | On track | As the iSAS Consortium
|  |  |  | * Genera Genaral Assembly to participate to | Adèle de Valera | Ketel Turzó |  | M19 |  |  | Done | On track | Sept 4-5 2025 in Limerick
|  |  |  | * New MoU to sign | Achille Stocchi | Adèle de Valera |  | M19 |  |  | Done | On track | Discussed in Limerick
M | 29 | WP8 | 8.3 | Implement portraits of role models on iSAS website | Adèle de Valera | Ketel Turzó | Y3 | M36 | Feb | 2027 | In progress | On track | w/ Genera Network input
|  |  |  | * Interviews of high-level women scientists | Adèle de Valera | Participants |  | M27 |  |  | In progress | On track | Maud Baylac, Yolanda GM, Emma Simpson & social media carrousel
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
D | 27 | WP8 | 8.3 | Report on diversity | Person responsible | Ketel Turzó | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Surveys | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on existing good practices, needs and ideas | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on diversity among early career researchers | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Awareness actions | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Mentorship for female PhD students | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M44 |  |  | Not started | On track | Comment
|  | WP8 | 8.4 Open science |  | CNRS
D | 25 | WP8 | 8.4 | Development of a data management plan (DMP) | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 28 | WP8 | 8.4 | Update of the DMP | Adèle de Valera |  | Y2 | M24 | Feb | 2026 | Accounted for | On track | Comment
|  |  |  | Choice of licence for ArXiv: CC BY-NC-ND 4.0 | Maud Baylac | Adèle de Valera |  | M27 |  |  | Done | On track | Same as Maalberg paper proceedings for IFAC'26
D | 28 | WP8 | 8.4 | Implement open platform solution for iSAS partners | Person responsible |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out |  |  |  | M |  |  | Not started | On track | Comment
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F32: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H38: adele de-valera: Review
Note on H39: adele de-valera: Review
Note on F57: adele de-valera: International conference on high energy physics (ICHEP)
Note on F59: adele de-valera: International Conference on Research Infrastructures (ICRI)
Note on F71: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F74: adele de-valera: (of iSAS participants)
Note on F76: adele de-valera: on unconscious biases about diversity tailored to accelerator physics groups
Note on F78: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H80: adele de-valera: Review
Note on F83: adele de-valera: "During the project, iSAS will select an open platform to make results available to industries and institutions. This will be done in collaboration with the H2020 ESCAPE Science Cluster open collaboration, to benefit from their work and solutions for FAIR data-intensive research and open science. iSAS will be a highlighted “innovation use-case” for ESCAPE in its aim to further structure the EOSC ecosystem as the European data space for science, research and innovation. For iSAS, an even greater impact can be expected due to its disciplinary context and its forward-looking approach that strengthens synergies between researchers and industries. Accordingly, iSAS is well positioned to foster the connection between EOSC and the other sector data spaces outlined in the European Strategy for Data (e.g., Industrial & Manufacturing, Green Deal). Maximizing the legacy of iSAS will be achieved with its plan to maintain data and services after the project, so adhering to the strategy of creating a single market for data that will ensure Europe’s global competitiveness and data sovereignty. In such a context, leveraging the collaboration with ESCAPE and the participation of some industries in the Gaia-X network, iSAS offers a potential pilot project to help in bridging collaborations for the implementation of the European cloud data federation" GA p121
Note on F85: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## WP8 M32
M/D | # | Related WP | Related task | Description | Responsible | Participants | Timeline in project months (M) |  |  |  | Status | Risk level | Comments
|  | WP8 | Societal impact |  | CNRS |  | Y3 | M32 | Oct | 2026 |  |  | Last update timestamp
|  |  |  | WP Coordination | Adèle de Valera | [5 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * WP8 meetings | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | * Steering Committee | [6 empty] | In progress | On track | Comment
|  |  |  | ** Oct 2024 Steering Co |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Jan 2025 Steering Co |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** April 2025 Steering Co |  |  |  | M14 |  |  | Done | On track | Advisory Board WPX recos to integrate
|  |  |  | ** July 2025 Steering Co |  |  |  | M17 |  |  | Done | On track | Comment
|  |  |  | ** Dec 2025 Steering Co |  |  |  | M22 |  |  | Done | On track | Comment
|  |  |  | ** Jan 2026 Steering Co |  |  |  | M23 |  |  | Done | On track | Comment
|  |  |  | ** Oct 2026 Steering Co |  |  |  | M32 |  |  | Not started | On track | Comment
|  |  |  | * Industry Board meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** 1st IB meeting |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** 2nd IB meeting |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Industry Workshop in Padova |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** 3rd IB meeting |  |  |  | M17 |  |  | Done | On track | Comment
|  |  |  | ** IB meeting in Berlin |  |  |  | M26 |  |  | Done | On track | Comment
|  |  |  | ** 1st Review meeting w/ ILOs |  |  |  | M33 |  |  | In progress | On track | Comment
|  |  |  | * Yearly project meetings | [6 empty] | In progress | On track | Comment
|  |  |  | ** Kick-off meeting at IJCLab |  |  |  | M2 |  |  | Done | On track | Comment
|  |  |  | ** Padova meeting |  |  |  | M13 |  |  | Done | On track | Comment
|  |  |  | ** Berlin meeting |  |  |  | M25 |  |  | Done | On track | Comment
|  |  |  | ** Lund meeting |  |  |  | M37 |  |  | In progress | On track | Comment
|  |  |  | ** Closure annual meeting at (tbc) |  |  |  | M48 |  |  | Not started | On track | Host tbc
|  |  |  | * Project data repository to update regularly | Person responsible | Participants |  |  |  |  | In progress | On track | w/ relevant WPX documentation to share
|  | WP8 | 8.1 Training & Early Career |  | CNRS | [7 empty] | No M or D in GANTT (GA p127) nor SyGMa for this task -> amendment
M/D | # | WP8 | 8.1 | Train early career & industrial researchers in iSAS tech | Person respoonsible | Participants | Y3 | M36 | Feb | 2027 | In progress | On track | w/ INFN Michele Bertucci confirmed interest
|  |  |  | * New online courses to create | Person responsible | Participants |  | MX |  |  | In progress | On track | with European projects EURO-LABS and I.FAST
|  |  |  | ** Phase 1 to develop iSAS tech | Person responsible | Participants |  | MX |  |  | In progress | On track | Comment
|  |  |  | ** Phase 2 to use iSAS tech | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** & hands-on training during validation phase | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
|  | WP8 | 8.1 | Counting of young researchers in the project | Person responsible | Participants |  | M28 |  |  | In progress | On track | Comment
|  |  |  | Def of postdocs tbd | Person responsible | Participants |  | M28 |  |  | In progress | On track | PhD + 7 years consensual within Consortium?
|  |  |  | Def of profiles of young researcher to count | Person responsible | Participants |  | M28 |  |  | In progress | On track | Postdocs, PhDs, Interns (by profile), hired by iSAS, working on other subjects too (by impact), etc.
|  |  |  | Table of young researchers & female accelerator scientists | Person responsible | Participants |  | M28 |  |  | In progress | On track | % created fromtable
|  | WP8 | 8.2 Outreach (from WP9.3) |  | CNRS
D | 29 | WP8 | 8.2 | Creation of the iSAS website | Ketel Turzó |  | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
D | 33 | WP8 | 8.2 | Creation of a dissemination & exploitation plan | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 27 | WP8 | 8.2 | First update of iSAS D&E plan | Adèle de Valera | Ketel Turzó | Y2 | M24 | Feb | 2026 | Accounted for | On track | Comment
D | 26 | WP8 | 8.2 | Report on the implementation of iSAS D&E |  |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Creation of iSAS logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Promotional mug with logo |  |  |  | M1 |  |  | Done | On track | Comment
|  |  |  | * Database of com actions to create & update |  |  |  | M5 |  |  | Done | On track | Including outside scope of conferences
|  |  |  | * Website task force to set up |  |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** Phase 1 - Skeleton |  |  |  | M8 |  |  | Done | On track | Comment
|  |  |  | ** Phase 2 - Content |  |  |  | M10 |  |  | In progress | On track | Web developpers not responsive despite reminders
|  |  |  | * News items to write, to relay | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** CERN Courier interview |  |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** Actu in2p3 interview (relayed to com@ijclab) |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ERL4ALL related topic by Maud |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Lode Vanhecke joins iSAS at the EPFL |  |  |  | M11 |  |  | Done | On track | Comment
|  |  |  | ** Andrei Maalberg hired, by Nick |  |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** Job opening at ESS: Junior Engineer or Scientist to innovate on Cryomodule sustainability |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** Breakthrough from our iSAS partner HZB in SRF accelerator physics |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | ** HZB to host First Workshop on Ferro-Electric Fast Reactive Tuners (FE-FRTs) |  |  |  | M14 |  |  | Done | On track | Comment
|  |  |  | * Conferences to participate to | [6 empty] | In progress | On track | All throughout the project (timeline-wise)
|  |  |  | ** ICHEP, Prague, talk | Jorgen D'Hondt |  |  | M5 |  |  | Done | On track | Comment
|  |  |  | ** ESSRI, Madrid, talk | Jorgen D'Hondt |  |  | M7 |  |  | Done | On track | Comment
|  |  |  | ** ICRI side-event, Brisbane, talk | Jorgen D'Hondt |  |  | M10 |  |  | Done | On track | Comment
|  |  |  | ** IPAC'25, Taipei, paper | HZB team |  |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** HIAT'25, paper presented | Maud Baylac | J. D’Hondt, J. Knobloch, C. Pira, A. Stocchi |  | M16 |  |  | Done | On track | Comment
|  |  |  | ** Workshop on FE-FRTs hosted by HZB | Nicholas Shipman |  |  | M21 |  |  | In progress | On track | Comment
|  |  |  | * Conference Coordinator to nominate | Nicholas Shipman |  |  | M4 |  |  | Done | On track | Comment
|  |  |  | ** Conference compilation available in repository | Nicholas Shipman |  |  | M18 |  |  | Done | On track | Comment
|  | WP8 | 8.3 Diversity & equity |  | CNRS
|  |  | 8.3 | Genera Network to join | Adèle de Valera | Ketel Turzó |  |  |  |  | In progress | On track | As the iSAS Consortium
|  |  |  | * Genera Genaral Assembly to participate to | Adèle de Valera | Ketel Turzó |  | M19 |  |  | Done | On track | Sept 4-5 2025 in Limerick
|  |  |  | * New MoU to sign | Achille Stocchi | Adèle de Valera |  | M19 |  |  | Done | On track | Discussed in Limerick
|  |  |  | * Genera Genaral Assembly to participate to | Adèle de Valera |  |  | M32 |  |  | Done | On track | Oct 7-9 2026 in Vilnius
M | 29 | WP8 | 8.3 | Implement portraits of role models on iSAS website | Adèle de Valera | Ketel Turzó | Y3 | M36 | Feb | 2027 | In progress | On track | w/ Genera Network input
|  |  |  | * Interviews of high-level women scientists | Adèle de Valera | Participants |  | M27 |  |  | In progress | On track | Maud Baylac, Yolanda GM, Emma Simpson & social media carrousel
|  |  |  | * Close out | Person responsible | Participants |  | M36 |  |  | Not started | On track | Comment
D | 27 | WP8 | 8.3 | Report on diversity | Person responsible | Ketel Turzó | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Surveys | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on existing good practices, needs and ideas | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | ** on diversity among early career researchers | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Awareness actions | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Mentorship for female Accelerator scientists | Adèle de Valera | Maud Baylac, Yolanda Gómez-Martínez, Karin Canderan, Maria Rosaria Masullo |  | M29 |  |  | In progress | On track | Comment
|  |  |  | * Close out | Person responsible | Participants |  | M44 |  |  | Not started | On track | Comment
|  | WP8 | 8.4 Open science |  | CNRS
D | 25 | WP8 | 8.4 | Development of a data management plan (DMP) | Adèle de Valera | Ketel Turzó | Y1 | M6 | August | 2024 | Accounted for | On track | Due date postponed 1 month to M7
M | 28 | WP8 | 8.4 | Update of the DMP | Adèle de Valera |  | Y2 | M24 | Feb | 2026 | Accounted for | On track | Comment
|  |  |  | Choice of licence for ArXiv: CC BY-NC-ND 4.0 | Maud Baylac | Adèle de Valera |  | M27 |  |  | Done | On track | Same as Maalberg paper proceedings for IFAC'26
D | 28 | WP8 | 8.4 | Implement open platform solution for iSAS partners | Person responsible |  | Y4 | M44 | Oct | 2027 | Not started | On track | Comment
|  |  |  | * Subtasks tbd | Person responsible | Participants |  | MX |  |  | Not started | On track | Comment
|  |  |  | * Close out |  |  |  | M |  |  | Not started | On track | Comment
Note on B1: adele de-valera: Milestone or Deliverable
Note on C1: adele de-valera: milestone or deliverable number
Note on D1: adele de-valera: WP1 Ferro-electric fast reactive tuners @HZB 1.1 HZB 1.2 CERN 1.3 HZB 1.4 CNRS WP2 Low level RF controls @DESY 2.1 DESY 2.2 DESY 2.3 DESY 2.4 HZB 2.5 DESY WP3 Nb3Sn-on-Cu films for 4.2-K cavity operation @INFN 3.1 INFN 3.2 UKRI 3.3 HZB 3.4 CEA 3.5 UKRI WP4 Higher-order mode dampers & fundamental power couplers @IPSC = CNRS 4.1 CNRS 4.2 INFN 4.3 CERN 4.4 CNRS 4.5 CERN 4.6 CERN 4.7 CERN WP5 Integration into a new LINAC cryomodule @ESS 5.1 ESS 5.2 CERN 5.3 CNRS 5.4 EPFL WP6 Integration into accelerator & collider RIs @IJCLab = CNRS 6.1 CNRS 6.2 UL? 6.3 ? 6.4 ? 6.5 ? WP7 Integration into industrial solutions @INFN 7.1 INFN 7.2 INFN? 7.3 INFN? WP8 Societal impact @IJCLab = CNRS 8.1 CNRS 8.2 CNRS 8.3 CNRS 8.4 CNRS WP9 Coordiantation & management @IJCLab = CNRS 9.1 CNRS 9.2 CNRS 9.3 CNRS 9.4 CNRS 9.5 CNRS
Note on H1: adele de-valera: other contributors than person responsible
Note on I1: adele de-valera: Due date last calendar day of the month, 12 pm Brussels time
Note on F34: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H41: adele de-valera: Review
Note on H42: adele de-valera: Review
Note on F60: adele de-valera: International conference on high energy physics (ICHEP)
Note on F62: adele de-valera: International Conference on Research Infrastructures (ICRI)
Note on F75: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on F78: adele de-valera: (of iSAS participants)
Note on F80: adele de-valera: on unconscious biases about diversity tailored to accelerator physics groups
Note on F82: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date
Note on H84: adele de-valera: Review
Note on F87: adele de-valera: "During the project, iSAS will select an open platform to make results available to industries and institutions. This will be done in collaboration with the H2020 ESCAPE Science Cluster open collaboration, to benefit from their work and solutions for FAIR data-intensive research and open science. iSAS will be a highlighted “innovation use-case” for ESCAPE in its aim to further structure the EOSC ecosystem as the European data space for science, research and innovation. For iSAS, an even greater impact can be expected due to its disciplinary context and its forward-looking approach that strengthens synergies between researchers and industries. Accordingly, iSAS is well positioned to foster the connection between EOSC and the other sector data spaces outlined in the European Strategy for Data (e.g., Industrial & Manufacturing, Green Deal). Maximizing the legacy of iSAS will be achieved with its plan to maintain data and services after the project, so adhering to the strategy of creating a single market for data that will ensure Europe’s global competitiveness and data sovereignty. In such a context, leveraging the collaboration with ESCAPE and the participation of some industries in the Gaia-X network, iSAS offers a potential pilot project to help in bridging collaborations for the implementation of the European cloud data federation" GA p121
Note on F89: adele de-valera: * M/D sent (by person responsible of the M/D) for check by coordination at least 1 week prior due date * Modification of M/D if needed & sent (by person responsible of the M/D) to management at least 1 day prior due date

## Key
By timeline | WP | Status | Risk level
Y1 | Task name | Not started | On track
Y2 | M/D description | In progress | Risk to mitigate
Y3 | * Subtasks | To review | In difficulty
Y4 | ** Sub-subtasks | Done
| {{ WPs interconnexions }} | To validate
| Test infra (to be) prepped | Accounted for
Test infra (to be) available
Note on H4: adele de-valera: no deviation from plans
Note on H5: adele de-valera: -> warn coordination asap for example, if follows similar trajectory, might likely get delayed or if a person responsible that has left is not replaced soon (and is not liekly to be)
Note on F6: adele de-valera: in-between in progress status and done status
Note on H6: adele de-valera: -> warn coordination asap for example the deliverable is not within reach anymore within the current agreed parameters (institute responsible, timeline, budget, etc.) and a solution has to be found and collectiveley validated to resume progress again
Note on F7: adele de-valera: after review status and before close out
Note on F8: adele de-valera: close out status, once M/D already done at WP level but not yet accounted for on EU reporting portal
Note on F9: adele de-valera: on EU continuous reporting portal by project management