iSAS weekly meeting

29th April 2026

Present: Achille Stocchi, Adèle de Valera

Notes:

RF2.0 & iSAS

* Rémi invited to weekly to start montage discussions

* Achille suggested aacronyms

* Adèle asks again for invitation e-mail from Anne to access Teams Channel

* iSAS GB asks for overlap risks w/ new project to be assessed & confirmed - Adèle TR to coordination

* & risks regarding results taken as a baseline to start the new project - Adèle TR to coordination

CA

* Alena sends CA vf compiled

* Adèle shares the CA final version in PDF as soon as DR4 will have done

AMD #2

* Jens sends HZB -> CERN funds transfer to account for & get PO greenlight

* Adèle asks for other M/D delays, tasks responsible changes or funds transfer needed to the work plan

WP6

* Adèle updates S. Berry as WP6 Deputy instead of Madur in all relevant documents

M&D due Feb 2026

WP3 missing D - IT bug w/ zip files enclosed in e-mails - recovered now - Adèle uploaded in EU portal & checks what might have happened

* Achille validates WP6 M

RP1 report

*Adèle updates portal w/ last M from M24 WP6 Impact risk analysis adjusted

* Achille reviews & validates

* Adèle sends the technical report to Justine Monnet @DR4 for process closure

Review meeting

* Adèle gets a few indicators for WP8 like the number of conference papers in the project data repository

* Adèle contacts com' team to get a few WP8 interviews done before the Review meeting

* Achille prepares a graph to show all interconnections between iSAS, EPITA, new project.... w/ iSAS at the centre & all branched out from it

* Adèle sends WP L&D Cc coo p the expectations for the PPTs (RP1 technical report in PPT format) w/ a template and due date in anticipation (1 week prior maybe?)

* Where to publish conf papers?

Next Weeklys

Not 6/5

* 13/5 COPIL INFRA...?

* 20/5 congés AS - to cancel...?

* 27/5 confirmed as to keep...?

June Weekly meetings not set yet

* Adèle sets next recurrence Weekly meetings...?