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iSAS weekly meeting 
29th April 2026 
 
Present: Achille Stocchi, Adèle de Valera 

Notes:

RF2.0 & iSAS 
* Rémi invited to weekly to start montage discussions
* Achille suggested aacronyms 
* Adèle asks again for invitation e-mail from Anne to access Teams Channel
* iSAS GB asks for overlap risks w/ new project to be assessed & confirmed - Adèle TR to coordination
* & risks regarding results taken as a baseline to start the new project - Adèle TR to coordination

CA  
* Alena sends CA vf compiled
* Adèle shares the CA final version in PDF as soon as DR4 will have done

AMD #2
* Jens sends HZB -> CERN funds transfer to account for & get PO greenlight
* Adèle asks for other M/D delays, tasks responsible changes or funds transfer needed to the work plan

WP6
* Adèle updates S. Berry as WP6 Deputy instead of Madur in all relevant documents

M&D due Feb 2026
WP3 missing D - IT bug w/ zip files enclosed in e-mails - recovered now - Adèle uploaded in EU portal & checks what might have happened
* Achille validates WP6 M 

RP1 report 
*Adèle updates portal w/ last M from M24 WP6 Impact risk analysis adjusted
* Achille reviews & validates 
* Adèle sends the technical report to Justine Monnet @DR4 for process closure 

Review meeting 
* Adèle gets a few indicators for WP8 like the number of conference papers in the project data repository
* Adèle contacts com' team to get a few WP8 interviews done before the Review meeting 
* Achille prepares a graph to show all interconnections between iSAS, EPITA, new project.... w/ iSAS at the centre & all branched out from it
* Adèle sends WP L&D Cc coo p the expectations for the PPTs (RP1 technical report in PPT format) w/ a template and due date in anticipation (1 week prior maybe?)
* Where to publish conf papers?

Next Weeklys
Not 6/5
* 13/5 COPIL INFRA...?
* 20/5 congés AS - to cancel...?
* 27/5 confirmed as to keep...?
June Weekly meetings not set yet
* Adèle sets next recurrence Weekly meetings...? 
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