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iSAS weekly meeting 
10th June 2026 
 
Present: Achille Stocchi, Adèle de Valera 

Notes:


RF2.0 & iSAS 
* E2-SCALE: Energy Efficient and Sustainable Collider, Accelerator and Light sources research infrastructures for Europe (confirmed)
* Plan A, B or C tbd

CA  
* Alena sends CA vf compiled
* Adèle proposed to compile if CNRS signature sent
* Adèle shares the CA final version in PDF as soon as DR4 will have done

AMD #2
* "Can you confirm that the 95k will be covered by internal resources and not by another public funding source?" (TR of msg from PO May 27 by Ketel)
* Adèle takes over from Ketel (for EPM) to survey delay needs from WP L&D -
* Vittorio & Jens send a technical justification for their funds transfer to hire a young researcher from CERN to HZB in WP1
* Adèle checks w/ WP5 Leader for technical justification & new due date for Task 5.4 delay to take into account the start date & duration of Lode's PhD contract 
* Adèle proposes dates (previously checked w/ Achille) to PO for discussing AMD#2 globally - all Coordination panel to include? 

Project extension 
* Adèle asks STIRI (then PO if needed) for clarification (after check in GA) on spending (especially if HR contracts that longer) after WP are closed in case of not all WP extended for the project extension (in case of only WP5, 6, 9 or so)
* Ketel is of the very strong opinion to extend ALL WPs - with a due justification

RP1 report 
* More detailed § on procurement difficulties in deviations section to be validated by Achille
* D#35 WP2.1 ML implementation plan re-submitted after SEN -> PU dissemination level modification
* Researchers involved in the project collection of missing info (like nationality & contract duration)
* IP strategy - IJCLab Technology Transfert TR documentation to prepare a proposal for industrial partners 
* EU logo to be replaced in industrial section of website - Adèle sent to vertical RGB neg logo to WP7 Leader
* EU logo to be checked on Indico presentations
* Publications tab to be modified (PID) - ArXiv to be the repository for publications & cannot be done by EPM (endorsed submissions)
* means we should prob afterwards delete the Indico page for conference talks & papers (otherwise too many different listings of the same documents to be kept updated & coherent with each other in their referencing - Achille to validate
* & means that IJCLab web developer then updates iSAS website navbar to ArXiv instead of Indico

Review meeting 
* Portraits for Maud & Yolanda published, Yolanda to modify photos & reduce text, Emma awaiting photo

Advisory Board report 
* Adèle sends clean vf to AdvB on May 27 

Next M/D due dates
WP9.1 D#34 Risk analysis related to impact of iSAS technologies due June 2026
* Who is responsible (technical dimension too) ?
* To de determined how the impact part factors in (no detail in GA)
* Ketel proposes to involve industrial partners in a prospective exercise
* PO asked for examples

Justification @DR4
* Adèle checks that PhD hire @IJCLab Axel Pérez Ruiz DOES account for his time on Agate-Tempo & on time (he's already in the system attached to iSAS)
* Achille ok for signature delegation to G. Olry? If yes, Adèle asks Clément Ascenção DR4

Communication
* To review Maud's response to conference talks Indico page w/ Achille (& notably on editorial practices of JACoW, because they have reviewers)
* To share expectations for the Conference coordinator w/ him (maybe done by Jorgen verbally 2 years ago, would probably be useful) 
* Online meeting External relations responsible & IJCLab Communication responsible to discuss future com' for iSAS for next months 

Next meetings 
* Adèle proposes dates for next academic year for all committees
* Adèle checks w/ Nuno if ESS would host next annual meeting in around Feb/March 2027 (ongoing internally at ESS for now)

Next Weeklys
* 15/7 TSEHEP Romania to cancel
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