iSAS weekly meeting

26th August 2026

Present: Achille Stocchi, Adèle de Valera

Notes:

M/D due August 2026 to review

Not received for review by coordination yet:

* WP3 D#11 Report on flux dynamics study in Nb3Sn on Cu samples -> WP3 Leader sent a reminder to Task Leader @UKRI

* WP6 D#20 Concept. design of a combined FE-FRT-HOM coupler -> WP6 Leader sent a reminder to Task Leader @UL

The 4 others are considered delayed by coordination arbitration

WP4

* INFN transfer done

RP1 evaluation

* Closed without observations on the portal by DR4

Formal IPR Strategy

* Adèle proposes a meeting w/ INFN TT

* Diego only responded as yet: Sept 11 at 2 pm or Sept 16 at 3 pm - Achille confirmed dates

AMD #2

* Adèle circled back to WPL who were not already GB members to inform them ab arbitrations made (WP2 & WP4)

* GB vote results until August 7:

* Adèle informed of decision made on August 10

* Adèle sent doc° @PO on August 10

* PO feedback not received yet

Justification @DR4

* Timesheets young researcher hired @IJCLab confirmed unnecessary

Coordination panel meeting

Sept 8

* To prepare

Invitation for RF2.0 closure project meeting

* Achille has been invited to present E2-SCALE, maybe w/ a few iSAS members

Annual meeting

* Adèle sends a reminder @Nuno if ESS hosts

Communication

* Achille proposes options for enlargement after annual meeting for mentoring programme: Hadil Abualrob, Rasha Abukeshek, Iryna Chaikovska, Angeles Faus Golfe, Sophie Chance

* Fairouz sees the person responsible for video caption on August 27 to get shooting dates

* Adèle & Maud start to build the iSAS collaborators list for the website - Achille suggests alphabetical order & institutes in 1