## Slide 1: Management Overview
StratusLab First Periodic Review
Brussels, Belgium
4 July 2011 (v4)

## Slide 2: StratusLab Project
Goal
  Create comprehensive, open-source, IaaS cloud distribution
  Focus on supporting grid services
Information
  1 June 2010—31 May 2012 (2 years)
  6 partners from 5 countries
  Budget : 3.3 M€ (2.3 M€ EC)
Contacts
  Site web: http://stratuslab.eu/
  Twitter: @StratusLab
  Support: support@stratuslab.eu
CNRS (FR)
UCM (ES)
GRNET (GR)
SIXSQ (CH)
TID (ES)
TCD (IE)

## Slide 3: Introductions
Charles LOOMIS | CNRS/LAL | Project coordinator, WP2 manager
Ruben MONTERO | UCM | Technical coordinator
David O’CALLAGHAN | TCD | WP3 manager
Marc-Elian BEGIN | SixSq | WP4 manager
Vangelis FLOROS | GRNET | WP5 manager
Henar MUNOZ | TID | WP6 manager
Christophe BLANCHET | CNRS/IBCP | WP2
Ignacio LLORENTE | UCM | WP6
All partners and all activities are represented.

## Slide 4: And the other participants…

## Slide 5: Objectives
Following presentations give detailed objectives for each work package.

## Slide 6: Changes in the Roadmap
Hybrid Cloud  Cloud API (public cloud)
  Cloud API (public cloud) moved from Y2 to Y1
  Hybrid cloud moved from Y1 to Y2
  Users requested access to public cloud sooner
  Federated cloud makes more sense once StratusLab distribution is complete and stable
Appliance Repository  Marketplace
  Emphasis on security and ability to understand image content
  Separate metadata and image storage
  Allows policies to be defined for “acceptable” images
  Takes advantage of cloud storage capabilities
No affect on objectives, milestones, or deliverables.

## Slide 7: Project Organization
WP1 (MGT): Project Management
  Overall coordination of project and technical program.
WP2 (NA): Interactions with Targeted Communities
  Manage liaisons with users and system administrators.
WP3 (NA): Dissemination
  Market StratusLab results to scientific community and general public.
WP4 (SA): Integration
  Integrate internal and external developments into StratusLab distribution.
WP5 (SA): Infrastructure Operations
  Operate cloud and grid services using StratusLab software.
WP6 (JRA): Innovative Cloud-like Services for Grid Site Management
  Develop innovative services to facilitate deployment/use of grid services.

## Slide 8: Project Management
Project Management Board
  Project coordinator
  Technical coordinator
  One representative from each partner
  Meets quarterly
  Sets overall goals of project and monitors progress
Technical and Scientific Coordination Group
  Technical coordinator
  Activity manager from each work package
  Meets monthly
  Defines overall architecture and development priorites

## Slide 9: Deliverables
Number | Title | Due Date
D2.1 | Review of the Use of Cloud and Virtualization Technologies in Grid Infrastructures | PM2
D4.1 | Reference Architecture for StratusLab Toolkit 1.0 | PM3
D5.1 | Infrastructure Specification | PM3
D3.1 | Initial Plan for Dissemination, Collaboration and Standardization Activities | PM4
D6.1 | Cloud-like Management of Grid Sites 1.0 Design Report | PM5
D5.2 | Infrastructure Tool and Policy Specification | PM6
D6.2 | Cloud-like Management of Grid Sites 1.0 Software | PM11
D2.2 | Report on Evaluation of StratusLab Products | PM12
D3.2 | Report on Dissemination, Collaboration and Standardization Activities | PM12
D3.3 | Exploitation and Sustainability First Plan | PM12
D4.2 | StratusLab Toolkit 1.0 | PM12
D4.3 | First Year Software Integration Report | PM12
D5.3 | First Year Infrastructure Operations Report | PM12
D6.3 | First Year Cloud-like Management of Grid Sites Research Report | PM12

## Slide 10: Milestones
Number | Title | Due Date
MS1 | Establishment of Management Infrastructure and Metrics Definition | PM3
MS6 | Website Operational | PM3
MS2 | Contact Procedures and Supporting Tools for Targeted Communities | PM4
MS7 | StratusLab Development, Certification and Release Procedures in Place | PM6
MS3 | Creation of Virtual Appliances for Bioinformatics Community | PM9
MS10 | Initial virtual appliance repository | PM9
MS14 | Release of Cloud-like Management of Grid Services and Resources 1.0 Beta | PM9
MS8 | Release of StratusLab 1.0 Beta | PM10
MS11 | Operation of Site Running StratusLab toolkit v1.0 | PM10
All milestones, deliverables, and quarterly reports have been submitted on schedule.
Two technical notes (Marketplace and Grid Service Operations in the Cloud) have also been produced.

## Slide 11: Financial Information
Underspending
  Most partners are underspending by ~25-30%
  No negative effects on work program, but…
  Need to discuss shifting budgets, prolonging project, etc.
Missing Information
  CNRS/IBCP
  TID

## Slide 12: CNRS/LAL
Comments
  Management taken less effort than foreseen, but periodic reporting will compensate somewhat.
  Overspend in WP2 compensates somewhat for underspend in WP5.
  Additional WP5 effort expected in Y2.
  Overspend on RC will become unfunded contributions to project.
 | RTD | Coordination | Support | Management | Other | Total
Planned Total |  | 144,036.00 |  | 122,166.00 | 155,491.00 | 623,463.00
Planned RC |  | 96,325.00 |  | 122,166.00 | 116,619.00 | 470,043.00
Y1 Planned Total |  | 72,018.00 |  | 61,083.00 | 77,745.50 | 311,731.50
Y1 Planned RC |  | 48,162.50 |  | 61,083.00 | 58,309.50 | 235,021.50
Y1 Actual Total |  | 104,154.14 |  | 43,792.51 | 68,925.17 | 216,871.82
Y1 Actual RC |  | 92,870.78 |  | 43,792.51 | 68,925.17 | 205,588.46
Diff Total |  | 45% |  | -28% | -11% | -30%
Diff RC |  | 93% |  | -28% | 18% | -13%

## Slide 13: UCM
Comments
  Blah…
 | RTD | Coordination | Support | Management | Other | Total
Planned Total | 241200.00 | 67600.00 |  |  | 282240.00 | 591040.00
Planned RC | 180900.00 | 45207.00 |  |  | 211680.00 | 437787.00
Y1 Planned Total | 120600.00 | 33800.00 |  |  | 141120.00 | 295520.00
Y1 Planned RC | 90450.00 | 22603.50 |  |  | 105840.00 | 218893.50
Y1 Actual Total | 58389.00 | 8553.00 |  |  | 32527.00 | 99469.00
Y1 Actual RC | 43792.00 | 5720.00 |  |  | 32527.00 | 82039.00
Diff Total | -52% | -75% |  |  | -77% | -66%
Diff RC | -52% | -75% |  |  | -69% | -63%

## Slide 14: GRNET
Comments
  Blah…
 | RTD | Coordination | Support | Management | Other | Total
Planned Total | 38,700.00 | 73,440.00 |  |  | 382,320.00 | 494,460.00
Planned RC | 19,350.00 | 43,656.00 |  |  | 286,740.00 | 349,746.00
Y1 Planned Total | 19,350.00 | 36,720.00 |  |  | 191,160.00 | 247,230.00
Y1 Planned RC | 9,675.00 | 21,828.00 |  |  | 143,370.00 | 174,873.00
Y1 Actual Total | 15,840.00 | 19,688.40 |  |  | 140,217.26 | 175,766.36
Y1 Actual RC | 7,920.00 | 11,703.66 |  |  | 140,217.26 | 159,840.92
Diff Total | -18% | -46% |  |  | -27% | -29%
Diff RC | -18% | -46% |  |  | -2% | -9%

## Slide 15: TCD
Comments
  Blah…
 | RTD | Coordination | Support | Management | Other | Total
Planned Total |  | 121,840.00 |  |  | 101,152.00 | 222,992.00
Planned RC |  | 81,480.00 |  |  | 75,864.00 | 157,344.00
Y1 Planned Total |  | 60,920.00 |  |  | 50,576.00 | 111,496.00
Y1 Planned RC |  | 40,740.00 |  |  | 37,932.00 | 78,672.00
Y1 Actual Total |  | 47,392.00 |  |  | 26,821.00 | 74,213.00
Y1 Actual RC |  | 31,694.00 |  |  | 26,821.00 | 58,515.00
Diff Total |  | -22% |  |  | -47% | -33%
Diff RC |  | -22% |  |  | -29% | -26%

## Slide 16
Questions?