## Sheet1
Super-B-Factory Cost Estimate (Accelerator) |  |  |  | 2007-04-12
WBS | Item | Number | Replace | EDIA | Technical | M&S
|  | Units | value |  | labor
|  |  | (kEuro) | (mm) | (mm) | (kEuro)
1 | Total Project |  | 126330 | 6853 | 5157 | 296866
1.1 | Project management |  | 0 | 2112 | 96 | 1800
1.1.01 | Technical management | 15 people | 0 | 720 | 12 | 300
1.1.02 | Project physicists | 10 people | 0 | 480 | 12 | 300
1.1.03 | Accelerator physics | 10 people | 0 | 480 | 12 | 300
1.1.04 | Cost accounting and tracking | 5 people | 0 | 240 | 24 | 200
1.1.05 | Database and documentation | 3 people | 0 | 144 | 24 | 100
1.1.06 | Project travel | 100 trips/yr | 0 | 48 | 12 | 600
1.2 | Magnet and support system |  | 25380 | 666 | 1199 | 28965
1.2.01 | Engineering, design, and prototypes | 10 people | 0 | 360 | 120 | 500
1.2.02 | Dipole (0.5 m) removal and refurbish | 144 | 1440 | 5 | 50 | 144
1.2.03 | Dipole (0.5 m) shipping | 144 | 0 | 5 | 5 | 144
1.2.04 | Dipole (0.5 m) installation | 144 | 0 | 5 | 20 | 144
1.2.05 | Dipole (0.5 m) power supplies+cables | 144 | 432 | 2 | 4 | 450
1.2.06 | Dipole (0.5 m) water cooling connection | 144 | 0 | 2 | 12 | 144
1.2.07 | Dipole (0.5 m) supports/ship | 144 | 576 | 2 | 4 | 300
1.2.08 | Dipole (0.5 m) alignment | 144 | 0 | 3 | 6 | 72
1.2.09 | Dipole (0.75 m) construction | 144 | 0 | 3 | 3 | 1440
1.2.10 | Dipole (0.75 m) installation | 144 | 0 | 5 | 20 | 144
1.2.11 | Dipole (0.75 m) power supplies+cables | 144 | 0 | 2 | 4 | 600
1.2.12 | Dipole (0.75 m) water cooling connection | 144 | 0 | 2 | 12 | 144
1.2.13 | Dipole (0.75 m) supports | 144 | 0 | 2 | 4 | 450
1.2.14 | Dipole (0.75 m) alignment | 144 | 0 | 3 | 4 | 72
1.2.15 | Dipole (5.4 m) removal and refurbish | 176 | 2640 | 6 | 60 | 176
1.2.16 | Dipole (5.4 m) shipping | 176 | 0 | 5 | 5 | 352
1.2.17 | Dipole (5.4 m) installation | 176 | 0 | 5 | 20 | 352
1.2.18 | Dipole (5.4 m) power supplies+cables | 176 | 528 | 4 | 8 | 800
1.2.19 | Dipole (5.4 m) water cooling connection | 176 | 0 | 2 | 12 | 176
1.2.20 | Dipole (5.4 m) supports/ship | 176 | 352 | 3 | 6 | 500
1.2.21 | Dipole (5.4 m) alignment | 176 | 0 | 3 | 6 | 88
1.2.22 | Dipole (2 m) removal and refurbish | 4 | 40 | 1 | 1 | 4
1.2.23 | Dipole (2 m) shipping | 4 | 0 | 1 | 1 | 8
1.2.24 | Dipole (2 m) installation | 4 | 0 | 1 | 1 | 8
1.2.25 | Dipole (2 m) power supplies+cables | 4 | 25 | 1 | 2 | 100
1.2.26 | Dipole (2 m) water cooling connection | 4 | 0 | 1 | 1 | 4
1.2.27 | Dipole (2 m) supports/ship | 4 | 8 | 1 | 1 | 20
1.2.28 | Dipole (2 m) alignment | 4 | 0 | 1 | 1 | 2
1.2.29 | Quadrupole (0.43 m) removal & refurbish | 341 | 3410 | 5 | 50 | 341
1.2.30 | Quadrupole (0.43 m) shipping | 341 | 0 | 5 | 10 | 500
1.2.31 | Quadrupole (0.43 m) installation | 341 | 0 | 5 | 20 | 682
1.2.32 | Quadrupole (0.43 m) PS+cables | 341 | 1023 | 5 | 10 | 1000
1.2.33 | Quadrupole (0.43 m) water cooling conn | 341 | 0 | 2 | 12 | 341
1.2.34 | Quadrupole (0.43 m) supports/ship | 341 | 288 | 4 | 8 | 700
1.2.35 | Quadrupole (0.43 m) alignment | 341 | 0 | 3 | 6 | 172
1.2.36 | Quadrupole (0.5 m) removal & refurbish | 70 | 700 | 5 | 50 | 70
1.2.37 | Quadrupole (0.5 m) shipping | 70 | 0 | 2 | 4 | 70
1.2.38 | Quadrupole (0.5 m) installation | 70 | 0 | 6 | 40 | 140
1.2.39 | Quadrupole (0.5 m) PS+cables | 70 | 280 | 5 | 10 | 210
1.2.40 | Quadrupole (0.5 m) water cooling conn | 70 | 0 | 2 | 6 | 70
1.2.41 | Quadrupole (0.5 m) supports/ship | 70 | 70 | 4 | 8 | 150
1.2.42 | Quadrupole (0.5 m) alignment | 70 | 0 | 2 | 5 | 70
1.2.43 | Quadrupole (0.56 m) removal & refurbish | 287 | 2870 | 5 | 50 | 600
1.2.44 | Quadrupole (0.56 m) shipping | 287 | 0 | 4 | 8 | 400
1.2.45 | Quadrupole (0.56 m) installation | 287 | 0 | 8 | 60 | 287
1.2.46 | Quadrupole (0.56 m) PS+cables | 287 | 861 | 5 | 10 | 800
1.2.47 | Quadrupole (0.56 m) water cooling conn | 287 | 0 | 4 | 8 | 287
1.2.48 | Quadrupole (0.56 m) supports/ship | 287 | 287 | 4 | 8 | 400
1.2.49 | Quadrupole (0.56 m) alignment | 287 | 0 | 4 | 8 | 150
1.2.50 | Quadrupole (0.73 m) removal & refurbish | 138 | 1380 | 5 | 40 | 200
1.2.51 | Quadrupole (0.73 m) shipping | 138 | 0 | 3 | 6 | 250
1.2.52 | Quadrupole (0.73 m) installation | 138 | 0 | 6 | 40 | 138
1.2.53 | Quadrupole (0.73 m) PS+cables | 138 | 414 | 4 | 9 | 400
1.2.54 | Quadrupole (0.73 m) water cooling conn | 138 | 0 | 4 | 8 | 138
1.2.55 | Quadrupole (0.73 m) supports/ship | 138 | 81 | 4 | 8 | 300
1.2.56 | Quadrupole (0.73 m) alignment | 138 | 0 | 4 | 8 | 138
1.2.57 | Sextupole (0.25 m) removal & refurbish | 452 | 3400 | 5 | 40 | 376
1.2.58 | Sextupole (0.25 m) shipping | 452 | 0 | 3 | 6 | 452
1.2.59 | Sextupole (0.25 m) installation | 452 | 0 | 6 | 40 | 452
1.2.60 | Sextupole (0.25 m) PS+cables | 452 | 900 | 8 | 16 | 1000
1.2.61 | Sextupole (0.25 m) water cooling conn | 452 | 0 | 4 | 7 | 350
1.2.62 | Sextupole (0.25 m) supports/ship | 452 | 188 | 4 | 7 | 500
1.2.63 | Sextupole (0.25 m) alignment | 452 | 0 | 4 | 7 | 226
1.2.64 | Sextupole (0.6 m) removal & refurbish | 8 | 32 | 2 | 8 | 75
1.2.65 | Sextupole (0.6 m) shipping | 8 | 0 | 0 | 0 | 0
1.2.66 | Sextupole (0.6 m) installation | 8 | 0 | 2 | 3 | 16
1.2.67 | Sextupole (0.6 m) PS+cables | 8 | 35 | 2 | 4 | 50
1.2.68 | Sextupole (0.6 m) water cooling conn | 8 | 0 | 1 | 2 | 8
1.2.69 | Sextupole (0.6 m) supports/ship | 8 | 0 | 1 | 2 | 20
1.2.70 | Sextupole (0.6 m) alignment | 8 | 0 | 1 | 2 | 4
1.2.71 | Corrector (0.6 m) removal & refurbish | 600 | 900 | 5 | 10 | 400
1.2.72 | Corrector (0.3m) construction | 236 | 0 | 4 | 8 | 100
1.2.73 | Corrector (0.6 m) shipping | 836 | 0 | 0 | 0 | 100
1.2.74 | Corrector (0.6 m) installation | 836 | 0 | 2 | 6 | 418
1.2.75 | Corrector (0.6 m) power supplies+cables | 836 | 500 | 2 | 6 | 700
1.2.76 | Corrector (0.6 m) water cooling conn | 836 | 0 | 2 | 6 | 10
1.2.77 | Corrector (0.6 m) supports/ship | 836 | 100 | 2 | 6 | 836
1.2.78 | Corrector (0.6 m) alignment | 836 | 0 | 2 | 6 | 200
1.2.79 | Corrector (0.3m) construction | 236 | 0 | 4 | 8 | 236
1.2.80 | Wiggler (1 m) construction | 200 | 0 | 6 | 12 | 3000
1.2.81 | Wiggler (1 m) installation | 200 | 0 | 2 | 6 | 200
1.2.82 | Wiggler (1 m) power supplies+cables | 200 | 0 | 3 | 6 | 600
1.2.83 | Wiggler (1 m) water cooling conn | 200 | 0 | 1 | 2 | 400
1.2.84 | Wiggler (1 m) supports/ship | 200 | 0 | 2 | 6 | 400
1.2.85 | Wiggler (1 m) alignment | 200 | 0 | 2 | 6 | 200
1.2.86 | Pol dipole (2 m) construction | 8 | 0 | 4 | 8 | 300
1.2.87 | Pol dipole (2 m) installation | 8 | 0 | 2 | 4 | 50
1.2.88 | Pol dipole (2 m) power supplies+cables | 8 | 0 | 4 | 8 | 150
1.2.89 | Pol dipole (2 m) water cooling connection | 8 | 0 | 1 | 2 | 20
1.2.90 | Pol dipole (2 m) supports | 8 | 0 | 2 | 4 | 64
1.2.91 | Pol dipole (2 m) alignment | 8 | 0 | 1 | 2 | 10
1.2.92 | IR skew quad (0.5 m) refurb & ship | 24 | 120 | 2 | 4 | 30
1.2.93 | IR skew quad (0.5 m) installation | 24 | 0 | 1 | 2 | 15
1.2.94 | IR skew quad (0.5 m) power supply/cable | 24 | 0 | 2 | 4 | 76
1.2.95 | IR skew quad (0.5 m) water cooling conn | 24 | 0 | 1 | 2 | 24
1.2.96 | IR skew quad (0.5 m) supports | 24 | 0 | 2 | 4 | 50
1.2.97 | IR skew quad (0.5 m) alignment | 24 | 0 | 1 | 2 | 5
1.2.98 | Injection kickers refurb & installation | 4 | 1000 | 4 | 8 | 400
1.2.99 | Abort kicker refurb &installation | 2 | 500 | 2 | 4 | 100
1.3 | Vacuum system |  | 14200 | 620 | 520 | 27600
1.3.01 | Engineering, design, and prototypes | 15 people | 0 | 480 | 240 | 750
1.3.02 | Vacuum extrusion | 2600 m | 0 | 3 | 6 | 1300
1.3.03 | Vacuum chamber machining | 2600 m | 0 | 24 | 48 | 5200
1.3.04 | Vacuum chamber assembly | 2600 m | 0 | 24 | 48 | 5200
1.3.05 | Vacuum chamber distributed pumps | 2600 m | 0 | 12 | 24 | 4600
1.3.06 | Vacuum chamber lumped pumps | 700 units | 2100 | 12 | 24 | 1400
1.3.07 | Vacuum chamber controls | 2600 m | 2600 | 12 | 24 | 1000
1.3.08 | Vacuum chamber installation | 4600 m | 0 | 12 | 24 | 2300
1.3.09 | Vacuum chamber refurbish and remove | 2000 m | 9500 | 5 | 10 | 1000
1.3.10 | Vacuum chamber shipping | 2000 m | 0 | 5 | 10 | 600
1.3.11 | Polarization vacuum chambers | 100 m | 0 | 8 | 16 | 1000
1.3.12 | Beam abort chambers | 2 units | 0 | 5 | 10 | 750
1.3.13 | IR high power vacuum chambers misc | 8 units | 0 | 8 | 16 | 1500
1.3.14 | ECI electrodes and controls | 500 units | 0 | 10 | 20 | 1000
1.4 | RF system |  | 60000 | 272 | 304 | 22300
1.4.01 | Engineering, design, and prototypes | 10 people | 0 | 240 | 240 | 500
1.4.02 | RF stations refurbish & remove | 15 stations | 60000 | 12 | 24 | 500
1.4.03 | RF station shipping | 15 stations | 0 | 2 | 4 | 3000
1.4.04 | RF station install | 15 stations | 0 | 12 | 24 | 15000
1.4.05 | RF station new controls | 15 stations | 0 | 3 | 6 | 3000
1.4.06 | RF station HVPS pads | 15 stations | 0 | 3 | 6 | 300
1.5 | Interaction region |  | 0 | 370 | 478 | 10950
1.5.01 | Engineering, design, and prototypes | 10 people | 0 | 240 | 240 | 500
1.5.02 | IP Be vacuum chamber | 2 units | 0 | 6 | 12 | 250
1.5.03 | IP Be vacuum bellows | 3 units | 0 | 2 | 4 | 200
1.5.04 | QD0H quadrupole (PM, 1.4 T, 0.46 m) | 2 units | 0 | 4 | 8 | 450
1.5.05 | QD0H quadrupole vacuum chamber | 2 units | 0 | 4 | 4 | 350
1.5.06 | QF1L quadrupole (SC, 0.4 m) | 2 units | 0 | 6 | 12 | 600
1.5.07 | QF1L quadrupole vacuum chamber | 2 units | 0 | 4 | 4 | 300
1.5.08 | Magic vacuum flange and remote act. | 2 units | 0 | 6 | 12 | 200
1.5.09 | Supports for QD0H and QF1 | 2 units | 0 | 3 | 6 | 250
1.5.10 | B00L magnet (0.4 m) | 2 units | 0 | 4 | 8 | 300
1.5.11 | QD0H (0.29 m) | 2 units | 0 | 3 | 6 | 400
1.5.12 | B00H (0.4 m) | 2 units | 0 | 3 | 6 | 250
1.5.13 | QF1H (0.4m) | 2 units | 0 | 3 | 6 | 400
1.5.14 | B0L (2 m) | 2 units | 0 | 3 | 6 | 300
1.5.15 | B0H (2 m) | 2 units | 0 | 3 | 6 | 300
1.5.16 | Forward support raft | 1 unit | 0 | 5 | 5 | 300
1.5.17 | Backward support raft | 1 unit | 0 | 5 | 5 | 300
1.5.18 | Cryogenic refrigerator | 1 unit | 0 | 3 | 6 | 700
1.5.19 | Croygenic distribution piping | 1 unit | 0 | 3 | 6 | 500
1.5.20 | Cryogenic controls | 1 unit | 0 | 3 | 4 | 300
1.5.21 | LN2 storage and distribution | 1 unit | 0 | 3 | 6 | 300
1.5.22 | H2O Cooling lines for IR components | 100 m | 0 | 3 | 6 | 250
1.5.23 | Water chillers for IR components | 4 units | 0 | 2 | 4 | 250
1.5.24 | Vacuum pump holding | 12 units | 0 | 2 | 3 | 200
1.5.25 | Vacuum holding controls and PS | 12 units | 0 | 2 | 3 | 100
1.5.26 | Vacuum pump TSPs | 20 units | 0 | 3 | 6 | 150
1.5.27 | Vacuum pump TSP controls and PS | 20 units | 0 | 3 | 6 | 150
1.5.28 | H2O temperature regulation | 10 units | 0 | 3 | 6 | 300
1.5.29 | Installation of IR components | +/- 10 m | 0 | 12 | 36 | 1500
1.5.30 | Alignment of IR components | +/- 10 m | 0 | 12 | 12 | 300
1.5.31 | Active vibration suppression for quads | 8 units | 0 | 12 | 24 | 300
1.6 | Controls, Diagnostics, Feedback |  | 8750 | 963 | 648 | 12951
1.6.01 | Engineering, design, and prototypes | 15 people | 0 | 480 | 240 | 600
1.6.02 | Beam position monitor electronics | 1000 units | 0 | 24 | 48 | 2000
1.6.03 | Beam position monitor cables | 20000 m | 0 | 24 | 48 | 2000
1.6.04 | Master control computer | 2 each | 0 | 2 | 4 | 200
1.6.05 | Local computers | 14 each | 0 | 5 | 10 | 200
1.6.06 | Network and routers | 14 each | 0 | 5 | 10 | 400
1.6.07 | Control software | 6 people | 0 | 288 | 24 | 200
1.6.08 | Interface electronics | 500 units | 0 | 24 | 48 | 500
1.6.09 | Synchrotron light monitors (xray) | 2 units | 1000 | 6 | 12 | 1500
1.6.10 | Data storage | 1000 Gbit | 0 | 2 | 4 | 20
1.6.11 | Long fdbk kicker-electronics refurbish | 6 units | 2000 | 12 | 24 | 500
1.6.12 | Long fdbk shipping | 6 units | 0 | 1 | 1 | 100
1.6.13 | Trans fdbk kicker-electronic refurbish | 6 units | 2000 | 12 | 24 | 500
1.6.14 | Trans fdbk shipping | 6 units | 0 | 1 | 1 | 100
1.6.15 | Installation BxB feedback systems | 8 units | 0 | 6 | 12 | 150
1.6.16 | ECI monitors | 4 units | 0 | 6 | 12 | 50
1.6.17 | Bunch current monitors refurbish | 2 units | 300 | 2 | 4 | 20
1.6.18 | Bunch current monitors ship | 2 units | 0 | 1 | 1 | 20
1.6.19 | Bunch current monitors install | 2 units | 0 | 4 | 8 | 100
1.6.20 | Bunch length monitors refurbish | 2 units | 600 | 1 | 2 | 20
1.6.21 | Bunch length monitors ship | 2 units | 0 | 1 | 2 | 10
1.6.22 | Bunch length monitors install | 2 units | 0 | 3 | 6 | 80
1.6.23 | Luminosity monitor refurbish | 1 unit | 200 | 1 | 2 | 20
1.6.24 | Luminosity monitor ship | 1 unit | 0 | 1 | 2 | 10
1.6.25 | Luminosity monitor install | 1 unit | 0 | 3 | 6 | 100
1.6.26 | Polarization monitor | 1 unit | 0 | 12 | 24 | 1000
1.6.27 | RF master oscillator | 1 unit | 0 | 3 | 6 | 50
1.6.28 | Timing generator | 1 unit | 0 | 3 | 6 | 50
1.6.29 | Bunch injection controller | 1 unit | 0 | 3 | 6 | 50
1.6.30 | Loss monitors refurbish | 300 units | 900 | 1 | 2 | 100
1.6.31 | Loss monitors ship | 300 units | 0 | 1 | 1 | 150
1.6.32 | Loss monitors install | 300 units | 0 | 3 | 6 | 200
1.6.33 | IR background detectors refurbish | 30 units | 250 | 1 | 1 | 25
1.6.34 | IR background detectors ship | 30 units | 0 | 1 | 1 | 50
1.6.35 | IR background detectors install | 30 units | 0 | 3 | 6 | 80
1.6.36 | Fast IP position fdbk refurbish | 6 units | 200 | 1 | 2 | 10
1.6.37 | Fast IP position fdbk ship | 6 units | 0 | 1 | 2 | 20
1.6.38 | Fast IP position fdbk install | 6 units | 0 | 4 | 8 | 80
1.6.39 | Temp sensors for ring components | 2000 units | 1000 | 5 | 10 | 666
1.6.40 | Polarization controls | 1 unit | 300 | 5 | 10 | 1000
1.6.41 | IP HOM monitors | 1 unit | 0 | 1 | 2 | 20
1.7 | Injection and transport systems |  | 18000 | 426 | 252 | 86600
1.7.01 | Engineering, design, and prototypes | 10 people | 0 | 360 | 120 | 600
1.7.02 | Injection e- gun |  | 2000 | 12 | 24 | 2000
1.7.03 | Positron target and capture region |  | 3000 | 12 | 24 | 2000
1.7.04 | 6 GeV Linac |  | 5000 | 12 | 24 | 50000
1.7.05 | 2 x 1 GeV damping ring |  | 3000 | 12 | 24 | 20000
1.7.06 | Two injection transport lines |  | 3000 | 12 | 24 | 10000
1.7.07 | Polarization manipulation for injection |  | 2000 | 6 | 12 | 2000
1.8 | Site Utilities |  | 0 | 820 | 1040 | 31700
1.8.01 | Engineering, design, and prototypes | 10 people | 0 | 360 | 120 | 500
1.8.02 | Cooling towers | 3x10 MW ea | 0 | 30 | 60 | 6000
1.8.03 | Water pump pads | 3 each | 0 | 12 | 24 | 2000
1.8.04 | Water pumps | 20 pumps | 0 | 12 | 24 | 1000
1.8.05 | Water piping | 10000 m | 0 | 200 | 400 | 10000
1.8.06 | Power transformers | 3x10 MW ea | 0 | 50 | 100 | 3000
1.8.07 | Stepdown transformers | 12 at 500 KW ea | 0 | 50 | 100 | 1200
1.8.08 | Power AC wiring | 10 km | 0 | 100 | 200 | 5000
1.8.09 | Air conditioning for support halls | 6 buildings | 0 | 6 | 12 | 3000
1.9 | Tunnel and Support Buildings |  | 0 | 604 | 620 | 74000
1.9.01 | Engineering, design, and prototypes | 10 people | 0 | 360 | 120 | 500
1.9.02 | Ring tunnel boring | 2300 m | 0 | 150 | 300 | 35000
1.9.03 | Ring tunnel equipment alcoves | 6 ea mid-arc | 0 | 12 | 25 | 3000
1.9.04 | Ring cable and RF shafts | 12 each | 0 | 12 | 25 | 3000
1.9.05 | Straight equipment halls | 3x350 sq-m | 0 | 15 | 40 | 15000
1.9.06 | Interaction region hall | 500 sq-m | 0 | 25 | 50 | 10000
1.9.07 | Linac tunnel and beam transport lines | 500 m | 0 | 30 | 60 | 7500
1.9.08 | Linac technical support gallery | 2000 sq-m | 0 | 30 | 60 | 7000