## Slide 1: Project Status
C. Loomis (CNRS/LAL)
Project Management Board
2 October 2012

## Slide 2: Contents
Final Review Report
EC Administrative Procedures
Reimbursement

## Slide 3: Final Review Report
Summary
  Received end of August 2012
  Feedback follows closely the informal comments after review
  Very positive port with overall “good” rating
  Only issue related to limited dissemination
Formal Responses
  No comments received from partners
  Thus no formal “observations” on report sent to EC

## Slide 4: EC Administrative Procedures
Review
  Completed with report received
  All deliverables and milestones accepted by reviewers
Reimbursement
  Final report completed and uploaded
  Forms C: Information for all partners; initial EC evaluation OK
  Blocking point: missing CFS for SixSq (ETA: ~5 Oct.)
Remaining Tasks
  Quick reaction on any problems identified in EC financial evaluation
  Signatures of Forms C once we have approval from EC

## Slide 5: Reimbursement
Timeline
  Reimbursements will be received within 45 days of EC approval
  Expect quick approval after the SixSq CFS is available
  EC must have signed Forms C before they release payment
  Will be redistributed to partners ASAP after reception by CNRS
Reimbursement Scenarios
  Receive <2.3 M€ or receive exactly 2.3 M€.
  PMB must decide/approve the reimbursement procedures

## Slide 6: Scenario 1 (Less likely)
Description
  EC reimburses costs based on individual partner declarations respecting maximum partner reimbursements in GA
  Total reimbursement will be less than 2.3 M€ because of partner under-spending
Procedure
  Partner reimbursement defined by maximum value calculated by EC based on provided financial information from partners
  Each partner receives balance based on the EC calculated value

## Slide 7: Scenario 2 (More likely)
Description
  EC reimburses 2.3 M€ (maximum permitted by GA) based on combined justified costs of all partners
  Possible because of overspending by several partners
Proposed Procedure
  First, reimburse each partner to EC reimbursement value or to maximum reimbursement permitted by GA, whichever is less.
  Second, allocate remaining money to partners that have exceeded their maximum reimbursement, in proportion to the excess declared costs.