## Slide 1: Readout chain sub-system for QUBIC
For Technological Demonstrator (T.D.)
And
For Final Instrument (F.I.)

## Slide 2: QUBIC detection chain
1 focal plane = 4 wafers of 256 TESs @300mK
  Readout: Time Domain Multiplexing 128:1
  128 SQUIDs @ 1K + 1 ASIC @ 40 K for ⅛ focal plane
  Specifications:
    NEP < 5.10-17W.Hz-0.5
    τ < 10ms
2 focal planes: 150GHz and 220GHz

## Slide 3: Sub-systems
Readout chain
SQUIDs
ASICs
Warm electronics
Wiring
Acquisition software
SQUIDs
PCB
Mechanics
ASICs
PCB
Mechanics
Wires
Inteconnexion box
Interconnexion PCB
Mechanics
Connectors

## Slide 4: SQUIDs
SQUIDs custom design made by STAR Cryoelectronics
  SQ600
Status:
  SQUIDS in hand: 2 wafers of 2000 SQUIDs each + 1 new wafer received with improved performances
  Warm tests and selection done
  PCBs production: received
    Defect to be studied

## Slide 5: Detection chain: ASIC
First version: fully functionnal
  Current source at warm T
Second version: received and tested
  Improved performances
  Current source in the ASIC
  Baseline for TD
  PCB being integrated
ASIC SiGe
SQUIDs (StarCryoelectronics)
TESs

## Slide 6: Warm electronics
Amplifier (APC): SR560
  Home made amplifier also possible
FPGA board (IRAP)
Status:
  2x SR 560 available for TD
  Home made amplifier being realised
  FPGA board available and functional
    With full acquisition speed and FLL in FPGA
    Check with IRAP availability of 2nd FPGA board

## Slide 7: Wiring
Content:
  Superconducting NbTi below 4K, Cu or Ph-Br wires above 4K
  Inteconnexion PCB
  Connectors
Status:
  Path defined in the cryostat, length known
  Cold interfaces fixed
  Interconnexion PCB under integration
  Warm interface to be designed (connectors flange)
  Detection chain wires: to be ordered to Universal Cryogenics
  Connectors to be ordered

## Slide 8: Acquisition software
QUBIC Studio (IRAP):
  Overall control of the experiment: TESs, RF switches, PT, thermometers, heaters
  Status:
    In use for detector characterisation
    Connection with other subsystem to be done
ASIC parameterising
Acquisition/Demultiplexing/Visualisation

## Slide 9: Detection chain: ¼ focal plane integration
Cryostat wiring for 128 TESs readout

## Slide 10: P41 characterisation
Excellent homogeneity: ±10%
QUBIC TESs: P41 @ T=350mK
(Camille Perbost)
P-V
I-V

## Slide 11: P41 characterisation

## Slide 12: P41 characterisation
Preliminary NEP distribution at 350mK:
  Requirement: NEP < 5.10-17 W.Hz-0.5

## Slide 13: First noise measurements
T=350mK, Vbias=1µV
Noise level fully understand
  Aliasing
  Nyquist inductors to be reduce the aliasing
10-16 W.Hz-0.5

## Slide 14: Nyquist inductors
32 Nb inductors (10µH) available from INFN Pisa
  Integration on a single SQUID PCB under study
  Tests to be done
Quotation available from STAR Cryoelectronics: ~20k€ for 2 wafers, 350 inductors per wafer
  Gradiometer version
For TD: no Nyquist inductors will be used at the beginning in order to save money

## Slide 15: Interfaces with other sub-systems
Mechanical interfaces:
  Wiring inside the cryostat, ASIC and interconnexion boxes frozen
  Warm connector part to be designed asap
  Localisation of warm electronics and FPGAs to be defined
Other interfaces:
  Acquisition software to be interfaced with switches, HWP rotating mechanism, mount

## Slide 16: Test, Delivery, Assembly, Calibration Operations
SQUID boards tests before delivery:
  In the dilution fridge
  Criterion: number of working SQUIDs, ∆V
ASIC boards tests before delivery:
  Warm functional test
  Criterion: noise level,
Wires tests before delivery:
  Tests by Universal Cryogenics
Assembly Operations in APC:
  SQUIDs tests: needs T<8K so no tests possible during integration
  ASIC functional test could be done after integration at room T

## Slide 17: Manpower
Name and responsibility | % FTE 2016 | % FTE 2017 | % FTE 2018
Fabrice Voisin | 60 | 60 | 60
Damien Prêle | 30 | 30 | 30
Tanguy Decourcelle | 30 | 0 | 0
Michel Piat | 20 | 20 | 20
TOTAL FTE | 1.4 | 1.1 | 1.1

## Slide 18: Risks analysis
Late delivery of wires or connectors
  Possibility to use wires from APC dilution cryostat but in this case we will have no test bed for SQUIDs and TESs
Degraded noise performances
  10-16 W.sqrt(Hz) demonstrated, OK for TD

## Slide 20: ATRIUM and Documentation
List (with reference ATRIUM-xxxxx) the technical documents related to your sub-system already in the ATRIUM repository.
Are these documents definitive ? Should we update the status of the document from “in project” to “validated” ?
Missing documents from other sub-systems ?
Future documents to be downloaded by you ?

## Slide 21: Status of the sub-system : blocking points and schedule
  What is the status of the sub-system ?
    Design/manufacturing (home made/industry)/assembly/tests ?
    When is this phase supposed to be finished ?
  If you are still designing the sub-system:
    Which inputs / specifications / requirements, needed to finish the detailed design of your sub-systems, are not yet delivered ?
      For D.T.
      For F.I.
    Which other working group should deliver these inputs (see annex 1 for list of main WP) ?
      For D.T.
      For F.I.
  What time is still needed in order to (for D.T.) – assume that the above inputs are provided if needed - :
    Finish the whole detailed design of D.T. ?
    Manufacture the sub-system ?
    Test the sub-system in your premises before delivery to APC / ROMA ?
  Idem for F.I.
  Do you think you can comply to the target schedule (see annex 2) ?

## Slide 22: Status of the sub-system : blocking points and schedule
  What is the status of the sub-system ?
    Design/manufacturing (home made/industry)/assembly/tests ?
    When is this phase supposed to be finished ?
  If you are still designing the sub-system:
    Which inputs / specifications / requirements, needed to finish the detailed design of your sub-systems, are not yet delivered ?
      For D.T.
      For F.I.
    Which other working group should deliver these inputs (see annex 1 for list of main WP) ?
      For D.T.
      For F.I.
  What time is still needed in order to (for D.T.) – assume that the above inputs are provided if needed - :
    Finish the whole detailed design of D.T. ?
    Manufacture the sub-system ?
    Test the sub-system in your premises before delivery to APC / ROMA ?
  Idem for F.I.
  Do you think you can comply to the target schedule (see annex 2) ?

## Slide 23: Budget (excluding salaries)for T.D. + F.I.
 | Spendings (type and amount) | Funding (source and amount) | Status of funding (granted / under examination)
2016 |  |  | 
2017 |  |  | 
2018 |  |  | 

## Slide 24: Annex 1: list of main-sub-system and WP leaders

## Slide 25: Annex 2 : Target schedule

## Slide 26: Annex 3: examples of possibly needed major tools or utilities
High voltage (380 V) power
Cold water
Liquid or gaseous N2 / He
Compressed air
Clean air laminar flow / clean room / conditioned air
Assembly Hall
Mechanical workshop
IT network or Wifi
Chemicals
ESD equipments
Crane or heavy handling systems
Metrology systems (Faro, MMT, Laser…)
VNA
Calibration source
Mount (or fake)
Vacuum systems (including degassing)
Acquisition systems
Computers / data acq. systems
Electrical test with probe station

## Slide 27: P41 characterisation
Characterisation of TESs: a lots of data!
QUBIC TESs
G~84pW/K
NEPphonon~3.10-17W.Hz-0.5

## Slide 28: P41 characterisation
23 pixel TESs @ 200mK [Martino 2012]
QUBIC TESs: P41 @ T=350mK
(Camille Perbost)
Excellent homogeneity: ±10%