## Slide 1: Integration Plan for the TD @APC
For Technological Demonstrator (T.D.)
And
For Final Instrument (F.I.)

## Slide 2: QUBIC Technological Demonstrator Integration Plan
First draft document distributed by Olivier on 21st September
Content:
  Integration
    Strategy
    Procedure
    Implementation
  Test plan
    At sub-system level
    Before integration
    After integration
  Calibration

## Slide 3: 1K box sub-system
  The mains components of the 1K box are :
    The 2 focal planes and their supports
    The mirrors M1 and M2 and their supports
    The 300mK passageway and links
    The filters : 300mK filters, dichroic filter, cold stop filter.
    And the 1K box itself
ONA focal plane
OFA focal plane
300mK passageway
Mirror M2
Mirror M1
Cold stop filter
Dichroic filter
Upper support frame
1K box
1K box equipped

## Slide 4: 1K box - Assembly Operations
1st step : assembly the 1K box structure
1 – first part : support belt
2 – Mounting of the support plate for M2
3 – Mounting of the Support
side plate for OFA focal plane

## Slide 5: 1K box - Assembly Operations
1st step : assembly the 1K box structure
5 – Mounting of the support
plate ONA-M1
6 – Mounting of the front arch
4 – Mounting of the other
support side plate
1K box structure

## Slide 6: 1K box - Assembly Operations
2nd step : mounting and alignment of the focal planes
ONA-FP : ONA focal plane
OFA-FP : OFA focal plane
7 – Mounting of the support of the
mirror M1
The support is assumed to be « aligned »
(with tools – to be defined)
8 – Mounting of the ONA-FP and its support
Alignment of the ONA-FP with mirror M1
(with Tools - to be defined)
9 – Mounting of the OFA-FP and its support
Alignment of the OFA-FP with ONA-FP
(with Tools - to be defined)

## Slide 7: 1K box - Assembly Operations
ONA-FP : ONA focal plane
OFA-FP : OFA focal plane
3rd step : mounting and alignment of the mirror M2
10 – Dismounting the ONA-FP
and the OFA-FP
11 – Mounting the support of the mirror M2
Alignment of the mirror M2 with
the mirror M1 (with tools – To be defined)
12 – (Re)Mounting the ONA-FP
and the OFA-FP

## Slide 8: 1K box - Assembly Operations
4th step : mounting and alignment of the dichroic filter
ONA-FP : ONA focal plane
OFA-FP : OFA focal plane
13 – Mounting the Dichroic filter
Alignment of its support with
the OFA-FP (with tools – to be defined)
14 – Dismounting the Dichroic filter, the
ONA-FP, the OFA-FP, the mirrors M1
and M2

## Slide 9: 1K box - Assembly Operations
5th step : mounting of the cold stop
15 – Mounting the cold stop
16 – (Re)mounting the mirrors M1 and M2
17 – (Re)mounting the dichroic filter

## Slide 10: 1K box - Assembly Operations
6th step : mounting of the 300mK passageway and
19 – (Re)mounting of the ONA-FP and
the OFA-FP
ONA-FP : ONA focal plane
OFA-FP : OFA focal plane
18 – Mounting of the 300mK passageway

## Slide 11: 1K box - Assembly Operations
7th step : mounting of the « top lid » and the upper support frame with the 6 pillars
20 – mounting the top lid
21 – Mounting the upper support frame with
the 6 pillars (with tools – to be defined)

## Slide 12: 1K box - Assembly Operations
22 – Dismounting the ONA-FP and
the OFA-FP for wiring
23 – (Re)mounting the ONA-FP and
the OFA-FP after wiring
8th step : wiring of the focal plan
ONA-FP : ONA focal plane
OFA-FP : OFA focal plane

## Slide 13: 1K box - Assembly Operations
9th step : mounting the lids and the covers
24 – Mounting the rear covers
25 – Mounting the remaining lids
1K box equipped

## Slide 14: Comments
1K integration needs to be optimised
  Reduction of mounting/dismounting procedures
  Laser alignement procedure to be added (in configuration 16?)

## Slide 15: Status of the sub-system : blocking points and schedule
  Status : under definition
    Integration of FP is missing (at APC clean room)
    Intgration of instrument: in the integration hall of APC
  Design:
    Tools needs to be designed (see Claude presentation)
  What time is still needed in order to (for D.T.):
    Finish the whole detailed design of D.T. ?
    Manufacture the sub-system ?
    Test the sub-system in your premises before delivery to APC / ROMA ?
  Idem for F.I.
    Same tools for F.I.!
  Do you think you can comply to the target schedule (see annex 2) ? Under study

## Slide 16: Interfaces with other sub-systems
APC integration hall is being prepared to receive QUBIC:
  Closed loop cold water line about to be implemented
  All other needed instrumentation needed (see Silvia’s talk) are available

## Slide 17: Tests and calibration
See the document : QUBIC Technological Demonstrator Integration Plan

## Slide 18: Tests and calibration

## Slide 19: Manpower
Name and responsibility | % FTE 2016 | % FTE 2017 | % FTE 2018
Claude Chapron | 50 | 50 | 50
Michel Piat | 10 | 10 | 10
Damien Prêle | 10 | 10 | 10
Fabrice Voisin | 10 | 10 | 10
+LAL, IRAP, Roma, Milano, Maynooth, Manchester… |  |  | 
TOTAL FTE |  |  | 

## Slide 21: ATRIUM and Documentation
List (with reference ATRIUM-xxxxx) the technical documents related to your sub-system already in the ATRIUM repository.
Are these documents definitive ? Should we update the status of the document from “in project” to “validated” ?
Missing documents from other sub-systems ?
Future documents to be downloaded by you ?

## Slide 22: Last news, program for late 2016 and 2017 and other useful information

## Slide 23: Budget (excluding salaries)for T.D. + F.I.
 | Spendings (type and amount) | Funding (source and amount) | Status of funding (granted / under examination)
2016 |  |  | 
2017 |  |  | 
2018 |  |  | 

## Slide 24: Risks analysis
List up to three major risks that can impact performances, schedule, costs for the delivery of your sub-systems.
Describe strategies dedicated to mitigate the probability of occurrence or the consequence of the risks

## Slide 25: Annex 1: list of main-sub-system and WP leaders

## Slide 26: Annex 2 : Target schedule

## Slide 27: Annex 3: examples of possibly needed major tools or utilities
High voltage (380 V) power
Cold water
Liquid or gaseous N2 / He
Compressed air
Clean air laminar flow / clean room / conditioned air
Assembly Hall
Mechanical workshop
IT network or Wifi
Chemicals
ESD equipments
Crane or heavy handling systems
Metrology systems (Faro, MMT, Laser…)
VNA
Calibration source
Mount (or fake)
Vacuum systems (including degassing)
Acquisition systems
Computers / data acq. systems
Electrical test with probe station