## WBS
| WBS PERLE |  |  | PM_PERLE_20201706
ATRIUM xxx
W. Kaabi
C.Vallerand
2020-06-17
Authors :
Contributors : | WBS Managers
Approbators : | A. Stocchi, M. Klein, S. Bousson, W. Kaabi, Management Board
WBS | WBS Name | Institution | WBS Manager | Task Manager | % progress
1 | Project Management
1.0 | Project charter => Initial Scope, PBSv0 (level 1-2), WBSv0 (level 1-2), Organigram…, initial schedule, budget estimate
1.1 | Project management Milestones
1.1.1 | CDR
1.1.2 | Project Management plan
Integration management plan
Scope management plan => PBS, WBS
Cost management plan
Schedule management plan => Duration WBS, gantt
Quality management plan
Requirements management plan
Communication management plan
Risk management plan
Stakeholder management plan
1.1.3 | TDR
1.1.4 | PERLE final footprint
1.1.5 | Injection line installation and tests
1.1.6 | PERLE @ 250 MeV
1.1.7 | PERLE @ 500 MeV
1.1.8 | Experimentation with PERLE
1.2 | Meetings & Reviews
1.3 | ASN Procedure
2. | Accelerator design
2.1 | Lattice and Optics | JLAB-IJCLab
2.1.1 | Linear lattice optimization Initial magnet specs
2.1.2 | Momentum acceptance and longitudinal match
2.1.3 | Correction of nonlinear aberrations with multipole magnets
2.1.4 | Repository and data base with version control
2.2 | Beam Dynamics | JLAB-IJCLab
2.2.1 | Start-to-End simulation with CSR & micro-bunching
2.2.2 | BBU studies
2.2.3 | Space-charge studies at injection
2.2.4 | Multi-particle tracking studies, error effects and halo formation
2.2.5 | Impedance analysis and wakefield effect mitigation
2.2 | Fractional Arc Lattice Design
2.3 | Single Pass Lattice Design
2.4 | Six Pass Lattice Design
3. | Electron source and injection
3.1 | ALICE gun installation and commissioning with GaAs photocathodes | IJCLab
3.1.1 | Inspection of delivered from STFC components
3.1.2 | Design of the test beam line
3.1.3 | Design and procurement of missing and additional components
3.1.4 | Preparation of SF6, power and water infrostrucuture
3.1.5 | Prepartaion of dust free area for gun assembly
3.1.6 | Assembling of the High Voltage power supply and the ALICE gun
3.1.7 | High voltage conditioning of the gun
3.1.8 | GaAs photocathode activation
3.1.9 | Beam commissioning of the gun
3.2 | Photo-injector Laser system for unpolarised regime | IJCLab
3.3 | Cathode delivery | STFC
3.3.1 | GaAs Photocathode delivery | STFC
3.4 | Buncher | IJCLab
3.4.1 | Buncher Cavity | IJCLab
3.5 | Booster
3.5.1 | Booster cavities
3.5.2 | Cryostat
3.6 | Merger
3.6.1 | Physical design | IJCLab + UoL + STFC
3.6.2 | Mechanical design | IJCLab
3.6.3 | Manufacturing and Procurement | IJCLab
3.6.3.1 | Magnets | IJCLab + BINP
3.6.3.2 | Collimators
3.6.3.3 | Vacuum chambers | IJCLab + BINP
3.7 | Diagnostics
3.8 | RF system for booster and buncher
3.9 | Upgrade of the gun for operation with interchangable photocathodes
3.9.1 | Review of the gun upgrade design | IJCLab and STFC
3.9.2 | Procurement of missing and additional gun upgrade components | IJCLab and STFC
3.9.3 | Desing and procurement of transport vessel fo alkali photocathodes | IJCLab and STFC
3.9.4 | Design and procurement of the Load lock System for alkali photocathodes | IJCLab and STFC
3.9.5 | Procurement and preparation of alkali photocathodes | IJCLab and STFC
3.10 | Update of the design and procurement GaAs preparation system
3.10.1 | Design and procurement of the spin manipulator
3.10.2 | Update of the design and procurement GaAs preparation system | IJCLab - STFC
3.10.3 | Procurement of highly polarised GaAs-based photocathodes | IJCLab
3.10.4 | Procurement of the IR laser for polarised regime | IJCLab
3.10.5 | Design and procurement of Mott polarimeter
4. | RF Systems
4.1 | SRF Cavity
4.1.1 | RF cavity and HOMs design | JLAB and IJCLab
4.1.2 | Fabrication & tests of first dressed cavity | JLAB
4.1.3 | Power coupler | IJCLab and CERN
4.1.4 | Fabrication and tests of 3 further cavities | JLAB
4.1.5 | Fabrication and tests of the residual 4 cavities | JLAB
4.2 | Cryomodule
4.2.1 | Adapting SPL Cryomodule and installation | IJCLab and CERN
4.2.2 | Dedicated Cryomodule design | IJCLab and CERN
4.2.3 | Installation of the 2nd Cryomodule | IJCLab
4.3 | LLRF
4.3.1 | Synchronisation
4.3.2 | Feedbacks
4.4 | RF Power Sources
4.5 | Cryomodule-Cryogenics, Instrumentation and Controls
5 | Magnets | BINP-IJCLab-CERN
5.1 | Dipole magnets | BINP-IJCLab-CERN
5.2 | Quadrupole magnets | BINP-IJCLab-CERN
5.3 | Corrector magnets | BINP-IJCLab-CERN
5.4 | Spreaders & Combiners magnets | BINP-IJCLab-CERN
5.5 | Multipole magnets | BINP-IJCLab-CERN
5.6 | Injection / Extraction magnets | BINP-IJCLab-CERN
6 | Power Supplies
6.1 | Dipole Power Supplies | BINP-IJCLab
6.2 | Quadrupole Power Supplies | BINP-IJCLab
6.3 | Corrector Power Supplies | BINP-IJCLab
6.4 | Splitter Power Supplies | BINP-IJCLab
6.5 | Injection / Extraction Power Supplies | BINP-IJCLab
7 | Vacuum Systems & Beam Dump
7.1 | Arc Vacuum Chamber Assemblies
7.2 | Beam Splitter Chamber Assemblies
7.3 | Injection BL and Dump BL Dipole Chamber Assemblies
7.4 | Straight Vacuum Chamber Assemblies
7.5 | Vacuum System - Pumps and Gauges
7.6 | Global Vacuum System - Supplies & Support
8 | Controls
8.1 | Network Infrastructure
8.2 | Computer Hardware
8.3 | Network Services
8.4 | (EPICS) Services
8.5 | (EPICS) Device Support
8.6 | (EPICS) IOCs
8.7 | Operator Interface
8.8 | Control Applications
8.9 | Timing System
8.10 | Machine Protection System
9 | Instrumentation
9.1 | Injector Merger
9.2 | Beam Arrival Monitors
9.3 | Beam Current Monitors
9.4 | Beam Loss Monitors
9.5 | Beam Position Monitors
9.6 | View Screens
9.8 | Transfer line
9.7 | Beam Dump
10 | System integration
10.1. | Preliminary studies
10.2 | Shielding
10.3 | Electricity
10.4 | Water cooling system and fluids
10.5 | Cryogenic plant and distribution
10.6 | Beamline System Integration (Installation)
11 | Beam commissioning and operation
11.1 | Gun and Injector
11.2 | Diagnostics Line
11.3 | Main Linac Cryomodule
11.4 | Data Acquisation and analysis
11.5 | Single Pass, Energy Scan
11.6 | Single Pass, Energy Recovery
11.7 | Three Pass Energy Recovery
11.8 | Beam delivery to experiments
12 | Safety
12.1 | Documentation & Reviews
12.2 | Site shielding
12.3 | Personnel Safety Systems
12.4 | Radiation Monitor Safety
12.5 | Radiation Maintenance
13 | Accelerator development program
14 | Experiments
14.1 | Selection of first possible experiment
14.2 | Design of experiment integration
14.3 | Experimentation with PERLE

## Dictionnary
| WBS DICTIONNARY PERLE |  |  | PM_PERLE_20201706
ATRIUM xxx
W. Kaabi
C.Vallerand
2020-06-17
Authors : | W. Kaabi, C. Vallerand
Contributors : | WBS Managers
Approbators : | A. Stocchi, M. Klein, S. Bousson, W. kaabi (Management Board)
WBS | WBS Name | Institution | WBS Manager | Task Manager
1 | Project Management
1.1 | Milestones This scope is a placeholder for all project high level milestones. There is no cost or labor related to this WBS element.
1.2 | Project Management This scope primarily supports labor for two principle investigators, the project leader and the management board. Responsibilities include cost analysis and control, project schedule activities and monitoring, and high level scientific and engineering review of activities.
1.2.1
1.2.2
1.2.3
1.3 | Meetings & Reviews This scope includes time for staff to participate in review meetings and at scientific conferences, including preparation work. The estimate is based on one review per year.
1.4 | ASN Procedure
2. | Accelerator design
2.1 | Baseline Lattice Design
2.1.1 | Lattice and Optics
2.1.1.1 | Linear lattice optimization Initial magnet specs
2.1.1.2 | Momentum acceptance and longitudinal match
2.1.1.3 | Correction of nonlinear aberrations with multipole magnets
2.1.1.4 | Repository and data base with version control
2.1.2 | Beam Dynamics
2.1.2.1 | Start-to-End simulation with CSR & micro-bunching
2.1.2.2 | BBU studies
2.1.2.3 | Space-charge studies at injection
2.1.2.4 | Multi-particle tracking studies, error effects and halo formation
2.1.2.5 | Impedance analysis and wakefield effect mitigation
2.2 | Fractional Arc Lattice Design
2.3 | Single Pass Lattice Design
2.4 | Four Pass Lattice Design
3. | Electron source and injection
3.1 | DC Gun/ Injector Line Upgrade |  |  | This scope includes all labor and minor purchases required to get the DC electron source (gun) and beamline components up to the Injector Cryomodule (ICM) operational. It includes maintenance and repairs to the existing DC electron source (gun) and buncher cavity.
3.2 | Cathode Development
3.2.1 | Photocathode fabrication and load lock system design
3.3 | Booster
Booster studies and design
3.4 | Buncher
3.5 | Laser Modifications/Upgrade
3.6 | Injection line
3.5 | Diagnostic Line
4. | RF Systems
4.1 | Main Linac Cryomodule (MLC)
4.1.1 | SRF Cavity
4.1.1.1 | RF cavity design
4.1.1.2 | Fabrication & tests
4.1.1.3 | HOM study
4.1.1.4 | Power coupler design and study
4.1.2 | Cryomodule
4.1.2.1 | Cryomodule design
4.2 | LLRF
4.2.1 | Synchronisation
4.2.2 | Feedbacks
4.3 | RF Power Sources
4.4 | Cryogenics
4.5 | Cryomodule Instrumentation and Controls
5 | Magnets
5.1 | Dipole magnets
5.2 | Quadrupole magnets
5.3 | Corrector magnets
5.4 | Spreaders & Combiners magnets
5.5 | Multipole magnets
5.6 | Injection / Extraction magnets
7 | Power Supplies
7.1 | Dipole Power Supplies
7.2 | Quadrupole Power Supplies
7.3 | Corrector Power Supplies
7.4 | Splitter Power Supplies
7.5 | Injection / Extraction Power Supplies
8 | Controls
8.1 | Network Infrastructure
8.2 | Computer Hardware
8.3 | Network Services
8.4 | EPICS Services
8.5 | EPICS Device Support
8.6 | EPICS IOCs
8.7 | Operator Interface
8.8 | Control Applications
8.9 | Timing System
8.10 | Machine Protection System
9 | Instrumentation
9.1 | Injector and Mirror Merger
9.2 | Beam Arrival Monitors
9.3 | Beam Current Monitors
9.4 | Beam Loss Monitors
9.5 | Beam Position Monitors
9.6 | View Screens
9.7 | Beam Dumps
9.7.1 | Operational dump
9.7.2 | Setup dump
9.7.3 | Emergency dump
9.7.4 | Transfer line
10 | Vacuum Systems & Beam Dump
10.1 | Arc Vacuum Chamber Assemblies
10.2 | Beam Splitter Chamber Assemblies
10.3 | Injection BL and Dump BL Dipole Chamber Assemblies
10.4 | Straight Vacuum Chamber Assemblies
10.5 | Vacuum System - Pumps and Gauges
10.6 | Global Vacuum System - Supplies & Support
11 | System integration
11.1 | Global Infrastructure
11.1.1 | Preliminary studies
11.1.1.1 | Requirement specifications
11.1.1.2 | Faisability specifications
11.1.1.3 | Topographic studies
11.1.2 | Schielding
11.1.3 | Infrastructure preparation
11.1.3.1 | Electricity
11.1.3.2 | Water cooling system
11.1.3.3 | Cryogenic plant and distribution
11.2 | Beamline System Integration (Installation)
12 | Beam commissioning
12.1 | Gun, Injector Cryomodule (ICM), and Beam Stop (Complete)
12.2 | Diagnostics Line (Existing but Relocated)
12.3 | Main Linac Cryomodule (MLC)
12.4 | Fractional Arc
12.5 | Single Pass, Energy Scan
12.6 | Single Pass, Energy Recovery
12.7 | Four Pass Energy Recovery
13 | Safety
13.1 | Documentation & Reviews
13.2 | Site shielding
13.3 | Personnel Safety Systems
13.4 | Radiation Monitor Safety
13.5 | Radiation Maintenance
14 | Physics case studies
14.1 | Photo-nuclear physics
14.2 | e- probe on Self-Confining Radioactive Ion Target
14.3 | ep scattering, dark photon detection, proton radius

## Milestones
| WBS PERLE |  |  | PM_PERLE_20201706
ATRIUM xxx
W. Kaabi
C.Vallerand
2020-06-17
Authors : | W. Kaabi, C. Vallerand
Contributors : | WBS Managers
Approbators : | A. Stocchi, M. Klein, S. Bousson, W. kaabi (Management Board)
WBS | WBS Name | Responsible Institution | Point of contact | Milestones | % Complete
1 | Project Management
1.1 | Milestones
1.2 | Project Management
1.3 | Meetings & Reviews
1.4 | ASN Procedure
2. | Accelerator design
2.1 | Baseline Lattice Design
2.1.1 | Lattice and Optics
2.1.1.1 | Linear lattice optimization Initial magnet specs
2.1.1.2 | Momentum acceptance and longitudinal match
2.1.1.3 | Correction of nonlinear aberrations with multipole magnets
2.1.1.4 | Repository and data base with version control
2.1.2 | Beam Dynamics
2.1.2.1 | Start-to-End simulation with CSR & micro-bunching
2.1.2.2 | BBU studies
2.1.2.3 | Space-charge studies at injection
2.1.2.4 | Multi-particle tracking studies, error effects and halo formation
2.1.2.5 | Impedance analysis and wakefield effect mitigation
2.2 | Fractional Arc Lattice Design
2.3 | Single Pass Lattice Design
2.4 | Four Pass Lattice Design
3. | Electron source and injection
3.1 | DC Gun/ Injector Line Upgrade
3.2 | Cathode Development
3.2.1 | Photocathode fabrication and load lock system design
3.3 | Booster
Booster studies and design
3.4 | Buncher
3.5 | Laser Modifications/Upgrade
3.6 | Injection line
3.5 | Diagnostic Line
4. | RF Systems
4.1 | Main Linac Cryomodule (MLC)
4.1.1 | SRF Cavity
4.1.1.1 | RF cavity design
4.1.1.2 | Fabrication & tests
4.1.1.3 | HOM study
4.1.1.4 | Power coupler design and study
4.1.2 | Cryomodule
4.1.2.1 | Cryomodule design
4.2 | LLRF
4.2.1 | Synchronisation
4.2.2 | Feedbacks
4.3 | RF Power Sources
4.4 | Cryogenics
4.5 | Cryomodule Instrumentation and Controls
5 | Magnets
5.1 | Dipole magnets
5.2 | Quadrupole magnets
5.3 | Corrector magnets
5.4 | Spreaders & Combiners magnets
5.5 | Multipole magnets
5.6 | Injection / Extraction magnets
7 | Power Supplies
7.1 | Dipole Power Supplies
7.2 | Quadrupole Power Supplies
7.3 | Corrector Power Supplies
7.4 | Splitter Power Supplies
7.5 | Injection / Extraction Power Supplies
8 | Controls
8.1 | Network Infrastructure
8.2 | Computer Hardware
8.3 | Network Services
8.4 | EPICS Services
8.5 | EPICS Device Support
8.6 | EPICS IOCs
8.7 | Operator Interface
8.8 | Control Applications
8.9 | Timing System
8.10 | Machine Protection System
9 | Instrumentation
9.1 | Injector and Mirror Merger
9.2 | Beam Arrival Monitors
9.3 | Beam Current Monitors
9.4 | Beam Loss Monitors
9.5 | Beam Position Monitors
9.6 | View Screens
9.7 | Beam Dumps
9.7.1 | Operational dump
9.7.2 | Setup dump
9.7.3 | Emergency dump
9.7.4 | Transfer line
10 | Vacuum Systems & Beam Dump
10.1 | Arc Vacuum Chamber Assemblies
10.2 | Beam Splitter Chamber Assemblies
10.3 | Injection BL and Dump BL Dipole Chamber Assemblies
10.4 | Straight Vacuum Chamber Assemblies
10.5 | Vacuum System - Pumps and Gauges
10.6 | Global Vacuum System - Supplies & Support
11 | System integration
11.1 | Global Infrastructure
11.1.1 | Preliminary studies
11.1.1.1 | Requirement specifications
11.1.1.2 | Faisability specifications
11.1.1.3 | Topographic studies
11.1.2 | Schielding
11.1.3 | Infrastructure preparation
11.1.3.1 | Electricity
11.1.3.2 | Water cooling system
11.1.3.3 | Cryogenic plant and distribution
11.2 | Beamline System Integration (Installation)
12 | Beam commissioning
12.1 | Gun, Injector Cryomodule (ICM), and Beam Stop (Complete)
12.2 | Diagnostics Line (Existing but Relocated)
12.3 | Main Linac Cryomodule (MLC)
12.4 | Fractional Arc
12.5 | Single Pass, Energy Scan
12.6 | Single Pass, Energy Recovery
12.7 | Four Pass Energy Recovery
13 | Safety
13.1 | Documentation & Reviews
13.2 | Site shielding
13.3 | Personnel Safety Systems
13.4 | Radiation Monitor Safety
13.5 | Radiation Maintenance
14 | Physics case studies
14.1 | Photo-nuclear physics
14.2 | e- probe on Self-Confining Radioactive Ion Target
14.3 | ep scattering, dark photon detection, proton radius

## Duration
| WBS PERLE |  | PM_PERLE_20201706
ATRIUM xxx
W. Kaabi
C.Vallerand
2020-06-17
Authors : | W. Kaabi, C. Vallerand
Contributors : | WBS Managers
Approbators : | A. Stocchi, M. Klein, S. Bousson, W. kaabi (Management Board)
WBS | WBS Name | Duration | Hypothesis (nb ETP, maturity…) | Constraints
1 | Project Management
1.1 | Milestones
1.2 | Project Management
1.2.1
1.2.2
1.2.3
1.3 | Meetings & Reviews
1.4 | ASN Procedure
2. | Accelerator design
2.1 | Baseline Lattice Design
2.1.1 | Lattice and Optics
2.1.1.1 | Linear lattice optimization Initial magnet specs
2.1.1.2 | Momentum acceptance and longitudinal match
2.1.1.3 | Correction of nonlinear aberrations with multipole magnets
2.1.1.4 | Repository and data base with version control
2.1.2 | Beam Dynamics
2.1.2.1 | Start-to-End simulation with CSR & micro-bunching
2.1.2.2 | BBU studies
2.1.2.3 | Space-charge studies at injection
2.1.2.4 | Multi-particle tracking studies, error effects and halo formation
2.1.2.5 | Impedance analysis and wakefield effect mitigation
2.2 | Fractional Arc Lattice Design
2.3 | Single Pass Lattice Design
2.4 | Four Pass Lattice Design
3. | Electron source and injection
3.1 | DC Gun/ Injector Line Upgrade
3.2 | Cathode Development
3.2.1 | Photocathode fabrication and load lock system design
3.3 | Booster
Booster studies and design
3.4 | Buncher
3.5 | Laser Modifications/Upgrade
3.6 | Injection line
3.5 | Diagnostic Line
4. | RF Systems
4.1 | Main Linac Cryomodule (MLC)
4.1.1 | SRF Cavity
4.1.1.1 | RF cavity design
4.1.1.2 | Fabrication & tests
4.1.1.3 | HOM study
4.1.1.4 | Power coupler design and study
4.1.2 | Cryomodule
4.1.2.1 | Cryomodule design
4.2 | LLRF
4.2.1 | Synchronisation
4.2.2 | Feedbacks
4.3 | RF Power Sources
4.4 | Cryogenics
4.5 | Cryomodule Instrumentation and Controls
5 | Magnets
5.1 | Dipole magnets
5.2 | Quadrupole magnets
5.3 | Corrector magnets
5.4 | Spreaders & Combiners magnets
5.5 | Multipole magnets
5.6 | Injection / Extraction magnets
7 | Power Supplies
7.1 | Dipole Power Supplies
7.2 | Quadrupole Power Supplies
7.3 | Corrector Power Supplies
7.4 | Splitter Power Supplies
7.5 | Injection / Extraction Power Supplies
8 | Controls
8.1 | Network Infrastructure
8.2 | Computer Hardware
8.3 | Network Services
8.4 | EPICS Services
8.5 | EPICS Device Support
8.6 | EPICS IOCs
8.7 | Operator Interface
8.8 | Control Applications
8.9 | Timing System
8.10 | Machine Protection System
9 | Instrumentation
9.1 | Injector and Mirror Merger
9.2 | Beam Arrival Monitors
9.3 | Beam Current Monitors
9.4 | Beam Loss Monitors
9.5 | Beam Position Monitors
9.6 | View Screens
9.7 | Beam Dumps
9.7.1 | Operational dump
9.7.2 | Setup dump
9.7.3 | Emergency dump
9.7.4 | Transfer line
10 | Vacuum Systems & Beam Dump
10.1 | Arc Vacuum Chamber Assemblies
10.2 | Beam Splitter Chamber Assemblies
10.3 | Injection BL and Dump BL Dipole Chamber Assemblies
10.4 | Straight Vacuum Chamber Assemblies
10.5 | Vacuum System - Pumps and Gauges
10.6 | Global Vacuum System - Supplies & Support
11 | System integration
11.1 | Global Infrastructure
11.1.1 | Preliminary studies
11.1.1.1 | Requirement specifications
11.1.1.2 | Faisability specifications
11.1.1.3 | Topographic studies
11.1.2 | Schielding
11.1.3 | Infrastructure preparation
11.1.3.1 | Electricity
11.1.3.2 | Water cooling system
11.1.3.3 | Cryogenic plant and distribution
11.2 | Beamline System Integration (Installation)
12 | Beam commissioning
12.1 | Gun, Injector Cryomodule (ICM), and Beam Stop (Complete)
12.2 | Diagnostics Line (Existing but Relocated)
12.3 | Main Linac Cryomodule (MLC)
12.4 | Fractional Arc
12.5 | Single Pass, Energy Scan
12.6 | Single Pass, Energy Recovery
12.7 | Four Pass Energy Recovery
13 | Safety
13.1 | Documentation & Reviews
13.2 | Site shielding
13.3 | Personnel Safety Systems
13.4 | Radiation Monitor Safety
13.5 | Radiation Maintenance
14 | Physics case studies
14.1 | Photo-nuclear physics
14.2 | e- probe on Self-Confining Radioactive Ion Target
14.3 | ep scattering, dark photon detection, proton radius