## Slide 1
Super Separator Spectrometer
Fundamental research in Nuclear & Atomic physics
High selectivity > 1013
High efficiency 50%
Mass resolution > 1/350
Versatility
Unique instrumentation (SIRIUS – LEB – FISIC)
SC LINAC
NFS
DESIR
H. Savajols (GANIL)
1

## Slide 2
Target station
Beam Dump
Electric Dipole
Superconducting Multipole Triplets
and Power-Supply Systems (x7)
Cryogenics
S3-Spectrometer
Open RT Triplet
Dipole 1
Dipole 2
Dipoles 3
Level of completion
2

## Slide 3
Beam dump
Downstream
Upstream
Cooling system
Cooling system completed
Upstream and downstream beam dump chamber completed
Next steps
Chambers installed on S3 line in Q1 2021 with vacuum tests
Translation mechanisms & 11 dump parts
(5 fingers, 4 shutters, 2 stationary plates) & shielding integration
planned in Q4 2021 at Irfu and Q1 2022 at GANIL
3

## Slide 4
3 SMT tested end 2020
All 7 Power Supplies Systems (PSS) installed on the beam line
PSS commissioning (90% completed) to be finalized in 2021
Nest steps
Second cryogenic test station in Q1 2021
3D mapper ready in April 2021 for magnetic field measurement & alignment
All SMT delivery by end 2021
SMT's, PSS and Cryogenics
4 SMT installed in the cave end 2020
4

## Slide 5
Electric dipole
Chamber, Ti electrodes and all hardware completed at IJCLab
New strategy for the ED with industrial +/- 300 kV high voltage with no impact on the scientific program
E-Dipole on the spectro line Q2 2022
Dipole horizontal gap 20 cm
Radius of curvature ρ = 4 m
Bend angle θ = 22 degrees
Vertical acceptance 25 cm
5

## Slide 6
Installation & final tests
Installation and tests are progressing well
All cable trays and electrical panels installed, cable connections on cabinets and part of S3 ongoing (35 over 74km done)
Vacuum tests of first section done
Work in progress to optimize the planning :
Installation process to be adapted to minimize risk to work beyond 40m with the end of the exemption in 2023 without emergency exit
6

## Slide 7
SIRIUS: highlights and next milestones
Next steps :
Test of all electronics channels at Irfu Q1 2021
Reception of all the part of SIRIUS at GANIL (Q2 2021). Source commissioning and in-beam tests in a realistic implantation-decay experiment  174Yb(40Ar,4-5n)209-210Ra
Resolution measurement of the detector installed in the SIRIUS chamber with the final electronics and the complete acquisition system (V6 SIRIUS + V5 and NARVAL acquisition from GANIL).
Resolution obtained (20.5 keV) meet the specifications
7
Zoé Favier talk

## Slide 8
S3LEB commissioning @ LPC: RFQ series transmission tests done in 2020
Laser spectroscopy of Er with GISELE: Spectral resolution improved (5 GHz -> 1,5 GHz)
Narrow bandwidth cw TiSa developments with a new collaboration (Nagoya University–Mainz University)
New PhD Student within LISA network (Marie Curie Initiative Training Network): Anjali Ajayakumar
PILGRIM (MR-Tof-MS) precision improved (dm/m ≈ 10-7)
Laser room : call for tender launched (Nov 2020)
S3Leb Technical Workshop (72 participants) in December 2020
Next steps:
Development of narrow bandwidth laser system and test at GISELE : end Q3 2021
Development of efficient ionisation scheme for day one experiment
Test in gas cell @ LPC with Er : Q2 2021
Test in gas jet high resolution @ LPC with Er : Q4 2021
LEB : highlights and next milestones
LEB@LPC
NB CW TiSa
PILGRIM
Er spectra @ GISELE
Worshop
8
Jekabs Romans talk

## Slide 9
Conclusion
9
Development of the S3 project is progressing well
  Spectrometer : ready for beam commissioning mid 2023
  SIRIUS : tests of all the system planned in 2021 at GANIL
  LEB : In jet laser spectroscopy of Er planned end 2021 at LPC
New strategy for the ED with industrial +/- 300 kV high voltage with no
impact on the scientific program
New strategy for FISIC : first installation at CRYING/FAIR
Scientific co-organization between S3 and DESIR :
  working document prepared by collaboration representatives 29/01/2021
  Common scientific steering committee 23/02/2021
Scientific program and campaigns setting
  3 months day1 campaign selected for each set-up (SIRIUS & LEB) in 2018 and presented to the GANIL SC in 2019
  Choice for the first set-up to be done beginning 2022
Notes: Question to the management/evaluation commitee :need for an official channel to submit proposals/LoIs – a clear time plan for the management