## Slide 1: WP3 - DC GUN
Task leader : M. Baylac, CNRS – LPSC, Grenoble - France - B. Militsyn, STFC, Daresbury – UK
D. Reynet, W. Kaabi , A. Gallas, G. Iaquaniello, R. Marie, D. Nutarelli, K. Cassou, A. Martens, V. Soskov
CNRS – IJCLab, Orsay - France
E. Labussière, CNRS – LPSC, Grenoble - France
B. Fell, L. Jones, K. Middleman, T. Noakes, R. Smith STFC, Daresbury – UK
B. Hounsell, M. Klein, University of Liverpool (UK)

## Slide 2: Perle installation at IJClab-Orsay
The installation of PERLE under study in Super ACO building
PERLE
(superAco)
Identification of main constraints :
Square meters for auxiliary components (magnet power supply, RF amplifiers, cryoplant…)
Mass of components and mass of concrete shielding to compare to the strength of the concrete slab
and needs :
Infrastructure for the machine (electrical, cooling water, pressurized air, optical fiber…).
Perle Footprint in super ACO

## Slide 3: Gun installation at IJClab - Orsay
The installation of gun began in another building : the Igloo : gun could be tested independently
PERLE
(superAco)
Photogun (Igloo)
The igloo is a fully equiped bunker (radioprotection, crane, electrical power, compressed air …)
Dedicated control room…
the implementation of the DC-GUN began in another building: the igloo

## Slide 4: Summary of 7 months of work on the gun : Equipment transferred to the igloo
March 2022

## Slide 5: High Voltage vessel installation
June 2022
Lift up
Opening and cleaning

## Slide 6: High Voltage Power Supply assembly
July 2022
Mechanical assembly : OK
Electrical test : OK

## Slide 7
September 2022
Check of HV vessel tightness
It takes time to lower the pressure (degassing of the columns)
Difficulty in starting leak detection
But no “big leak”
Admissible pressure to transfer SF6 into the tank

## Slide 8: High Voltage conditionning
SF6 system
  Discussions underway with vendor
  Call for tender expected end 2022
Next steps
  Preliminary tests (limited at low voltage (up to 30 kV) by french regulations) in November
  Permit from Nuclear Safety Authorization (ASN) required for operation at high voltage
    Nuclear safety file being prepared
  Permit expected by mid 2023  HV conditioning to follow
Writing the specifications for the laser
          Discussions underway with vendor
          Call for tender expected end 2022
Laser

## Slide 9: Gun commissioning
Main steps & schedule
  Gun fully assembled, under vacuum and operational
  procurement of the SF6 system
  procurement and installation of the Laser and the optical system
  Obtain permit from the French nuclear safety authority (ASN)
  HV conditoning for operation at 350 kV
  Initial functional tests with a robust photocathode (vent-bake gun)
 Goal : first functional test (electrons on a viewer) by early 2024