## Slide 1
Summary of the ARIEL project
Arnd Junghans, Helmholtz-Zentrum Dresden-Rossendorf
January, 17, 2024, IJCLab Orsay
This project has received funding from the Euratom research and
training programme 2014-2018 under grant agreement No 847594 (ARIEL).
www.ariel-h2020.eu
Accelerator and Research reactor Infrastructures for
Education and Learning
ARIEL
Notes: 1

## Slide 2
Management Board (MB):
A. Junghans (HZDR), A. Plompen (JRC), E. Pirovano (PTB), C. Guerrero (USE), H. Penttilä (JYU)
Project Advisory Committee (PAC):
D. Cano-Ott (CIEMAT), R. Capote (IAEA), R. Jacqmin (CEA), M. Kerveno (CNRS), G. Van den Eynde (SCK CEN)
ARIEL factsheet
Grant agreement ID: 847594
Funded under:
H2020-Euratom-1.8 (NFRP-2018-7)
EC budget contribution: Coordinated by:
2 M€ HZDR
Project type: Partners:
Coordination & Support Action 26 from 15 countries
Project duration: Start /End date:
54 months September 1, 2019 – February 29, 2024
Access to neutron facilties
ESR training visits
Research visits
Summer schools
Collaboration with JEFF, IAEA & TSOs and other EC projects
Research Reactors
Accelerators
Scientific workshops
Diverse scientific community

## Slide 3
www.ariel-h2020.eu

## Slide 4
SUMMARY OF H2020-ARIEL FACILITIES AVAILABLE FOR TAA |  | ACCELERATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | RESEARCH REACTORS |  |  |  | 
 |  | e- BEAMS |  | ION BEAMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | nELBE@HZDR | GELINA@JRC | MONNET@JRC | n_TOF@CERN | AIFIRA@CNRS | ALTO@CNRS | GENESIS@CNRS | NFS@GANIL | CEA-DAM | FNG@ENEA | PTB | FNG@NPI | HISPANOS@CNA | NESSA@UU | U. Oslo | NPL | IFIN-HH | JYU | AMANDE@IRSN | BRR@MTA-EK | BR1@SCK·CEN | TRIGA@JGU | LR-0/LVR-15@CVR | RHF@ILL
Neutrons | Cold (<25 meV) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Thermal (‹En›=25 meV) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Epithermal (25 meV – 100 keV) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Fast (0.1-20 MeV) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Very fast (>20 MeV) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Pulsed beam |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Time-of-flight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Charged particles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Radioactive beam |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5
TRAINING
Mobility support for up to 30 research stays for up to 12 weeks for Early Stage Researchers, external senior experts, technical staff
[WP4: 303 k€]
TRANSNATIONAL ACCESS
About 3000 hours of beam time will be funded for TAA at any of the 25 partner laboratories
[WP3: 903 k€]
EDUCATION
4 Summer Schools
CIEMAT, CAN HISPANOS, JGU Triga reactor, Uppsala NESSA
[WP5: 525 k€]
H2020-ARIEL
Training & Education of Nuclear Data Experts
[WP1 & WP2: 261 K€]

## Slide 6: ARIEL achievements:
Education and Training: 261 weeks endorsed in 30 proposals
Transnational access to neutron beam facilities: 3369 beam time hours in 35 experiments 4767 beam time hours delivered !
ESR training visits
Access to neutron facilties
Provide young scientists, researchers and experts with access to high quality nuclear research and training facilities.
Experiments in international teams: Hands-on training for students in the graduate and postgraduate level - lead to PhD and master theses.
Integration of the full nuclear data cycle by collaboration with JEFF (OECD/NEA), IAEA, IRSN
Collaboration with research reactor facilities and with ENEN
Increase number of students in the nuclear data field
Increase support for early stage researchers
Inclusion of technical staff (engineers, operators) in ARIEL activities
Four summer schools organized by Madrid, Seville, Budapest and Mainz
Summer schools

## Slide 7: ARIEL support for PhD theses
Project | Name | University | Project | Name | University
TAA_1_2 | Tomas Czakoj | Rez | TAA_6_5, SV_6_3 | Styliani Goula | Ioannina
TAA_1_3 | Aurélien Chevalier | Caen | TAA_6_7, SV_2_4 | David Knežević | Belgrade
TAA_1_4 | Oscar Putignano | Milano | SV_1_1 | Miguel Astrain Etxezarreta | Madrid
TAA_1_5 | Matt Birch | Teddington | SV_1_3 | Adrian Bembibre | Santiago de Compostela
TAA_1_6 | Augusto Di Chicco | Cadarache | SV_2_6 | Riccardo Mucciola | Perugia
TAA_2_2 | Francois Claeys | Strasbourg | SV_2_8 | María Ángeles Millán Callado | Sevilla
TAA_2_3 | Zhihao Gao | Uppsala | SV_3_1,TAA_6_8 | Pablo Perez Maroto | Sevilla
TAA_3_3,TAA_7_2 | Moad Al-dbissi | Chalmers | SV_4_1 | Adrian Sánchez Caballero | Madrid
TAA_3_4,SV_1_2, SV_5_2 | Ana Maria Gomez | Uppsala | SV_5_6, SV_7_5 | Νikolaos Kyritsis | Athens
TAA_4_1, TAA_4_2, TAA_6_8, SV_7_4 | Maria-Elisso Stamati, Nikolaos Kyritsis | Ioannina / Athens | SV_5_7, TAA_7_11 | Kalliope Kaperoni | Athens
TAA_4_3, TAA_7_11 | Sotirios Chasapoglou | Athens | SV_5_1,SV_7_1 | Georgios Gkatis | Cadarache
TAA_4_5 | Martin von Tresckov | Darmstadt | TAA_7_1 | Jiří Jarošík | Prague
TAA_5_2, TAA_7_8 | DorIan Belverge | Cadarache | TAA_7_3 | Diane QUEVAUVILLERS | Aix Marseille
TAA_2_3 | Simone Cannarozzo | Uppsala | TAA_7_4, SV_7_3 | Marco Antonio Martinez Canadas | Granada
TAA_5_4 | Kevin Irazoqui | Cadarache | TAA_7_7 | William Hillman | Manchester
TAA_6_2,SV_6_1 | Antònia Verdera | Granada | TAA_7_8, TAA_7_10 | Lucas de Arruda Serra Filho | Caen+Uppsala
TAA_6_4 | Thomas Ligonnet | Lausanne |  |  | 
Theses work supported for 33 PhD students.

## Slide 8
Publications with ARIEL support
Sebastian Urlass, Arnd Junghans, Federica Mingrone, Paul Peronnard, Daniel Stach, Laurent Tassan-Got, David Weinberger, The n_TOF Collaboration,
Nuclear Inst. and Methods in Physics Research, A 1002 (2021) 165297
Gómez-Camacho, J., García López, J., Guerrero, C. et al. Research facilities and highlights at the Centro Nacional de Aceleradores (CNA). Eur. Phys. J. Plus 136, 273 (2021).
X. Ledoux, J. C. Foy, J. E. Ducret, A. M. Frelin, D. Ramos, J. Mrazek, E. Simeckova, R. Behal, L. Caceres, V. Glagolev, B. Jacquot, A. Lemasson, J. Pancin, J. Piot, C. Stodel, M. Vandebrouck, First beams at neutrons for science, Eur. Phys. J. A (2021) 57:257
Aleš Jančář, Jiří Čulen, Filip Mravec, Michal Košťál, Daniel Dlhopolček, Elisa Pirovano, Ralf Nolte, František Cvachovec, Václav Přenosil, Zdeněk Matěj, Tests of Various Scintillator Detectors in Selected Mono-Energetic Neutron Beams, ANIMMA 2021, EPJ Web of Conferences 253, 07007 (2021)
Jaroslav Jánský , Jiřı́ Janda , Zdeněk Matěj , Filip Mravec , Michal Košťál ,
František Cvachovec, Measurement and simulation of the new liquid organic scintillator response to fast neutrons, ANIMMA2021, EPJ Web of Conferences 253, 11006 (2021)
Carola Franzen, Arnd R. Junghans, Enrique M. Gonzalez, and Arjan J. M. Plompen, ARIEL & SANDA nuclear data activities, EPJ Nuclear Sci. Technol. 8, 19 (2022)
E. Grosse, A.R. Junghans, Broken axial symmetry as essential feature for a consistent modelling of various observables in heavy nuclei, Phys. Lett. B 833 (2022) 137328
Augusto Di Chicco, Alix Sardet, Michaël Petit, Robert Jacqmin, Vincent Gressier,
Brian Stout, Gamma-response characterization of a solution-grown stilbene based detector assembly in the 59 keV–4.44 MeV energy range; an alternative low-resolution gamma spectrometer, Nuclear Instruments and Methods in Physics Research A 1034 (2022) 166740
R. Mucciola, C. Paradela, G. Alaerts, S. Kopecky, C. Massimi, A. Moens,
P. Schillebeeckx, R. Wynants, Evaluation of resonance parameters for neutron interactions with
Molybdenum, Nuclear Instruments and Methods in Physics Research B 531 (2022) 100–108
R. Mucciola, C. Paradela, and the n_TOF Collaboration, Neutron capture and total cross-section measurements on 94;95;96Mo at n_TOF and GELINA EPJ Web of Conferences 284 (2023) 01031
M.A. Millán-Callado, C. Guerrero, B. Fernández, J. Gómez-Camacho a,b, M. Macías, J.M. Quesada, Continuous and pulsed fast neutron beams at the CNA HiSPANoS facility, Radiation Physics and Chemistry 217 (2024) 111464

## Slide 9: Scientific meetings
ARIEL Kick-off meeting September 11-12, 2019
Fondation Universitaire, Bruxelles
https://www.ariel-h2020.eu/index.php/en/2-uncategorised/13-kick-off-meeting
Joint ARIEL / SANDA meeting 07.03.-11.03.2022.
Virtual meeting https://agenda.ciemat.es/event/3827/
Second ARIEL progress meeting and scientific workshop, 15.-16.03.2023 NPL, Teddington
https://indico.cern.ch/event/1242540/
Final meeting IJCLab Orsay, 17.-19. January 2024
https://indico.ijclab.in2p3.fr/event/9751/timetable/#all

## Slide 10: ARIEL schools
2/2022 @CIEMAT, Madrid, Spain
Nuclear data: the path from the detector to the reactor calculation (24 participants)
9/2022 @CNA, Seville, Spain
Hands-on school on the production, detection and use of neutron beams
(24 participants)
9/2023 @ BME-NTI and MTA EK, Budapest, Hungary H2020 ARIEL Hands-on School on Nuclear Data from Research Reactors (23 participants)
11/2023 @JGU, Mainz, Germany
  Lab course in Reactor Operation and Nuclear Chemistry
  (10 participants)
EXTEND school was canceled. (Neutron generator unavailable)
Delays in school realization due to COVID restrictions

## Slide 11: Share of proposals
Facility | Proposals accepted | Proposals not accepted |  | Education and Training activities
AGOR (Groningen) |  | 2 |  | 
AIFIRA (Bordeaux) |  |  |  | 
ALTO (Orsay) | 1 |  |  | (1)
AMANDE (Cadarache) | 1 | 1 |  | 
BNC (Budapest) | 1 |  |  | 1
CEA-DAM (Arpajon) |  |  |  | 
CVR (Rez) | 1 |  |  | 
FNG (Frascati) |  |  |  | 
GENESIS (Grenoble) |  |  |  | 
HISPANoS (Seville) | 4 | 3 |  | 
IFIN-HH (Bucarest) | 2 |  |  | 
ILL (Grenoble) | 3 | 2 |  | 
JGU (Mainz) |  |  |  | 1
JRC (Geel) | 4 | 1 |  | 16
JYFL (Jyväskylä) | 1 |  |  | 
n_TOF (Geneva) | 2 | 2 |  | 8
nELBE (Dresden) | 1 | 1 |  | 3
NESSA (Uppsala) |  |  |  | 
NFS (Caen) | 1 |  |  | 
NPL (Teddington) | 1 |  |  | 
PIAF (Braunschweig) | 6 | 3 |  | 1
SCK-CEN (Mol) | 3 |  |  | 
U. Oslo |  |  |  | 
UJF (Rez) |  |  |  | 
Status: January 2024

## Slide 12: Performance indicators (status January 2024)
28 completed experiments involved 125 users from 12 countries, including 52 early stage researchers and 71 first time users at the respective facilities.
Early stage researchers from Czech Rep.(2), Finland (1), France (15), Germany (5), Greece(4), Italy(4), Norway (4), Poland (3), Romania (2), Spain (6), Sweden (6) , South Africa (1) and the United Kingdom (5) conducted experiments or took part in education and training activities.(preliminary)
Notes: Numbers are based on 10 *completed* experiments and 11 *completed* education and training visits.
The typical supported number of users per experiment is 4.
(There are more users, as some experiments involved users that where not supported by ARIEL,
but took part in the project)

## Slide 13: ARIEL project performance indicators
ARIEL has been extended by 6 months: project duration: 54 months
March 2023 (month 43): endorsed beam time hours: 2739
January 2024(month 53): endorsed beam time hours: 3369
28 completed experiments of 35 endorsed experiments 1386 beam time hours delivered (month 43) 4767 hours (month 53) participants of experiments: 128, early stage researchers: 52
Average user satisfaction score: 1,2
Number of deliverables: 19

## Slide 14: Budget summary (Januar 2024)
TAA User support: 203 000 EUR budget 142 000 EUR committed (70 %) (90 000 EUR paid) remaining budget: 60 000 EUR (assumption 4 user per experiment too high, some experiments did not use what they applied for)
TAA Facility support: 532 000 EUR budget 495 000 EUR committed (93%) ( 285 000 EUR paid) remaining budget: 37 000 EUR
Education and Training/scientific visits: 264 000 EUR budget 270 000 EUR committed (102 %) 237 000 EUR paid no remaining budget
Open access cost for publications: 30 000 EUR mostly not requested

## Slide 15: Finalizing the ARIEL project
Reporting and Deliverables, see presentation Carola Franzen
Travel support for users and Education & Training / scientific visits: PLEASE send us your reimbursement claims now ! Deadline: February 15, 2024
Facility reimbursement via Facility reimbursement form or in the final reporting, deadline: April 10, 2024
OPEN ACCESS PUBLICATION cost for ARIEL supported research can be paid by the project. Please contact the project coordinator
Report all ARIEL supported publications to the project coordinator and communication Manager (C. Guerrero)
Funding statement: This project has received funding from the Euratom research and training programme 2014-2018 under grant agreement No. 847594 (ARIEL).

## Slide 16: ARIEL Scientific reporting
For every experiment (TAA): Facility report + one User report
Education and Training: Scientific Visitor report
Reports are short and easy to write: Forms are available
The following reports are due and need to be send now:
User reports | Facility reports
TAA_4_1 N. Patronis | TAA_4_1 CERN n_TOF
TAA_6_5 N. Patronis | TAA_6_5 + TAA_6_9 ILL
TAA_7_8 P. Leconte | TAA_7_9 + TAA_7_10 NFS (GANIL)
 | TAA_7_11 CERN n_TOF

## Slide 17: ARIEL Scientific reporting
The following Education and Training / Scientific Visitor reports are due and need to be sent now:
SV_1_3 D. Tarrio
SV_2_1 N. Carjan (draft of publication received)
SV_5_2 A. Gomez
SV_5_4 N. Carjan
SV_5_9 A. Al-Adili
SV_6_1 A. Verdera-Garau
SV_6_3 S. Goula

## Slide 18: Management Board
Project Coordinator: Arnd Junghans, HZDR
Scientific Coordinator: Arjan Plompen, JRC
Transnational Access Coordinator: Elisa Pirovano, PTB
Communication Manager: Carlos Guerrero, USE
Training Coordinator: Heikki Penttilä, JYU
Carola Franzen, Roland Beyer, Katja Gröger, Sebastian Urlass, HZDR
Project Advisory Committee
Management Team
Daniel Cano-Ott, CIEMAT
Roberto Capote, IAEA
Robert Jacqmin, CEA
Maëlle Kerveno, CNRS
Gert van den Eynde, SCK CEN
I personnally would like to thank all my colleagues
for the always fruitful collaboration and their
Invaluable help with the ARIEL project
Please relate to EURO-LABS, OFFERR and ENEN
For future research support on nuclear data

## Slide 19: End of presentation